## STR
Inspection Request - STR | [9 empty] | A | Approved |  | Date: | 2026-04-02
[10 empty] | B | Approved with notes
[10 empty] | C | Reject & Resubmit
[10 empty] | CC | Not Resubmitted
[10 empty] | UR | Under Review
DOCUMENT REFERENCE NO |  |  | Element | Location | DESCRIPTION | Attachment |  | Outgoing to Consultant |  | Code Action | Status | Progress | Over Duration | scan | Duration
No. | Referance | REV |  |  |  | Dwg | Report | Submission date | Received Date
1 | WIR-Civil-001 | 0 | STR | Zone 2 Building : GA-(01-02-03-04-05-06-13-14-15-17-18) | Compaction to 4 layers |  |  | 2025-11-08 | 2025-11-09 | B | CLOSED | 1 | 0 | IN
2 | WIR-Civil-002 | 0 | STR | Zone 2 Building : GA-( 01-02-03-04-05-06 ) | Prevention Termites , Polythene Sheet |  |  | 2025-12-12 | 2025-12-13 | B | CLOSED | 1 | 0 | IN
3 | WIR-Civil-003 | 0 | STR | Zone 2 Building : GA-( 01-02-03-04-05-06 ) | Form Work of P.C Footing |  |  | 2025-12-12 | 2025-12-12 | B | CLOSED | 1 | 0 | IN
4 | WIR-Civil-004 | 0 | STR | Zone 2 Building : GA-( 01-02-03-04-05-06 ) | Form and Steel Work of R.C Footing |  |  | 2025-12-12 | 2025-12-12 | B | CLOSED | 1 | 0 | IN
5 | WIR-Civil-005 | 0 | STR | Zone 2 Building : GA-( 01-02-03-04-05-06 ) | Surface Preparation for R.C Footing Before Insulation |  |  | 2025-12-12 | 2025-12-12 | B | CLOSED | 1 | 0 | IN
6 | WIR-Civil-006 | 0 | STR | Zone 2 Building : GA-( 01-02-03-04-05-06 ) | 1st Layer Insulation of R.C Footing |  |  | 2025-12-12 | 2025-12-15 | B | CLOSED | 1 | 0 | IN
7 | WIR-Civil-007 | 0 | STR | Zone 2 Building : GA-( 01-02-03-04-05-06 ) | 2nd Layer Insulation of R.C Footing |  |  | 2025-12-12 | 2025-12-15 | B | CLOSED | 1 | 0 | IN
8 | WIR-Civil-008 | 0 | STR | Zone 2 Building : GA-( 01-02-03-04-05-06 ) | Form and Steel Work of Grade Beam |  |  | 2025-12-12 | 2025-11-20 | B | CLOSED | 1 | 0 | IN
9 | WIR-Civil-009 | 0 | STR | Zone 2 Building : GA-( 01-02-03-04-05-06 ) | Surface Preparation for Grade Beam Before Insulation |  |  | 2025-12-12 | 2025-11-15 | B | CLOSED | 1 | 0 | IN
10 | WIR-Civil-010 | 0 | STR | Zone 2 Building : GA-( 01-02-03-04-05-06 ) | 1st Layer Insulation of Grade Beam |  |  | 2025-12-12 | 2025-11-15 | B | CLOSED | 1 | 0 | IN
11 | WIR-Civil-011 | 0 | STR | Zone 2 Building : GA-( 01-02-03-04-05-06 ) | 2nd Layer Insulation of Grade Beam |  |  | 2025-12-12 | 2025-11-15 | B | CLOSED | 1 | 0 | IN
12 | WIR-Civil-012 | 0 | STR | Zone 2 Building : GA-( 01-02-03-04-05-06 ) | Steel Work of Columns |  |  | 2025-12-12 | 2026-03-07 | B | CLOSED | 1 | 0 | IN
13 | WIR-Civil-013 | 0 | STR | Zone 2 Building : GA-( 01-02-03-04-05-06 ) | Form Work of Columns |  |  | 2025-12-12 | 2025-11-20 | B | CLOSED | 1 | 0 | IN
14 | WIR-Civil-014 | 0 | STR | Zone 2 Building : GA-( 01-02-03-04-05-06 ) | Steel Work of Upper Beam |  |  | 2025-12-12 | 2025-11-20 | B | CLOSED | 1 | 0 | IN
15 | WIR-Civil-015 | 0 | STR | Zone 2 Building : GA-( 01-02-03-04-05-06 ) | Form Work of Upper Beam |  |  | 2025-12-12 | 2025-11-20 | B | CLOSED | 1 | 0 | IN
16 | WIR-Civil-016 | 0 | STR | Zone 2 Building : GA-( 01-02-03-04-05-06 ) | Steel works of S.O.G |  |  | 2025-12-12 | 2025-11-20 | B | CLOSED | 1 | 0 | IN
17 | WIR-Civil-017 | 0 | STR | Zone 2 Building : GA-( 01-02-03-04-05-06 ) | installation of H.C.S |  |  | 2025-12-12 | 2025-11-20 | B | CLOSED | 1 | 0 | IN
18 | WIR-Civil-018 | 0 | STR | Zone 2 Building : GA-( 01-02-03-04-05-06 ) | Steel works of Screed after H.C.S |  |  | 2025-12-12 | 2025-11-20 | B | CLOSED | 1 | 0 | IN
19 | WIR-Civil-019 | 0 | STR | Zone : 3 Building : vip ( Q Vv01 ) – ( Q VF02-03-04-05-17-18-19-20-21 ) | Compaction |  |  | 2025-11-23 | 2025-11-23 | B | CLOSED | 1 | 0 | IN
20 | WIR-Civil-020 | 0 | STR | Zone : 3 Building : twins Q-VS ( 01-02-03-04-09-10-11-12-13-19-20-21-22-33-34-35-36 ) | Compaction |  |  | 2025-11-23 | 2025-11-23 | B | CLOSED | 1 | 0 | IN
21 | WIR-Civil-021 | 0 | STR |  | الرد على NCR 001 |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
22 | WIR-Civil-021 | 1 | STR |  | الرد على NCR 001 |  |  | 2025-12-10 | 2026-02-19 | B | CLOSED | 1 | 0 | IN
23 | WIR-Civil-022 | 0 | STR |  | الرد على NCR 002 |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
24 | WIR-Civil-022 | 1 | STR |  | الرد على NCR 002 |  |  | 2025-12-10 |  | S | CLOSED | 1 | 0 | IN
25 | WIR-Civil-022 | 2 | STR |  | closing NCR 002 |  |  | 2025-12-10 | 2026-02-19 | B | CLOSED | 1 | 0 | IN
26 | WIR-Civil-023 | 0 | STR | مكرر وسيتم الغاءه | NCR 005 |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
27 | WIR-Civil-023 | 1 | STR | مكرر وسيتم الغاءه | الرد على NCR 005 |  |  | 2025-12-10 | 2025-12-03 | C | CLOSED | 1 | 0 | IN
28 | WIR-Civil-024 | 0 | STR |  | الرد على NCR 04 |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
29 | WIR-Civil-024 | 1 | STR |  | الرد على NCR 04 |  |  | 2025-12-10 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
30 | WIR-Civil-024 | 2 | STR |  | الرد على NCR 04 |  |  | 2026-03-25 | 2026-03-25 | B | CLOSED | 1 | 0 | IN
30 | WIR-Civil-025 | 0 | STR | Zone : 4 Building : Q-VF01 | plan concrete Footing |  |  | 2025-11-29 | 2025-12-03 | B | CLOSED | 1 | 0 | IN
31 | WIR-Civil-026 | 0 | STR | Zone : 4 Building : Q-VF01 | Steel Work of R.C raft |  |  | 2025-11-30 | 2025-11-30 | C | CLOSED | 1 | 0 | IN
32 | WIR-Civil-027 | 0 | STR | Zone : 4 Building : Q-VF01 | Surface Preparation for R.C Footing Before Insulation |  |  | 2025-11-30 | 2025-11-30 | B | CLOSED | 1 | 0 | IN
33 | WIR-Civil-028 | 0 | STR | Zone : 4 Building : Q-VF01 | 1st Layer Insulation of R.C raft |  |  | 2025-11-30 | 2025-11-30 | B | CLOSED | 1 | 0 | IN
34 | WIR-Civil-029 | 0 | STR | Zone : 4 Building : Q-VF01 | 2nd Layer Insulation of R.C raft |  |  | 2025-11-30 | 2025-11-30 | B | CLOSED | 1 | 0 | IN
35 | WIR-Civil-030 | 0 | STR | Zone : 4 Building : Q-VF01 | Form and Steel Work of Grade Beam |  |  | 2025-11-30 | 2025-11-30 | C | CLOSED | 1 | 0 | IN
| WIR-Civil-030 | 1 | STR | Zone : 4 Building : Q-VF01 | Form and Steel Work of Grade Beam |  |  | 2025-12-13 | 2025-12-15 | D
36 | WIR-Civil-031 | 0 | STR | Zone : 4 Building : Q-VS01 | Form Work of P.C raft |  |  | 2025-11-30 | 2025-11-30 | B | CLOSED | 1 | 0 | IN
37 | WIR-Civil-032 | 0 | STR | Zone : 4 Building : Q-VS01 | Form and Steel Work of R.C raft |  |  | 2025-11-30 | 2025-11-30 | B | CLOSED | 1 | 0 | IN
38 | WIR-Civil-033 | 0 | STR | Zone : 4 Building : Q-VS01 | Surface Preparation for R.C raft Before Insulation |  |  | 2025-11-30 | 2025-11-30 | B | CLOSED | 1 | 0 | IN
39 | WIR-Civil-034 | 0 | STR | Zone : 4 Building : Q-VS01 | 1st Layer Insulation of R.C raft |  |  | 2025-11-30 | 2025-11-30 | B | CLOSED | 1 | 0 | IN
40 | WIR-Civil-035 | 0 | STR | Zone : 4 Building : Q-VS01 | 2nd Layer Insulation of R.C raft |  |  | 2025-11-30 | 2025-11-30 | B | CLOSED | 1 | 0 | IN
41 | WIR-Civil-036 | 0 | STR | Zone : 4 Building : Q-VS01 | Form and Steel Work of Grade Beam |  |  | 2025-11-30 | 2025-11-30 | C | CLOSED | 1 | 0 | IN
| WIR-Civil-036 | 1 | STR | Zone : 4 Building : Q-VS01 | Form and Steel Work of Grade Beam |  |  | 2025-12-13 | 2025-12-15 | D
42 | WIR-Civil-037 | 0 | STR |  | الرد على 007 NCR |  |  | 2025-11-30 | 2025-11-30 | S | CLOSED | 1 | 0 | IN
43 | WIR-Civil-037 | 1 | STR |  | الرد على 007 NCR |  |  | 2025-12-22 | 2025-12-22 | S | CLOSED | 1 | 0 | IN
44 | WIR-Civil-037 | 2 | STR |  | الرد على 007 NCR |  |  | 2026-03-04 | 2026-03-04 | B | CLOSED | 1 | 0 | IN
45 | WIR-Civil-038 | 0 | STR | Zone : 03 Building : u-vf07 (vip) | prevention termites and polythene sheet |  |  | 2025-11-30 | 2025-11-30 | S | CLOSED | 1 | 0 | IN
46 | WIR-Civil-038 | 1 | STR | Zone : 03 Building : u-vf07 (vip) | prevention termites and polythene sheet |  |  | 2025-12-13 | 2025-12-14 | B | CLOSED | 1 | 0 | IN
47 | WIR-Civil-039 | 0 | STR | Zone : 03 Building : u-vf07 (vip) | Form Work of P.C Footing |  |  | 2025-11-30 | 2025-11-30 | S | CLOSED | 1 | 0 | IN
48 | WIR-Civil-039 | 1 | STR | Zone : 03 Building : u-vf07 (vip) | Form Work of P.C Footing |  |  | 2025-12-13 | 2025-12-14 | S | CLOSED | 1 | 0 | IN
49 | WIR-Civil-039 | 2 | STR | Zone : 03 Building : u-vf07 (vip) | Form Work of P.C Footing |  |  | 2026-11-03 | 16/3/2026 | B
50 | WIR-Civil-040 | 0 | STR | Zone : 03 Building : u-vf07 (vip) | Form and Steel Work of R.C raft |  |  | 2025-11-30 | 2025-11-30 | S | CLOSED | 1 | 0 | IN
51 | WIR-Civil-040 | 1 | STR | Zone : 03 Building : u-vf07 (vip) | Form and Steel Work of R.C raft |  |  | 2025-12-13 | 2025-12-14 | S | CLOSED | 1 | 0 | IN
52 | WIR-Civil-040 | 2 | STR | Zone : 03 Building : u-vf07 (vip) | Form and Steel Work of R.C raft |  |  | 2026-03-16 | 2026-03-16 | B
53 | WIR-Civil-041 | 0 | STR | Zone : 03 Building : u-vf07 (vip) | Insulation of R.C raft |  |  | 2025-11-30 | 2025-11-30 | S | CLOSED | 1 | 0 | IN
54 | WIR-Civil-041 | 1 | STR | Zone : 03 Building : u-vf07 (vip) | Insulation of R.C raft |  |  | 2025-12-13 | 2025-12-14 | B | CLOSED | 1 | 0 | IN
55 | WIR-Civil-042 | 0 | STR | Zone : 03 Building : u-vf07 (vip) | curing of R.C raft |  |  | 2025-11-30 | 2025-11-30 | S | CLOSED | 1 | 0 | IN
56 | WIR-Civil-042 | 1 | STR | Zone : 03 Building : u-vf07 (vip) | curing of R.C raft |  |  | 2025-12-13 | 2025-12-14 | S | CLOSED | 1 | 0 | IN
57 | WIR-Civil-042 | 2 | STR | Zone : 03 Building : u-vf07 (vip) | curing of R.C raft |  |  | 2026-11-03 | 16/3/2026 | B
58 | WIR-Civil-043 | 0 | STR | Zone : 03 Building : u-vf07 (vip) | structure Steel Work |  |  | 2025-11-30 | 2025-11-30 | S | CLOSED | 1 | 0 | IN
59 | WIR-Civil-043 | 1 | STR | Zone : 03 Building : u-vf07 (vip) | structure Steel Work |  |  | 2025-12-13 | 2025-12-14 | S | CLOSED | 1 | 0 | IN
60 | WIR-Civil-043 | 2 | STR | Zone : 03 Building : u-vf07 (vip) | structure Steel Work |  |  | 2026-11-03 |  | UR
61 | WIR-Civil-044 | 0 | STR | Zone : 03 Building : u-vf07 (vip) | prevention termites and polythene sheet |  |  | 2025-11-30 | 2025-11-30 | S | CLOSED | 1 | 0 | IN
62 | WIR-Civil-044 | 1 | STR | Zone : 03 Building : u-vf07 (vip) | prevention termites and polythene sheet |  |  | 2025-12-10 | 2026-03-07 | B | CLOSED | 1 | 0 | IN
63 | WIR-Civil-045 | 0 | STR | Zone : 03 Building : u-vf08 (vip) | Form Work of P.C Footing |  |  | 2025-11-30 | 2025-11-30 | S | CLOSED | 1 | 0 | IN
64 | WIR-Civil-045 | 1 | STR | Zone : 03 Building : u-vf08 (vip) | Form Work of P.C Footing |  |  | 2025-12-13 | 2025-12-14 | S | CLOSED | 1 | 0 | IN
65 | WIR-Civil-045 | 2 | STR | Zone : 03 Building : u-vf08 (vip) | Form work of P.C Footing |  |  | 2025-12-10 | 16/3/2026 | B
66 | WIR-Civil-046 | 0 | STR | Zone : 03 Building : u-vf08 (vip) | Form and Steel Work of R.C raft |  |  | 2025-11-30 | 2025-11-30 | S | CLOSED | 1 | 0 | IN
67 | WIR-Civil-046 | 1 | STR | Zone : 03 Building : u-vf08 (vip) | Form and Steel Work of R.C raft |  |  | 2025-12-13 | 2025-12-14 | S | CLOSED | 1 | 0 | IN
68 | WIR-Civil-046 | 2 | STR | Zone : 03 Building : u-vf08 (vip) | Form and Steel Work of R.C raft |  |  | 2025-12-10 | 16/3/2026 | B
69 | WIR-Civil-047 | 0 | STR | Zone : 03 Building : u-vf08 (vip) | Surface Preparation for R.C raft Before Insulation |  |  | 2025-11-30 | 2025-11-30 | S | CLOSED | 1 | 0 | IN
70 | WIR-Civil-047 | 1 | STR | Zone : 03 Building : u-vf08 (vip) | Surface Preparation for R.C raft Before Insulation |  |  | 2025-12-13 | 2025-12-14 | B | CLOSED | 1 | 0 | IN
71 | WIR-Civil-048 | 0 | STR | Zone : 03 Building : u-vf08 (vip) | Insulation of R.C raft |  |  | 2025-11-30 | 2025-11-30 | S | CLOSED | 1 | 0 | IN
72 | WIR-Civil-048 | 1 | STR | Zone : 03 Building : u-vf08 (vip) | Insulation of R.C raft |  |  | 2025-12-13 | 2025-12-14 | B | CLOSED | 1 | 0 | IN
73 | WIR-Civil-049 | 0 | STR | Zone : 03 Building : u-vf08 (vip) | curing of R.C raft |  |  | 2025-11-30 | 2025-11-30 | S | CLOSED | 1 | 0 | IN
74 | WIR-Civil-049 | 1 | STR | Zone : 03 Building : u-vf08 (vip) | curing of R.C raft |  |  |  | 2026-02-14 | S | CLOSED | 1 | 0 | IN
75 | WIR-Civil-049 | 2 | STR | Zone : 03 Building : u-vf08 (vip) | curing of R.C raft |  |  | 2025-12-10 | 16/3/2026 | B
76 | WIR-Civil-050 | 0 | STR | Zone : 03 Building : u-vf08 (vip) | structure Steel Work |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
77 | WIR-Civil-050 | 1 | STR | Zone : 03 Building : u-vf08 (vip) | structure Steel Work |  |  | 2025-12-10 | 2026-12-11 | S | CLOSED | 1 | 0 | IN
78 | WIR-Civil-050 | 2 | STR | Zone : 03 Building : u-vf08 (vip) | structure Steel work |  |  | 2025-12-10 |  | UR
79 | WIR-Civil-051 | 0 | STR | Zone : 03 Building : u-vf09 (vip) | prevention termites and polythene sheet |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
80 | WIR-Civil-051 | 1 | STR | Zone : 03 Building : u-vf09 (vip) | prevention termites and polythene sheet |  |  | 2025-12-09 | 2025-12-11 | B | CLOSED | 1 | 0 | IN
81 | WIR-Civil-052 | 0 | STR | Zone : 03 Building : u-vf09 (vip) | Form Work of P.C Footing |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
82 | WIR-Civil-052 | 1 | STR | Zone : 03 Building : u-vf09 (vip) | Form Work of P.C Footing |  |  | 2025-12-09 | 2025-12-11 | S | CLOSED | 1 | 0 | IN
83 | WIR-Civil-052 | 2 | STR | Zone : 03 Building : u-vf09 (vip) | Form work of P.C Footing |  |  | 2025-12-10 | 16/3/2026 | B
84 | WIR-Civil-053 | 0 | STR | Zone : 03 Building : u-vf09 (vip) | Form and Steel Work of R.C raft |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
85 | WIR-Civil-053 | 1 | STR | Zone : 03 Building : u-vf09 (vip) | Form and Steel Work of R.C raft |  |  | 2025-12-09 | 2025-12-11 | S | CLOSED | 1 | 0 | IN
86 | WIR-Civil-053 | 2 | STR | Zone : 03 Building : u-vf09 (vip) | Form and Steel work of R.C raft |  |  | 2025-12-10 | 16/3/2026 | B
87 | WIR-Civil-054 | 0 | STR | Zone : 03 Building : u-vf09 (vip) | Surface Preparation for R.C raft Before Insulation |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
88 | WIR-Civil-054 | 1 | STR | Zone : 03 Building : u-vf09 (vip) | Surface Preparation for R.C raft Before Insulation |  |  | 2025-12-09 | 2025-12-11 | B | CLOSED | 1 | 0 | IN
89 | WIR-Civil-055 | 0 | STR | Zone : 03 Building : u-vf09 (vip) | Insulation of R.C raft |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
90 | WIR-Civil-055 | 1 | STR | Zone : 03 Building : u-vf09 (vip) | Insulation of R.C raft |  |  | 2025-12-09 | 2025-12-11 | B | CLOSED | 1 | 0 | IN
91 | WIR-Civil-056 | 0 | STR | Zone : 03 Building : u-vf09 (vip) | curing of R.C raft |  |  | 2025-12-09 | 2025-12-11 | S | CLOSED | 1 | 0 | IN
92 | WIR-Civil-056 | 1 | STR | Zone : 03 Building : u-vf09 (vip) | curing of R.C raft |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
93 | WIR-Civil-056 | 2 | STR | Zone : 03 Building : u-vf09 (vip) | curing of R.C raft |  |  | 2025-12-10 | 16/3/2026 | B
94 | WIR-Civil-057 | 0 | STR | Zone : 03 Building : u-vf09 (vip) | structure Steel Work |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
95 | WIR-Civil-057 | 1 | STR | Zone : 03 Building : u-vf09 (vip) | structure Steel Work |  |  | 2025-12-10 | 2026-12-11 | S | CLOSED | 1 | 0 | IN
96 | WIR-Civil-057 | 2 | STR | Zone : 03 Building : u-vf09 (vip) | structure Steel Work |  |  | 2025-12-10 |  | UR
97 | WIR-Civil-058 | 0 | STR | Zone : 03 Building : u-vf10 (vip) | prevention termites and polythene sheet |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
98 | WIR-Civil-058 | 1 | STR | Zone : 03 Building : u-vf10 (vip) | prevention termites and polythene sheet |  |  | 2025-12-09 | 2025-12-11 | B | CLOSED | 1 | 0 | IN
99 | WIR-Civil-059 | 0 | STR | Zone : 03 Building : u-vf10 (vip) | Form Work of P.C Footing |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
100 | WIR-Civil-059 | 1 | STR | Zone : 03 Building : u-vf10 (vip) | Form Work of P.C Footing |  |  | 2025-12-09 | 2025-12-11 | S | CLOSED | 1 | 0 | IN
101 | WIR-Civil-059 | 2 | STR | Zone : 03 Building : u-vf10 (vip) | Form Work of P.C Footing |  |  | 2025-12-10 | 16/3/2026 | B
102 | WIR-Civil-060 | 0 | STR | Zone : 03 Building : u-vf10 (vip) | Form and Steel Work of R.C raft |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
103 | WIR-Civil-060 | 1 | STR | Zone : 03 Building : u-vf10 (vip) | Form and Steel Work of R.C raft |  |  | 2025-12-09 | 2025-12-11 | S | CLOSED | 1 | 0 | IN
104 | WIR-Civil-060 | 2 | STR | Zone : 03 Building : u-vf10 (vip) | Form and Steel Work of R.C raft |  |  | 2025-12-10 | 16/3/2026 | B
105 | WIR-Civil-061 | 0 | STR | Zone : 03 Building : u-vf10 (vip) | Surface Preparation for R.C raft Before Insulation |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
106 | WIR-Civil-061 | 1 | STR | Zone : 03 Building : u-vf10 (vip) | Surface Preparation for R.C raft Before Insulation |  |  | 2025-12-09 | 2025-12-11 | B | CLOSED | 1 | 0 | IN
107 | WIR-Civil-062 | 0 | STR | Zone : 03 Building : u-vf10 (vip) | Insulation of R.C raft |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
108 | WIR-Civil-062 | 1 | STR | Zone : 03 Building : u-vf10 (vip) | Insulation of R.C raft |  |  | 2025-12-09 | 2025-12-11 | B | CLOSED | 1 | 0 | IN
109 | WIR-Civil-063 | 0 | STR | Zone : 03 Building : u-vf10 (vip) | curing of R.C raft |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
110 | WIR-Civil-063 | 1 | STR | Zone : 03 Building : u-vf10 (vip) | curing of R.C raft |  |  | 2025-12-09 | 2025-12-11 | S | CLOSED | 1 | 0 | IN
111 | WIR-Civil-063 | 2 | STR | Zone : 03 Building : u-vf10 (vip) | curing of R.C raft |  |  | 2025-10-12 | 16/3/2026 | B
112 | WIR-Civil-064 | 0 | STR | Zone : 03 Building : u-vf10 (vip) | structure Steel Work |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
113 | WIR-Civil-064 | 1 | STR | Zone : 03 Building : u-vf10 (vip) | structure Steel Work |  |  | 2025-12-10 | 2026-12-11 | S | CLOSED | 1 | 0 | IN
114 | WIR-Civil-064 | 1 | STR | Zone : 03 Building : u-vf10 (vip) | structure Steel Work |  |  | 2025-10-12 |  | UR
115 | WIR-Civil-065 | 0 | STR | Zone : 03 Building : u-vf06 (vip) | prevention termites and polythene sheet |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
116 | WIR-Civil-065 | 1 | STR | Zone : 03 Building : u-vf06 (vip) | prevention termites and polythene sheet |  |  | 2025-12-09 | 2025-12-11 | B | CLOSED | 1 | 0 | IN
117 | WIR-Civil-066 | 0 | STR | Zone : 03 Building : u-vf06 (vip) | Form Work of P.C Footing |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
118 | WIR-Civil-066 | 1 | STR | Zone : 03 Building : u-vf06 (vip) | Form Work of P.C Footing |  |  | 2025-12-09 | 2025-12-11 | S | CLOSED | 1 | 0 | IN
119 | WIR-Civil-066 | 2 | STR | Zone : 03 Building : u-vf06 (vip) | Form Work of P.C Footing |  |  | 2025-12-10 | 16/3/2026 | B
120 | WIR-Civil-067 | 0 | STR | Zone : 03 Building : u-vf06 (vip) | Form and Steel Work of R.C raft |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
121 | WIR-Civil-067 | 1 | STR | Zone : 03 Building : u-vf06 (vip) | Form and Steel Work of R.C raft |  |  | 2025-12-09 | 2025-12-11 | S | CLOSED | 1 | 0 | IN
| WIR-Civil-067 | 2 | STR | Zone : 03 Building : u-vf06 (vip) | Form and Steel Work of R.C raft |  |  | 2026-03-16 | 2026-03-16 | B
122 | WIR-Civil-068 | 0 | STR | Zone : 03 Building : u-vf06 (vip) | Surface Preparation for R.C raft Before Insulation |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
123 | WIR-Civil-068 | 1 | STR | Zone : 03 Building : u-vf06 (vip) | Surface Preparation for R.C raft Before Insulation |  |  | 2025-12-09 | 2025-12-11 | B | CLOSED | 1 | 0 | IN
124 | WIR-Civil-069 | 0 | STR | Zone : 03 Building : u-vf06 (vip) | Insulation of R.C raft |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
125 | WIR-Civil-069 | 1 | STR | Zone : 03 Building : u-vf06 (vip) | Insulation of R.C raft |  |  | 2025-12-09 | 2025-12-11 | B | CLOSED | 1 | 0 | IN
126 | WIR-Civil-070 | 0 | STR | Zone : 03 Building : u-vf06 (vip) | curing of R.C raft |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
127 | WIR-Civil-070 | 1 | STR | Zone : 03 Building : u-vf06 (vip) | curing of R.C raft |  |  | 2025-12-09 | 2025-12-11 | S | CLOSED | 1 | 0 | IN
128 | WIR-Civil-070 | 2 | STR | Zone : 03 Building : u-vf06 (vip) | curing of R.C raft |  |  | 2025-12-10 | 16/3/2026 | B
129 | WIR-Civil-071 | 0 | STR | Zone : 03 Building : u-vf06 (vip) | structure Steel Work |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
130 | WIR-Civil-071 | 0 | STR | Zone : 03 Building : u-vf06 (vip) | structure Steel Work |  |  | 2025-12-10 | 2026-12-11 | S | CLOSED | 1 | 0 | IN
131 | WIR-Civil-071 | 0 | STR | Zone : 03 Building : u-vf06 (vip) | structure Steel Work |  |  | 2025-12-10 |  | UR
132 | WIR-Civil-072 | 0 | STR | Zone : 03 Building : twinz ( u-vs10-11 ) | prevention termites and polythene sheet |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
133 | WIR-Civil-072 | 1 | STR | Zone : 03 Building : twinz ( u-vs10-11 ) | prevention termites and polythene sheet |  |  | 2025-12-09 | 2025-12-11 | B | CLOSED | 1 | 0 | IN
134 | WIR-Civil-073 | 0 | STR | Zone : 03 Building : twinz ( u-vs10-11 ) | Form Work of P.C Footing |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
135 | WIR-Civil-073 | 1 | STR | Zone : 03 Building : twinz ( u-vs10-11 ) | Form Work of P.C Footing |  |  | 2025-12-09 | 2025-12-11 | B | CLOSED | 1 | 0 | IN
136 | WIR-Civil-074 | 0 | STR | Zone : 03 Building : twinz ( u-vs10-11 ) | Form and Steel Work of R.C raft |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
137 | WIR-Civil-074 | 1 | STR | Zone : 03 Building : twinz ( u-vs10-11 ) | Form and Steel Work of R.C raft |  |  | 2025-12-10 | 2025-12-11 | B | CLOSED | 1 | 0 | IN
138 | WIR-Civil-075 | 0 | STR | Zone : 03 Building : twinz ( u-vs10-11 ) | Surface Preparation for R.C raft Before Insulation |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
139 | WIR-Civil-075 | 1 | STR | Zone : 03 Building : twinz ( u-vs10-11 ) | Surface Preparation for R.C raft Before Insulation |  |  | 2025-12-10 | 2025-12-11 | B | CLOSED | 1 | 0 | IN
140 | WIR-Civil-076 | 0 | STR | Zone : 03 Building : twinz ( u-vs10-11 ) | Insulation of R.C raft |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
141 | WIR-Civil-076 | 1 | STR | Zone : 03 Building : twinz ( u-vs10-11 ) | Insulation of R.C raft |  |  | 2025-12-10 | 2025-12-11 | B | CLOSED | 1 | 0 | IN
142 | WIR-Civil-077 | 0 | STR | Zone : 03 Building : twinz ( u-vs10-11 ) | curing of R.C raft |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
143 | WIR-Civil-077 | 1 | STR | Zone : 03 Building : twinz ( u-vs10-11 ) | curing of R.C raft |  |  | 2025-12-10 | 2025-12-11 | C | CLOSED | 1 | 0 | IN
144 | WIR-Civil-078 | 0 | STR | Zone : 03 Building : twinz ( u-vs10-11 ) | structure Steel Work |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
145 | WIR-Civil-078 | 1 | STR | Zone : 03 Building : twinz ( u-vs10-11 ) | structure Steel Work |  |  | 2025-12-10 | 2026-12-11 | C | CLOSED | 1 | 0 | IN
146 | WIR-Civil-079 | 0 | STR | Zone : 03 Building : twinz ( u-vs12-13 ) | prevention termites and polythene sheet |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
147 | WIR-Civil-079 | 1 | STR | Zone : 03 Building : twinz ( u-vs12-13 ) | prevention termites and polythene sheet |  |  | 2025-12-10 | 2025-12-11 | B | CLOSED | 1 | 0 | IN
148 | WIR-Civil-080 | 0 | STR | Zone : 03 Building : twinz ( u-vs12-13 ) | Form Work of P.C Footing |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
149 | WIR-Civil-080 | 1 | STR | Zone : 03 Building : twinz ( u-vs12-13 ) | Form Work of P.C Footing |  |  | 2025-12-10 | 2025-12-11 | B | CLOSED | 1 | 0 | IN
150 | WIR-Civil-081 | 0 | STR | Zone : 03 Building : twinz ( u-vs12-13 ) | Form and Steel Work of R.C raft |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
151 | WIR-Civil-081 | 1 | STR | Zone : 03 Building : twinz ( u-vs12-13 ) | Form and Steel Work of R.C raft |  |  | 2025-12-10 | 2025-12-11 | B | CLOSED | 1 | 0 | IN
152 | WIR-Civil-082 | 0 | STR | Zone : 03 Building : twinz ( u-vs12-13 ) | Surface Preparation for R.C raft Before Insulation |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
153 | WIR-Civil-082 | 1 | STR | Zone : 03 Building : twinz ( u-vs12-13 ) | Surface Preparation for R.C raft Before Insulation |  |  | 2025-12-10 | 2025-12-14 | B | CLOSED | 1 | 0 | IN
154 | WIR-Civil-083 | 0 | STR | Zone : 03 Building : twinz ( u-vs12-13 ) | Insulation of R.C raft |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
155 | WIR-Civil-083 | 1 | STR | Zone : 03 Building : twinz ( u-vs12-13 ) | Insulation of R.C raft |  |  | 2025-12-10 | 2025-12-14 | B | CLOSED | 1 | 0 | IN
156 | WIR-Civil-084 | 0 | STR | Zone : 03 Building : twinz ( u-vs12-13 ) | curing of R.C raft |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
157 | WIR-Civil-084 | 1 | STR | Zone : 03 Building : twinz ( u-vs12-13 ) | curing of R.C raft |  |  | 2025-12-10 | 2025-12-14 | C | CLOSED | 1 | 0 | IN
158 | WIR-Civil-085 | 0 | STR | Zone : 03 Building : twinz ( u-vs12-13 ) | structure Steel Work |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
159 | WIR-Civil-085 | 1 | STR | Zone : 03 Building : twinz ( u-vs12-13 ) | structure Steel Work |  |  | 2025-12-10 | 2026-12-11 | C | CLOSED | 1 | 0 | IN
| WIR-Civil-085 | 2 | STR | Zone : 03 Building : twinz ( u-vs12-13 ) | structure Steel Work |  |  | 2026-03-07 |  | UR
160 | WIR-Civil-086 | 0 | STR | Zone : 03 Building :twinz ( u-vs14-15 )) | prevention termites and polythene sheet |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
161 | WIR-Civil-086 | 1 | STR | Zone : 03 Building :twinz ( u-vs14-15 )) | prevention termites and polythene sheet |  |  | 2025-12-10 | 2025-12-14 | B | CLOSED | 1 | 0 | IN
162 | WIR-Civil-087 | 0 | STR | Zone : 03 Building :twinz ( u-vs14-15 )) | Form Work of P.C Footing |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
163 | WIR-Civil-087 | 1 | STR | Zone : 03 Building :twinz ( u-vs14-15 )) | Form Work of P.C Footing |  |  | 2025-12-10 | 2025-12-11 | B | CLOSED | 1 | 0 | IN
164 | WIR-Civil-088 | 0 | STR | Zone : 03 Building :twinz ( u-vs14-15 )) | Form and Steel Work of R.C raft |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
165 | WIR-Civil-088 | 1 | STR | Zone : 03 Building :twinz ( u-vs14-15 )) | Form and Steel Work of R.C raft |  |  | 2025-12-10 | 2025-12-11 | B | CLOSED | 1 | 0 | IN
166 | WIR-Civil-089 | 0 | STR | Zone : 03 Building :twinz ( u-vs14-15 )) | Surface Preparation for R.C raft Before Insulation |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
167 | WIR-Civil-089 | 1 | STR | Zone : 03 Building :twinz ( u-vs14-15 )) | Surface Preparation for R.C raft Before Insulation |  |  | 2025-12-10 | 2025-12-11 | B | CLOSED | 1 | 0 | IN
168 | WIR-Civil-090 | 0 | STR | Zone : 03 Building :twinz ( u-vs14-15 )) | Insulation of R.C raft |  |  | 2025-11-29 | 2025-12-03 | C | CLOSED | 1 | 0 | IN
169 | WIR-Civil-090 | 1 | STR | Zone : 03 Building :twinz ( u-vs14-15 )) | Insulation of R.C raft |  |  | 2025-12-10 | 2025-12-11 | B | CLOSED | 1 | 0 | IN
170 | WIR-Civil-091 | 0 | STR | Zone : 03 Building :twinz ( u-vs14-15 )) | curing of R.C raft |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
171 | WIR-Civil-091 | 1 | STR | Zone : 03 Building :twinz ( u-vs14-15 )) | curing of R.C raft |  |  | 2025-12-10 | 2025-12-11 | C | CLOSED | 1 | 0 | IN
172 | WIR-Civil-092 | 0 | STR | Zone : 03 Building :twinz ( u-vs14-15 )) | structure Steel Work |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
173 | WIR-Civil-092 | 1 | STR | Zone : 03 Building :twinz ( u-vs14-15 )) | structure Steel Work |  |  | 2025-12-10 | 2025-12-11 | C | CLOSED | 1 | 0 | IN
174 | WIR-Civil-093 | 0 | STR | Zone : 03 Building :twinz ( u-vs16-17 ) | prevention termites and polythene sheet |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
175 | WIR-Civil-093 | 1 | STR | Zone : 03 Building :twinz ( u-vs16-17 ) | prevention termites and polythene sheet |  |  | 2025-12-10 | 2025-12-11 | b | CLOSED | 1 | 0 | IN
176 | WIR-Civil-094 | 0 | STR | Zone : 03 Building :twinz ( u-vs16-17 ) | Form Work of P.C Footing |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
177 | WIR-Civil-094 | 1 | STR | Zone : 03 Building :twinz ( u-vs16-17 ) | Form Work of P.C Footing |  |  | 2025-12-10 |  | UR | CLOSED | 1 | 0 | IN
178 | WIR-Civil-095 | 0 | STR | Zone : 03 Building :twinz ( u-vs16-17 ) | Form and Steel Work of R.C raft |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
179 | WIR-Civil-095 | 1 | STR | Zone : 03 Building :twinz ( u-vs16-17 ) | Form and Steel Work of R.C raft |  |  | 2025-12-13 | 2025-12-14 | B | CLOSED | 1 | 0 | IN
180 | WIR-Civil-096 | 0 | STR | Zone : 03 Building :twinz ( u-vs16-17 ) | Surface Preparation for R.C raft Before Insulation |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
181 | WIR-Civil-096 | 1 | STR | Zone : 03 Building :twinz ( u-vs16-17 ) | Surface Preparation for R.C raft Before Insulation |  |  | 2025-12-13 | 2025-12-14 | B | CLOSED | 1 | 0 | IN
182 | WIR-Civil-097 | 0 | STR | Zone : 03 Building :twinz ( u-vs16-17 ) | Insulation of R.C raft |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
183 | WIR-Civil-097 | 1 | STR | Zone : 03 Building :twinz ( u-vs16-17 ) | Insulation of R.C raft |  |  | 2025-12-13 | 2025-12-14 | B | CLOSED | 1 | 0 | IN
184 | WIR-Civil-098 | 0 | STR | Zone : 03 Building :twinz ( u-vs16-17 ) | curing of R.C raft |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
185 | WIR-Civil-098 | 1 | STR | Zone : 03 Building :twinz ( u-vs16-17 ) | curing of R.C raft |  |  | 2025-12-13 | 2025-12-14 | C | CLOSED | 1 | 0 | IN
186 | WIR-Civil-099 | 0 | STR | Zone : 03 Building :twinz ( u-vs16-17 ) | structure Steel Work |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
187 | WIR-Civil-099 | 1 | STR | Zone : 03 Building :twinz ( u-vs16-17 ) | structure Steel Work |  |  | 2025-11-29 | 2025-12-03 | C | CLOSED | 1 | 0 | IN
188 | WIR-Civil-100 | 0 | STR | Zone : 03 Building :royal ( u-vv01 ) | prevention termites and polythene sheet |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
189 | WIR-Civil-100 | 1 | STR | Zone : 03 Building :royal ( u-vv01 ) | prevention termites and polythene sheet |  |  | 2025-12-13 | 2025-12-14 | B | CLOSED | 1 | 0 | IN
190 | WIR-Civil-101 | 0 | STR | Zone : 03 Building :royal ( u-vv01 ) | Form Work of P.C Footing |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
191 | WIR-Civil-101 | 1 | STR | Zone : 03 Building :royal ( u-vv01 ) | Form Work of P.C Footing |  |  | 2025-12-13 | 2025-12-14 | C | CLOSED | 1 | 0 | IN
192 | WIR-Civil-102 | 0 | STR | Zone : 03 Building :royal ( u-vv01 ) | Form and Steel Work of R.C raft |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
193 | WIR-Civil-102 | 1 | STR | Zone : 03 Building :royal ( u-vv01 ) | Form and Steel Work of R.C raft |  |  | 2025-12-13 | 2025-12-14 | C | CLOSED | 1 | 0 | IN
194 | WIR-Civil-103 | 0 | STR | Zone : 03 Building :royal ( u-vv01 ) | Surface Preparation for R.C raft Before Insulation |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
195 | WIR-Civil-103 | 1 | STR | Zone : 03 Building :royal ( u-vv01 ) | Surface Preparation for R.C raft Before Insulation |  |  | 2025-12-13 | 2025-12-14 | B | CLOSED | 1 | 0 | IN
196 | WIR-Civil-104 | 0 | STR | Zone : 03 Building :royal ( u-vv01 ) | Insulation of R.C raft |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
197 | WIR-Civil-104 | 1 | STR | Zone : 03 Building :royal ( q-vv01 ) | Insulation of R.C raft |  |  | 2025-12-13 | 2025-12-14 | b | CLOSED | 1 | 0 | IN
198 | WIR-Civil-105 | 0 | STR | Zone : 03 Building :royal ( u-vv01 ) | curing of R.C raft |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
199 | WIR-Civil-105 | 1 | STR | Zone : 03 Building :royal ( u-vv01 ) | curing of R.C raft |  |  | 2025-11-29 | 2025-12-03 | C | CLOSED | 1 | 0 | IN
200 | WIR-Civil-106 | 0 | STR | Zone : 03 Building :royal ( u-vv01 ) | structure Steel Work |  |  | 2025-11-29 | 2025-12-03 | S | CLOSED | 1 | 0 | IN
201 | WIR-Civil-106 | 1 | STR | Zone : 03 Building :royal ( u-vv01 ) | structure Steel Work |  |  | 2025-11-29 | 2025-12-03 | C | CLOSED | 1 | 0 | IN
202 | WIR-Civil-107 | 0 | STR | Zone 2 Building : GA-( 07-08-09-10-11 ) | Prevention Termites , Polythene Sheet |  |  | 2025-12-20 | 2025-12-22 | B | CLOSED | 1 | 0 | IN
203 | WIR-Civil-108 | 0 | STR | Zone 2 Building : GA-( 07-08-09-10-11 ) | Form Work of P.C Footing |  |  | 2025-12-20 | 2025-12-22 | B | CLOSED | 1 | 0 | IN
204 | WIR-Civil-109 | 0 | STR | Zone 2 Building : GA-( 07-08-09-10-11 ) | Form and Steel Work of R.C Footing |  |  | 2025-12-20 | 2025-12-22 | B | CLOSED | 1 | 0 | IN
205 | WIR-Civil-110 | 0 | STR | Zone 2 Building : GA-( 07-08-09-10-11 ) | Surface Preparation for R.C Footing Before Insulation |  |  | 2025-12-20 | 2025-12-22 | B | CLOSED | 1 | 0 | IN
206 | WIR-Civil-111 | 0 | STR | Zone 2 Building : GA-( 07-08-09-10-11 ) | 1st Layer Insulation of R.C Footing |  |  | 2025-12-20 | 2025-12-22 | B | CLOSED | 1 | 0 | IN
207 | WIR-Civil-112 | 0 | STR | Zone 2 Building : GA-( 07-08-09-10-11 ) | 2nd Layer Insulation of R.C Footing |  |  | 2025-12-20 | 2025-12-22 | B | CLOSED | 1 | 0 | IN
208 | WIR-Civil-113 | 0 | STR | Zone 2 Building : GA-( 07-08-09-10-11 ) | Form and Steel Work of Grade Beam |  |  | 2025-12-20 | 2025-12-22 | B | CLOSED | 1 | 0 | IN
209 | WIR-Civil-114 | 0 | STR | Zone 2 Building : GA-( 07-08-09-10-11 ) | Surface Preparation for Grade Beam Before Insulation |  |  | 2025-12-20 | 2025-12-22 | B | CLOSED | 1 | 0 | IN
210 | WIR-Civil-115 | 0 | STR | Zone 2 Building : GA-( 07-08-09-10-11 ) | 1st Layer Insulation of Grade Beam |  |  | 2025-12-20 | 2025-12-22 | B | CLOSED | 1 | 0 | IN
211 | WIR-Civil-116 | 0 | STR | Zone 2 Building : GA-( 07-08-09-10-11 ) | 2nd Layer Insulation of Grade Beam |  |  | 2025-12-20 | 2025-12-22 | B | CLOSED | 1 | 0 | IN
212 | WIR-Civil-117 | 0 | STR | Zone 2 Building : GA-( 07-08-09-10-11 ) | Steel Work of Columns |  |  | 2025-12-20 | 2025-12-22 | B | CLOSED | 1 | 0 | IN
213 | WIR-Civil-118 | 0 | STR | Zone 2 Building : GA-( 07-08-09-10-11 ) | Form Work of Columns |  |  | 2025-12-20 | 2025-12-22 | B | CLOSED | 1 | 0 | IN
214 | WIR-Civil-119 | 0 | STR | Zone 2 Building : GA-( 07-08-09-10-11 ) | Steel Work of Upper Beam |  |  | 2025-12-20 | 2025-12-22 | B | CLOSED | 1 | 0 | IN
215 | WIR-Civil-120 | 0 | STR | Zone 2 Building : GA-( 07-08-09-10-11 ) | Form Work of Upper Beam |  |  | 2025-12-20 | 2025-12-22 | B | CLOSED | 1 | 0 | IN
216 | WIR-Civil-121 | 0 | STR | Zone 2 Building : GA-( 07-08-09-10-11 ) | Steel works of S.O.G |  |  | 2025-12-20 | 2025-12-22 | C | CLOSED | 1 | 0 | IN
217 | WIR-Civil-122 | 0 | STR | Zone 2 Building : GA-( 07-08-09-10-11 ) | installation of H.C.S |  |  | 2025-12-20 | 2025-12-22 | B | CLOSED | 1 | 0 | IN
218 | WIR-Civil-123 | 0 | STR | GA-(01-02-03-04-05-06) | Pouring for P.C Footing |  |  | 2025-12-20 | 2025-12-22 | S | CLOSED | 1 | 0 | IN
| WIR-Civil-123 | 1 | STR | GA-(01-02-03-04-05-06) | Pouring for P.C Footing |  |  | 2026-10-03 | 2026-10-03 | B | CLOSED | 1 | 0 | IN
219 | WIR-Civil-124 | 0 | STR | GA-(07-08-09-10-11) | Pouring for P.C Footing |  |  | 2025-12-20 | 2025-12-22 | S | CLOSED | 1 | 0 | IN
| WIR-Civil-124 | 1 | STR | GA-(07-08-09-10-11) | Pouring for P.C Footing |  |  | 2026-10-03 | 2026-10-03 | B | CLOSED | 1 | 0 | IN
220 | WIR-Civil-125 | 0 | STR | GA-(01-02-03-04-05-06) | Pouring for P.C Footing |  |  | 2025-12-20 | 2025-12-22 | S | CLOSED | 1 | 0 | IN
220 | WIR-Civil-125 | 1 | STR | GA-(01-02-03-04-05-06) | Pouring for P.C Footing |  |  | 2026-03-10 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
221 | WIR-Civil-126 | 0 | STR | GA-(07-08-09-10-11) | Pouring for P.C Footing |  |  | 2025-12-20 | 2025-12-22 | S | CLOSED | 1 | 0 | IN
221 | WIR-Civil-126 | 1 | STR | GA-(07-08-09-10-11) | Pouring for P.C Footing |  |  | 2026-03-10 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
222 | WIR-Civil-127 | 0 | STR | GA-(01-02-03-04-05-06) | Pouring for Grade Beam |  |  | 2025-12-20 | 2025-12-22 | S | CLOSED | 1 | 0 | IN
222 | WIR-Civil-127 | 1 | STR | GA-(01-02-03-04-05-06) | Pouring for Grade Beam |  |  | 2026-03-10 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
223 | WIR-Civil-128 | 0 | STR | GA-(07-08-09-10-11) | Pouring for Grade Beam |  |  | 2025-12-20 | 2025-12-22 | S | CLOSED | 1 | 0 | IN
223 | WIR-Civil-128 | 1 | STR | GA-(07-08-09-10-11) | Pouring for Grade Beam |  |  | 2026-03-10 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
224 | WIR-Civil-129 | 0 | STR | GA-(01-02-03-04-05-06) | Pouring for Columns |  |  | 2025-12-20 | 2025-12-22 | S | CLOSED | 1 | 0 | IN
224 | WIR-Civil-129 | 1 | STR | GA-(01-02-03-04-05-06) | Pouring for Columns |  |  | 2026-03-10 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
225 | WIR-Civil-130 | 0 | STR | GA-(07-08-09-10-11) | Pouring for Columns |  |  | 2025-12-20 | 2025-12-22 | S | CLOSED | 1 | 0 | IN
225 | WIR-Civil-130 | 1 | STR | GA-(07-08-09-10-11) | Pouring for Columns |  |  | 2026-03-10 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
226 | WIR-Civil-131 | 0 | STR | GA-(01-02-03-04-05-06) | Pouring for Upeer Beam |  |  | 2025-12-20 | 2025-12-22 | S | CLOSED | 1 | 0 | IN
226 | WIR-Civil-131 | 1 | STR | GA-(01-02-03-04-05-06) | Pouring for Upeer Beam |  |  | 2026-03-10 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
227 | WIR-Civil-132 | 0 | STR | GA-(07-08-09-10-11) | Pouring for Upeer Beam |  |  | 2025-12-20 | 2025-12-22 | S | CLOSED | 1 | 0 | IN
227 | WIR-Civil-132 | 1 | STR | GA-(07-08-09-10-11) | Pouring for Upeer Beam |  |  | 2026-03-10 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
228 | WIR-Civil-133 | 0 | STR | GA-(01-02-03-04-05-06) | Pouring for S.O.G |  |  | 2025-12-20 | 2025-12-22 | S | CLOSED | 1 | 0 | IN
| WIR-Civil-133 | 1 | STR | GA-(01-02-03-04-05-06) | Pouring for S.O.G |  |  | 2026-03-10 | 2026-03-10 | B
229 | WIR-Civil-134 | 0 | STR | GA-(07-08-09-10-11) | Pouring for S.O.G |  |  | 2025-12-20 | 2025-12-22 | B | CLOSED | 1 | 0 | IN
230 | WIR-Civil-135 | 0 | STR | GA-(01-02-03-04-05-06) | Pouring for Screed |  |  | 2025-12-20 | 2025-12-22 | S | CLOSED | 1 | 0 | IN
| WIR-Civil-135 | 1 | STR | GA-(01-02-03-04-05-06) | Pouring for Screed |  |  | 2026-03-10 | 2026-03-10 | B
231 | WIR-Civil-136 | 0 | STR | GA-(07-08-09-10-11) | Pouring for Screed |  |  | 2025-12-20 | 2025-12-22 | S | CLOSED | 1 | 0 | IN
| WIR-Civil-136 | 1 | STR | GA-(07-08-09-10-11) | Pouring for Screed |  |  | 2026-03-10 | 2026-03-10 | B
232 | WIR-Civil-137 | 0 | STR |  | الرد علي NCR-009 |  |  | 2025-12-29 |  | S | CLOSED | 1 | 0 | IN
233 | WIR-Civil-137 | 1 | STR |  | الرد علي NCR-009 |  |  | 2026-03-04 | 2026-03-04 | B | CLOSED | 1 | 0 | IN
234 | WIR-Civil-138 | 0 | STR |  | NCR closing 12 |  |  | 2025-12-08 | 2025-12-25 | S | CLOSED | 1 | 0 | IN
235 | WIR-Civil-138 | 1 | STR |  | NCR closing 12 |  |  | 2026-10-03 |  | UR | CLOSED | 1 | 0 | IN
236 | WIR-Civil-139 | 0 | STR | Q-FA02-Q-FA01 | Pouring work of P.C footing |  |  | 2025-12-28 | 2026-01-03 | c | CLOSED | 1 | 0 | IN
237 | WIR-Civil-140 | 0 | STR | Q-FA02-Q-FA01 | Form and steel work of R.C raft |  |  | 2025-12-28 | 2026-01-03 | b | CLOSED | 1 | 0 | IN
238 | WIR-Civil-141 | 0 | STR | Q-FA02-Q-FA01 | Pouring for R.C Raft |  |  | 2025-12-28 | 2026-01-03 | c | CLOSED | 1 | 0 | IN
239 | WIR-Civil-142 | 0 | STR | Q-FA02-Q-FA01 | Surface preparation for R.C footing before insulation |  |  | 2025-12-28 | 2026-01-03 | b | CLOSED | 1 | 0 | IN
240 | WIR-Civil-143 | 0 | STR | Q-FA02-Q-FA01 | Insulation of R.C raft |  |  | 2025-12-28 | 2026-01-03 | b | CLOSED | 1 | 0 | IN
241 | WIR-Civil-144 | 0 | STR | Q-FA02-Q-FA01 | Steel work of columns |  |  | 2025-12-28 | 2026-01-03 | b | CLOSED | 1 | 0 | IN
242 | WIR-Civil-145 | 0 | STR | Q-FA02-Q-FA01 | Form work of columns |  |  | 2025-12-28 | 2026-01-03 | b | CLOSED | 1 | 0 | IN
243 | WIR-Civil-146 | 0 | STR | Q-FA02-Q-FA01 | Pouring for Columns |  |  | 2025-12-29 |  | c | CLOSED | 1 | 0 | IN
244 | WIR-Civil-147 | 0 | STR | Q-FA02-Q-FA01 | Steel work of upper beam and slab |  |  | 2025-12-28 | 2026-01-03 | d | CLOSED | 1 | 0 | IN
245 | WIR-Civil-148 | 0 | STR | Q-FA02-Q-FA01 | Form qork of upper bean and slab |  |  | 2025-12-28 | 2026-01-03 | d | CLOSED | 1 | 0 | IN
246 | WIR-Civil-149 | 0 | STR | Q-FA02-Q-FA01 | Pouring for Upeer Beam and slab |  |  | 2025-12-28 | 2026-01-03 | d | CLOSED | 1 | 0 | IN
247 | WIR-Civil-150 | 0 | STR | Q-FA02-Q-FA01 | Pouring for screed Ground dloor |  |  | 2025-12-29 |  | C | CLOSED | 1 | 0 | IN
248 | WIR-Civil-151 | 0 | STR | Q-FA02-Q-FA01 | Installation of H.C.S |  |  | 2025-12-29 |  | d | CLOSED | 1 | 0 | IN
249 | WIR-Civil-152 | 0 | STR | Q-FA02-Q-FA01 | Steel works of screed after H.C.S |  |  | 2025-12-29 | 2025-12-22 | D | CLOSED | 1 | 0 | IN
250 | WIR-Civil-153 | 0 | STR | Q-FA02-Q-FA01 | Pouring for Screed |  |  | 2025-12-29 | 2025-12-22 | C | CLOSED | 1 | 0 | IN
251 | WIR-Civil-154 | 0 | STR | Q-WC01, Q-Wc02 | Pervention termites, polythene sheet |  |  | 2025-12-29 | 2026-01-01 | b | CLOSED | 1 | 0 | IN
252 | WIR-Civil-155 | 0 | STR | Q-WC01, Q-Wc02 | Form work of P.C footing |  |  | 2025-12-29 | 2026-01-01 | b | CLOSED | 1 | 0 | IN
253 | WIR-Civil-156 | 0 | STR | Q-WC01, Q-Wc02 | Pouring for P.C Footing |  |  | 2025-12-29 |  | c | CLOSED | 1 | 0 | IN
254 | WIR-Civil-157 | 0 | STR | Q-WC01, Q-Wc02 | Surface prepration for R.C footing before insulation |  |  | 2025-12-29 | 2026-01-01 | b | CLOSED | 1 | 0 | IN
255 | WIR-Civil-158 | 0 | STR | Q-WC01, Q-Wc02 | 1st layer insulation of R.C footing |  |  | 2025-12-29 | 2026-01-01 | b | CLOSED | 1 | 0 | IN
256 | WIR-Civil-159 | 0 | STR | Q-WC01, Q-Wc02 | 2nd layer insulation of R.C footing |  |  | 2025-12-29 | 2026-01-01 | b | CLOSED | 1 | 0 | IN
257 | WIR-Civil-160 | 0 | STR | Q-WC01, Q-Wc02 | Form and steel work of grade beam |  |  | 2025-12-29 | 2026-01-01 | b | CLOSED | 1 | 0 | IN
258 | WIR-Civil-161 | 0 | STR | Q-WC01, Q-Wc02 | Pouring for Grade Beam |  |  | 2025-12-29 | 2026-01-19 | c | CLOSED | 1 | 0 | IN
259 | WIR-Civil-162 | 0 | STR | Q-WC01, Q-Wc02 | Surface prepration for grade beam before insulation |  |  | 2025-12-29 | 2026-01-01 | b | CLOSED | 1 | 0 | IN
260 | WIR-Civil-163 | 0 | STR | Q-WC01, Q-Wc02 | 1st layer insulation of grade beam |  |  | 2025-12-29 | 2026-01-01 | b | CLOSED | 1 | 0 | IN
261 | WIR-Civil-164 | 0 | STR | Q-WC01, Q-Wc02 | 2nd layer insulation of grade beam |  |  | 2025-12-29 | 2026-01-01 | b | CLOSED | 1 | 0 | IN
262 | WIR-Civil-165 | 0 | STR | Q-WC01, Q-Wc02 | Steel work of columns |  |  | 2025-12-29 | 2026-01-01 | b | CLOSED | 1 | 0 | IN
263 | WIR-Civil-166 | 0 | STR | Q-WC01, Q-Wc02 | Form work of columns |  |  | 2025-12-29 | 2026-01-01 | b | CLOSED | 1 | 0 | IN
264 | WIR-Civil-167 | 0 | STR | Q-WC01, Q-Wc02 | Pouring for Columns |  |  | 2025-12-29 | 2026-01-19 | c | CLOSED | 1 | 0 | IN
265 | WIR-Civil-168 | 0 | STR | Q-WC01, Q-Wc02 | Steel work of upper beam |  |  | 2025-12-29 | 2026-01-01 | d | CLOSED | 1 | 0 | IN
266 | WIR-Civil-169 | 0 | STR | Q-WC01, Q-Wc02 | Form work of Upper beam |  |  | 2025-12-29 | 2026-01-01 | d | CLOSED | 1 | 0 | IN
267 | WIR-Civil-170 | 0 | STR | Q-WC01, Q-Wc02 | Pouring for Upeer Beam |  |  | 2025-12-29 | 2026-01-19 | c | CLOSED | 1 | 0 | IN
268 | WIR-Civil-171 | 0 | STR | Q-WC01, Q-Wc02 | Steel works of S.O.G |  |  | 2025-12-29 | 2026-01-01 | b | CLOSED | 1 | 0 | IN
269 | WIR-Civil-172 | 0 | STR | Q-WC01, Q-Wc02 | Pouring for S.O.G |  |  | 2025-12-29 | 2026-01-19 | c | CLOSED | 1 | 0 | IN
270 | WIR-Civil-173 | 0 | STR | Q-WC01, Q-Wc02 | Installation of H.C.S |  |  | 2025-12-29 | 2026-01-01 | d | CLOSED | 1 | 0 | IN
271 | WIR-Civil-174 | 0 | STR | Q-WC01, Q-Wc02 | Steel works of screed after H.C.S |  |  | 2025-12-29 | 2026-01-01 | d | CLOSED | 1 | 0 | IN
272 | WIR-Civil-175 | 0 | STR | Q-WC01, Q-Wc02 | Pouring for Screed |  |  | 2025-12-29 |  | c | CLOSED | 1 | 0 | IN
273 | WIR-Civil-176 | 0 | STR | QR03-04 | Prevention Termites-Polythene sheet |  |  | 2025-12-29 | 2026-03-07 | B | CLOSED | 1 | 0 | IN
274 | WIR-Civil-177 | 0 | STR | QR03-04 | Form work of P.C footing |  |  | 2025-12-29 | 2026-03-07 | B | CLOSED | 1 | 0 | IN
275 | WIR-Civil-178 | 0 | STR | QR03-04 | Pouring for P.C Footing |  |  | 2025-12-29 | 2026-10-03 | B | CLOSED | 1 | 0 | IN
276 | WIR-Civil-179 | 0 | STR | QR03-04 | Form and steeel work of R.C raft |  |  | 2025-12-29 | 2026-03-07 | B | CLOSED | 1 | 0 | IN
277 | WIR-Civil-180 | 0 | STR | QR03-04 | Pouring of R.C Raft |  |  | 2025-12-29 |  | UR | CLOSED | 1 | 0 | IN
278 | WIR-Civil-181 | 0 | STR | QR03-04 | Surface prepration for R.C footing before insulation |  |  | 2025-12-29 | 2026-03-07 | B | CLOSED | 1 | 0 | IN
279 | WIR-Civil-182 | 0 | STR | Q-R03-04 | 1st Layer insulation of R.C footing |  |  | 2025-12-29 | 2026-01-05 | b | CLOSED | 1 | 0 | IN
280 | WIR-Civil-183 | 0 | STR | Q-R03-04 | 2nd Layer insulation of R.C footing |  |  | 2025-12-29 | 2026-01-05 | b | CLOSED | 1 | 0 | IN
281 | WIR-Civil-184 | 0 | STR | Q-R03-04 | Form and steel work of grade beam |  |  | 2025-12-29 | 2026-01-05 | b | CLOSED | 1 | 0 | IN
282 | WIR-Civil-185 | 0 | STR | Q-R03-04 | Pouring for Grade Beam |  |  | 2026-01-13 | 2026-01-19 | c | CLOSED | 1 | 0 | IN
283 | WIR-Civil-186 | 0 | STR | Q-R03-04 | Surface preparation for Grade beam before insulation |  |  | 2025-12-29 | 2026-01-05 | b | CLOSED | 1 | 0 | IN
284 | WIR-Civil-187 | 0 | STR | Q-R03-04 | 1st layer insulation of grade beam |  |  | 2025-12-30 | 2026-01-05 | b | CLOSED | 1 | 0 | IN
285 | WIR-Civil-188 | 0 | STR | Q-R03-04 | 2nd layer insulation of grade beam |  |  | 2025-12-30 | 2026-01-05 | b | CLOSED | 1 | 0 | IN
286 | WIR-Civil-189 | 0 | STR | Q-R03-04 | Steel work of columns |  |  | 2025-12-30 | 2026-01-05 | b | CLOSED | 1 | 0 | IN
287 | WIR-Civil-190 | 0 | STR | Q-R03-04 | Form work of columns |  |  | 2025-12-30 | 2026-01-05 | b | CLOSED | 1 | 0 | IN
288 | WIR-Civil-191 | 0 | STR | Q-R03-04 | Pouring for Columns |  |  | 2026-01-23 | 2026-01-19 | c | CLOSED | 1 | 0 | IN
289 | WIR-Civil-192 | 0 | STR | Q-R03-04 | Steel work of upper beam |  |  | 2025-12-30 | 2026-01-05 | c | CLOSED | 1 | 0 | IN
290 | WIR-Civil-193 | 0 | STR | Q-R03-04 | Form work of Upper beam |  |  | 2025-12-30 | 2026-01-05 | c | CLOSED | 1 | 0 | IN
291 | WIR-Civil-194 | 0 | STR | Q-R03-04 | Pouring for upper beam |  |  | 2026-01-23 | 2026-01-19 | c | CLOSED | 1 | 0 | IN
292 | WIR-Civil-195 | 0 | STR | Q-R03-04 | Hollowcare slab working |  |  | 2026-01-23 | 2026-01-19 | c | CLOSED | 1 | 0 | IN
293 | WIR-Civil-196 | 0 | STR | Q-R03-04 | Steel works of S.O.G |  |  | 2026-01-23 | 2026-01-19 | B | CLOSED | 1 | 0 | IN
294 | WIR-Civil-197 | 0 | STR | Q-R03-04 | Pouring for S.O.G |  |  | 2026-01-23 | 2026-01-19 | c | CLOSED | 1 | 0 | IN
295 | WIR-Civil-198 | 0 | STR | Q-R03-04 | Installation pf H.G.S |  |  | 2026-01-23 | 2026-01-19 | D | CLOSED | 1 | 0 | IN
296 | WIR-Civil-199 | 0 | STR | Q-R03-04 | Steel works of screed after H.C.S |  |  | 2026-01-23 | 2026-01-19 | B | CLOSED | 1 | 0 | IN
297 | WIR-Civil-200 | 0 | STR | Q-R03-04 | Pouring for screed |  |  | 2026-01-23 | 2026-01-19 | c | CLOSED | 1 | 0 | IN
298 | WIR-Civil-201 | 0 | STR | Q-R03-04 | Form and steel work of R.C footing |  |  | 2026-01-23 |  | UR | CLOSED | 1 | 0 | IN
299 | WIR-Civil-202 | 0 | STR | Q-C(03-04-05-06-07-08) | Form work of P.C footing |  |  | 2026-01-23 |  | UR | CLOSED | 1 | 0 | IN
300 | WIR-Civil-203 | 0 | STR | Q-C(03-04-05-06-07-08) | Prevention Termites-Polythene sheet |  |  | 2026-01-23 | 2026-10-03 | B | CLOSED | 1 | 0 | IN
301 | WIR-Civil-204 | 0 | STR | Q-C(03-04-05-06-07-08) | Form work of P.C footing |  |  | 2026-01-23 | 2026-10-03 | B | CLOSED | 1 | 0 | IN
302 | WIR-Civil-205 | 0 | STR | Q-C(03-04-05-06-07-08) | Pouring of R.C footing |  |  | 2026-01-23 | 2026-10-03 | B | CLOSED | 1 | 0 | IN
303 | WIR-Civil-206 | 0 | STR | Q-C(03-04-05-06-07-08) | Form and steel work of R.C raft |  |  | 2026-01-23 | 2026-10-03 | B | CLOSED | 1 | 0 | IN
304 | WIR-Civil-207 | 0 | STR | Q-C(03-04-05-06-07-08) | Pouring for R.C Raft |  |  | 2026-01-23 |  | UR | CLOSED | 1 | 0 | IN
305 | WIR-Civil-208 | 0 | STR | Q-C(03-04-05-06-07-08) | Surface preparation for R.C footing before insulation |  |  | 2026-01-23 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
306 | WIR-Civil-209 | 0 | STR | Q-C(03-04-05-06-07-08) | Insulation of R.C raft |  |  | 2026-01-23 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
307 | WIR-Civil-210 | 0 | STR | Q-C(03-04-05-06-07-08) | Steel structure working |  |  | 2026-01-23 |  | UR | CLOSED | 1 | 0 | IN
308 | WIR-Civil-211 | 0 | STR | Q-C(03-04-05-06-07-08) | Pouring for screed Ground floor |  |  | 2026-01-23 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
309 | WIR-Civil-212 | 0 | STR | G-01 | Prevention Termites-Polythene sheet |  |  | 2026-01-23 |  | UR | CLOSED | 1 | 0 | IN
310 | WIR-Civil-213 | 0 | STR | G-01 | Form work of P.C footing |  |  | 2026-01-23 |  | UR | CLOSED | 1 | 0 | IN
311 | WIR-Civil-214 | 0 | STR | G-01 | Pouring of P.C Footing |  |  | 2026-01-23 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
312 | WIR-Civil-215 | 0 | STR | G-01 | Form and steel work of R.C raft |  |  | 2026-01-23 |  | UR | CLOSED | 1 | 0 | IN
313 | WIR-Civil-216 | 0 | STR | G-01 | Pouring of R.C Raft |  |  | 2026-01-23 |  | UR | CLOSED | 1 | 0 | IN
314 | WIR-Civil-217 | 0 | STR | G-01 | Drilling works for anchor bolts |  |  | 2026-01-23 |  | UR | CLOSED | 1 | 0 | IN
315 | WIR-Civil-218 | 0 | STR | G-01 | Alignment and vertically of anchor bolts |  |  | 2026-01-23 |  | UR | CLOSED | 1 | 0 | IN
316 | WIR-Civil-219 | 0 | STR | G-01 | Fixing and tightening of anchor bolts |  |  | 2026-01-23 |  | UR | CLOSED | 1 | 0 | IN
317 | WIR-Civil-220 | 0 | STR | G-01 | Installation of steel structure works |  |  | 2026-01-23 |  | UR | CLOSED | 1 | 0 | IN
318 | WIR-Civil-221 | 0 | STR | G-08-09 | Prevention Termites-Polythene sheet |  |  | 2026-03-07 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
319 | WIR-Civil-222 | 0 | STR | G-08-09 | Form work of P.C footing |  |  | 2026-03-07 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
320 | WIR-Civil-223 | 0 | STR | G-08-09 | Pouring for P.C Footing |  |  | 2026-01-23 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
321 | WIR-Civil-224 | 0 | STR | G-08-09 | Form and steel work of R.C raft |  |  | 2026-01-23 |  | UR | CLOSED | 1 | 0 | IN
322 | WIR-Civil-226 | 0 | STR | G-08-09 | Pouring for R.C Raft |  |  | 2026-03-07 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
323 | WIR-Civil-227 | 0 | STR | G-08-09 | Surface preparation for R.C footing before insulation |  |  | 2026-03-07 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
324 | WIR-Civil-228 | 0 | STR | G-08-09 | Insulation of R.C raft |  |  | 2026-01-23 |  | UR | CLOSED | 1 | 0 | IN
325 | WIR-Civil-229 | 0 | STR | G-08-09 | Steel structure working |  |  | 2026-01-23 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
326 | WIR-Civil-230 | 0 | STR | G-08-09 | Pouring for screed Ground floor |  |  | 2026-01-23 |  | UR | CLOSED | 1 | 0 | IN
327 | WIR-Civil-231 | 0 | STR | G-08-09 | Installation of H.C.S |  |  | 2026-01-23 |  | UR | CLOSED | 1 | 0 | IN
328 | WIR-Civil-232 | 0 | STR | G-08-09 | Steel works of screed after H.C.S |  |  | 2026-01-23 | 2026-03-25 | C | CLOSED | 1 | 0 | IN
329 | WIR-Civil-233 | 0 | STR | G-08-09 | Pouring for screed |  |  | 2026-03-07 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
330 | WIR-Civil-234 | 0 | STR | G-08-09 | Prevention Termites-Polythene sheet |  |  | 2026-03-07 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
331 | WIR-Civil-235 | 0 | STR | G-08-09 | Form and steel work of R.C raft |  |  | 2026-01-23 |  | UR | CLOSED | 1 | 0 | IN
332 | WIR-Civil-236 | 0 | STR | Q-C(03-04) | Steel works of screed after H.C.S |  |  | 2026-01-23 |  | UR | CLOSED | 1 | 0 | IN
333 | WIR-Civil-237 | 0 | STR | Q-C(03-04) | Steel works of screed after H.C.S |  |  | 2026-01-23 | 2026-03-07 | B | CLOSED | 1 | 0 | IN
334 | WIR-Civil-238 | 0 | STR | Q-C(03-04) | Surface preparation for R.C footing before insulation |  |  | 2026-01-24 | 2026-02-02 | b | CLOSED | 1 | 0 | IN
335 | WIR-Civil-239 | 0 | STR | Q-C(07-08) | Prevention Termites-Polythene sheet |  |  | 2026-01-24 | 2026-02-02 | b | CLOSED | 1 | 0 | IN
336 | WIR-Civil-240 | 0 | STR | Q-C(07-08) | Form work of P.C footing |  |  | 2026-01-24 | 2026-02-02 | c | CLOSED | 1 | 0 | IN
337 | WIR-Civil-241 | 0 | STR | ZONE :2 Building : Q-K(11-24) | (Form and Steel Work of R.C raft) |  |  | 2026-01-24 | 2026-02-02 | b | CLOSED | 1 | 0 | IN
338 | WIR-Civil-242 | 0 | STR | ZONE :2 Building : Q-K(11-24) | (Pouring For R.C raft) |  |  | 2026-01-24 | 2026-02-02 | c | CLOSED | 1 | 0 | IN
339 | WIR-Civil-243 | 0 | STR | ZONE :2 Building : Q-K(11-24) | (Surface Preparation for R.C Footing Before Insulation) |  |  | 2026-01-24 | 2026-02-02 | b | CLOSED | 1 | 0 | IN
340 | WIR-Civil-244 | 0 | STR | ZONE :2 Building : Q-K(11-24) | (Insulation of R.C raft) |  |  | 2026-01-24 | 2026-02-02 | b | CLOSED | 1 | 0 | IN
341 | WIR-Civil-245 | 0 | STR | ZONE :2 Building : Q-K(11-24) | (Steel structure working) |  |  | 2026-01-24 | 2026-02-02 | c | CLOSED | 1 | 0 | IN
342 | WIR-Civil-246 | 0 | STR | ZONE :2 Building : Q-K(11-24) | (Steel structure working) |  |  | 2026-01-26 | 2026-03-07 | b | CLOSED | 1 | 0 | IN
343 | WIR-Civil-247 | 0 | STR | ZONE :2 Building : Q-K(11-24) | (Pouring For Screed ( ground floor )) |  |  | 2026-01-24 | 2026-02-02 | c | CLOSED | 1 | 0 | IN
344 | WIR-Civil-248 | 0 | STR | ZONE :3-4 Building : Q-K(05-06-18-19) | (Prevention Termites . Polythene Sheet) |  |  | 2026-01-27 | 2026-01-31 | b | CLOSED | 1 | 0 | IN
345 | WIR-Civil-249 | 0 | STR | ZONE :3-4 Building : Q-K(05-06-18-19) | (Form Work of P.C Footing) |  |  | 2026-01-24 | 2026-02-02 | b | CLOSED | 1 | 0 | IN
346 | WIR-Civil-250 | 0 | STR | ZONE :3-4 Building : Q-K(05-06-18-19) | (Pouring For P.C Footing) |  |  | 2026-01-26 | 2026-01-31 | c | CLOSED | 1 | 0 | IN
347 | WIR-Civil-251 | 0 | STR | ZONE :3-4 Building : Q-K(05-06-18-19) | (Form and Steel Work of R.C raft) |  |  | 2026-01-26 | 2026-01-31 | b | CLOSED | 1 | 0 | IN
348 | WIR-Civil-252 | 0 | STR | ZONE :3-4 Building : Q-K(05-06-18-19) | (Pouring For R.C raft) |  |  | 2026-01-26 | 2026-01-31 | c | CLOSED | 1 | 0 | IN
349 | WIR-Civil-253 | 0 | STR | ZONE :3-4 Building : Q-K(05-06-18-19) | (Surface Preparation for R.C Footing Before Insulation) |  |  | 2026-01-26 | 2026-01-31 | b | CLOSED | 1 | 0 | IN
350 | WIR-Civil-254 | 0 | STR | ZONE :3-4 Building : Q-K(05-06-18-19) | (Insulation of R.C raft) |  |  | 2026-01-26 | 2026-01-31 | b | CLOSED | 1 | 0 | IN
351 | WIR-Civil-255 | 0 | STR | ZONE :3-4 Building : Q-K(05-06-18-19) | (Steel structure working) |  |  | 2026-01-26 | 2026-01-31 | c | CLOSED | 1 | 0 | IN
352 | WIR-Civil-256 | 0 | STR | ZONE :3-4 Building : Q-K(05-06-18-19) | (Pouring For Screed ( ground floor )) |  |  | 2026-01-26 | 2026-01-31 | b | CLOSED | 1 | 0 | IN
353 | WIR-Civil-257 | 0 | STR | ZONE :3-4 Building : Q-K(05-06-18-19) | (Installation of H.C.S) |  |  | 2026-01-26 | 2026-01-31 | d | CLOSED | 1 | 0 | IN
354 | WIR-Civil-258 | 0 | STR | ZONE :3-4 Building : Q-K(05-06-18-19) | (Steel works of Screed after H.C.S |  |  | 2026-01-26 | 2026-01-31 | d | CLOSED | 1 | 0 | IN
355 | WIR-Civil-259 | 0 | STR | ZONE :3-4 Building : Q-K(05-06-18-19) | (Pouring For Screed) |  |  | 2026-01-26 | 2026-01-31 | b | CLOSED | 1 | 0 | IN
356 | WIR-Civil-260 | 0 | STR | ZONE :2 Building : Q-K(07-20) | (Prevention Termites . Polythene Sheet) |  |  | 2026-01-31 | 2026-02-02 | b | CLOSED | 1 | 0 | IN
357 | WIR-Civil-261 | 0 | STR | ZONE :2 Building : Q-K(07-20) | (Form Work of P.C Footing) |  |  | 2026-01-31 | 2026-02-02 | b | CLOSED | 1 | 0 | IN
358 | WIR-Civil-262 | 0 | STR | ZONE :2 Building : Q-K(07-20) | (Pouring For P.C Footing) |  |  | 2026-01-31 | 2026-02-02 | c | CLOSED | 1 | 0 | IN
359 | WIR-Civil-263 | 0 | STR | ZONE :2 Building : Q-K(07-20) | (Form and Steel Work of R.C raft) |  |  | 2026-01-31 | 2026-02-02 | b | CLOSED | 1 | 0 | IN
360 | WIR-Civil-264 | 0 | STR | ZONE :2 Building : Q-K(07-20) | (Pouring For R.C raft) |  |  | 2026-01-31 | 2026-02-02 | c | CLOSED | 1 | 0 | IN
361 | WIR-Civil-265 | 0 | STR | ZONE :2 Building : Q-K(07-20) | (Surface Preparation for R.C Footing Before Insulation) |  |  | 2026-01-31 | 2026-02-02 | b | CLOSED | 1 | 0 | IN
362 | WIR-Civil-266 | 0 | STR | ZONE :2 Building : Q-K(07-20) | (Insulation of R.C raft) |  |  | 2026-01-31 | 2026-02-02 | b | CLOSED | 1 | 0 | IN
363 | WIR-Civil-267 | 0 | STR | ZONE :2 Building : Q-K(07-20) | (Steel structure working) |  |  | 2026-01-31 | 2026-02-02 | c | CLOSED | 1 | 0 | IN
364 | WIR-Civil-268 | 0 | STR | ZONE :2 Building : Q-K(07-20) | (Pouring For Screed ( ground floor )) |  |  | 2026-01-31 | 2026-02-02 | c | CLOSED | 1 | 0 | IN
365 | WIR-Civil-269 | 0 | STR | ZONE :2 Building : Q-K(07-20) | (Installation of H.C.S) |  |  | 2026-01-31 | 2026-02-02 | d | CLOSED | 1 | 0 | IN
366 | WIR-Civil-270 | 0 | STR | ZONE :2 Building : Q-K(07-20) | (Steel works of Screed after H.C.S) |  |  | 2026-01-31 | 2026-02-02 | d | CLOSED | 1 | 0 | IN
367 | WIR-Civil-271 | 0 | STR | ZONE :2 Building : Q-K(07-20) | (Pouring For Screed) |  |  | 2026-01-31 | 2026-02-02 | b | CLOSED | 1 | 0 | IN
368 | WIR-Civil-272 | 0 | STR | Building : VIP RECEPTION | Pouring For Upper Beam ands slab |  |  | 2026-01-26 | 2026-02-15 | c | CLOSED | 1 | 0 | IN
369 | WIR-Civil-273 | 0 | STR | Building : VIP RECEPTION | Steel works of Screed UPPER SLAB |  |  | 2026-01-26 | 2026-02-15 | b | CLOSED | 1 | 0 | IN
370 | WIR-Civil-274 | 0 | STR | Building : VIP RECEPTION | Pouring For screed UPPER SLAB |  |  | 2026-01-26 | 2026-02-15 | c | CLOSED | 1 | 0 | IN
371 | WIR-Civil-275 | 0 | STR | Building : VIP RECEPTION | Steel works of S.O.G |  |  | 2026-01-26 | 2026-02-15 | b | CLOSED | 1 | 0 | IN
372 | WIR-Civil-276 | 0 | STR | Building : VIP RECEPTION | Pouring For S.O.G |  |  | 2026-01-26 |  | c | CLOSED | 1 | 0 | IN
373 | WIR-Civil-277 | 0 | STR | Building : GATHERING | Prevention Termites , Polythene Sheet |  |  | 2026-01-26 |  | b | CLOSED | 1 | 0 | IN
374 | WIR-Civil-278 | 0 | STR | Building : GATHERING | Form Work of P.C Footing |  |  | 2026-01-26 |  | b | CLOSED | 1 | 0 | IN
375 | WIR-Civil-279 | 0 | STR | Building : GATHERING | Pouring For P.C Footing |  |  | 2026-01-26 | 2026-02-19 | c | CLOSED | 1 | 0 | IN
376 | WIR-Civil-280 | 0 | STR | Building : GATHERING | Form and Steel Work of R.C Footing |  |  | 2026-01-26 | 2026-02-19 | b | CLOSED | 1 | 0 | IN
377 | WIR-Civil-281 | 0 | STR | Building : GATHERING | Pouring For R.C Footing |  |  | 2026-01-26 | 2026-02-19 | c | CLOSED | 1 | 0 | IN
378 | WIR-Civil-282 | 0 | STR | Building : GATHERING | Surface Preparation for R.C Footing Before Insulation |  |  | 2026-01-26 | 2026-02-19 | b | CLOSED | 1 | 0 | IN
379 | WIR-Civil-283 | 0 | STR | Building : GATHERING | 1st Layer Insulation of R.C Footing |  |  | 2026-01-26 | 2026-02-19 | b | CLOSED | 1 | 0 | IN
380 | WIR-Civil-284 | 0 | STR | Building : GATHERING | 2nd Layer Insulation of R.C Footing |  |  | 2026-01-26 | 2026-03-08 | B | CLOSED | 1 | 0 | IN
381 | WIR-Civil-285 | 0 | STR | Building : GATHERING | Form and Steel Work of Grade Beam |  |  | 2026-01-26 | 2026-02-19 | b | CLOSED | 1 | 0 | IN
382 | WIR-Civil-286 | 0 | STR | Building : GATHERING | Pouring For Grade Beam |  |  | 2026-01-26 | 2026-02-19 | C | CLOSED | 1 | 0 | IN
383 | WIR-Civil-287 | 0 | STR | Building : GATHERING | Surface Preparation for Grade Beam Before Insulation |  |  | 2026-01-26 | 2026-02-19 | b | CLOSED | 1 | 0 | IN
384 | WIR-Civil-288 | 0 | STR | Building : GATHERING | 1st Layer Insulation of Grade Beam |  |  | 2026-01-26 | 2026-02-19 | b | CLOSED | 1 | 0 | IN
385 | WIR-Civil-289 | 0 | STR | Building : GATHERING | 2nd Layer Insulation of Grade Beam |  |  | 2026-01-26 | 2026-02-14 | b | CLOSED | 1 | 0 | IN
386 | WIR-Civil-290 | 0 | STR | Building : GATHERING | Steel Work of Columns |  |  | 2026-01-26 | 2026-02-19 | b | CLOSED | 1 | 0 | IN
387 | WIR-Civil-291 | 0 | STR | Building : GATHERING | Form Work of Columns |  |  | 2026-01-26 | 2026-02-19 | b | CLOSED | 1 | 0 | IN
388 | WIR-Civil-292 | 0 | STR | Building : GATHERING | Pouring For Columns |  |  | 2026-01-26 | 2026-02-19 | C | CLOSED | 1 | 0 | IN
389 | WIR-Civil-293 | 0 | STR | Building : GATHERING | Steel Work of Upper Beam |  |  | 2026-01-26 | 2026-02-19 | C | CLOSED | 1 | 0 | IN
390 | WIR-Civil-294 | 0 | STR | Building : GATHERING | Form Work of Upper Beam |  |  | 2026-01-26 | 2026-02-19 | b | CLOSED | 1 | 0 | IN
391 | WIR-Civil-295 | 0 | STR | Building : GATHERING | Pouring For Upper Beam |  |  | 2026-01-26 | 2026-02-19 | C | CLOSED | 1 | 0 | IN
392 | WIR-Civil-296 | 0 | STR | Building : GATHERING | Steel works of S.O.G |  |  | 2026-01-26 | 2026-02-19 | b | CLOSED | 1 | 0 | IN
393 | WIR-Civil-297 | 0 | STR | Building : GATHERING | Pouring For S.O.G |  |  | 2026-01-26 | 2026-02-19 | C | CLOSED | 1 | 0 | IN
394 | WIR-Civil-298 | 0 | STR | Building : GATHERING | Installation of H.C.S |  |  | 2026-01-26 |  | C | CLOSED | 1 | 0 | IN
395 | WIR-Civil-299 | 0 | STR | Building : GATHERING | Steel works of Screed after H.C.S |  |  | 2026-01-26 | 2026-07-03 | B | CLOSED | 1 | 0 | IN
396 | WIR-Civil-300 | 0 | STR | Building : GATHERING | Pouring For Screed |  |  | 2026-01-26 |  | C | CLOSED | 1 | 0 | IN
397 | WIR-Civil-301 | 0 | STR | Building : CONTROL ROOM | Prevention Termites . Polythene Sheet |  |  | 2026-01-26 |  | UR | CLOSED | 1 | 0 | IN
398 | WIR-Civil-302 | 0 | STR | Building : CONTROL ROOM | Form Work of P.C |  |  | 2026-01-26 |  | UR | CLOSED | 1 | 0 | IN
399 | WIR-Civil-303 | 0 | STR | Building : CONTROL ROOM | Pouring For P.C |  |  | 2026-01-26 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
400 | WIR-Civil-304 | 0 | STR | Building : CONTROL ROOM | Form and Steel Work of R.C raft |  |  | 2026-01-26 |  | UR | CLOSED | 1 | 0 | IN
401 | WIR-Civil-305 | 0 | STR | Building : CONTROL ROOM | Pouring For R.C raft |  |  | 2026-01-26 | 2026-03-25 | B | CLOSED | 1 | 0 | IN
402 | WIR-Civil-306 | 0 | STR | Building : CONTROL ROOM | Surface preparation for r.c raft before insulation |  |  | 2026-01-26 | 2026-03-25 | C | CLOSED | 1 | 0 | IN
403 | WIR-Civil-307 | 0 | STR | ZONE : 2 Building : Q-C(11-12-15-16) | Prevention Termites Polythene Sheet |  |  | 2025-12-26 | 2025-12-30 | B | CLOSED | 1 | 0 | IN
404 | WIR-Civil-308 | 0 | STR | ZONE : 3-4 Building : Q-C(11-12-15-16) | Form Work of P.C Footing |  |  | 2026-01-26 | 2026-01-31 | B | CLOSED | 0 | 0 | IN
405 | WIR-Civil-309 | 0 | STR | ZONE : 2 Building : Q-C(11-12-15-16) | (Pouring For P.C Footing) |  |  | 2026-01-26 | 2026-01-31 | C | CLOSED | 1 | 0 | IN
406 | WIR-Civil-310 | 0 | STR | ZONE :3-4 Building : Q-C(11-12-15-16) | Form and Steel Work of R.C raft |  |  | 2026-01-26 | 2026-01-31 | B | CLOSED | 1 | 0 | IN
407 | WIR-Civil-311 | 0 | STR | ZONE :3-4 Building : Q-C(11-12-15-16) | Pouring For R.C raft |  |  | 2026-01-26 | 2026-01-31 | C | CLOSED | 1 | 0 | IN
408 | WIR-Civil-312 | 0 | STR | ZONE :3-4 Building : Q-C(11-12-15-16) | Surface Preparation for R.C Footing Before Insulation |  |  | 2026-01-26 | 2026-01-31 | B | CLOSED | 1 | 0 | IN
409 | WIR-Civil-313 | 0 | STR | ZONE : 3-4 Building : Q-C(11-12-15-16) | Insulation of R.C raft |  |  | 2026-01-26 | 2026-01-31 | B | CLOSED | 1 | 0 | IN
410 | WIR-Civil-314 | 0 | STR | ZONE : 3-4 Building : Q-C(11-12-15-16) | Steel Work of Columns |  |  | 2026-01-26 | 2026-01-31 | B | CLOSED | 1 | 0 | IN
411 | WIR-Civil-315 | 0 | STR | ZONE : 3-4 Building : Q-C(11-12-15-16) | Form Work of Columns |  |  | 2026-01-26 | 2026-01-31 | B | CLOSED | 1 | 0 | IN
412 | WIR-Civil-316 | 0 | STR | ZONE : 3-4 Building : Q-C(11-12-15-16) | Pouring For Columns |  |  | 2026-01-26 | 2026-01-31 | C | CLOSED | 1 | 0 | IN
413 | WIR-Civil-317 | 0 | STR | ZONE : 3-4 Building : Q-C(11-12-15-16) | Steel Work of Upper Beam and slab |  |  | 2026-01-26 |  | B | CLOSED | 1 | 0 | IN
414 | WIR-Civil-318 | 0 | STR | ZONE : 3-4 Building : Q-C(11-12-15-16) | Form Work of Upper Beam and slab |  |  | 2026-01-26 | 2026-07-03 | B | CLOSED | 1 | 0 | IN
415 | WIR-Civil-319 | 0 | STR | ZONE : 3-4 Building : Q-C(11-12-15-16) | Pouring For Upper Beam ands slab |  |  | 2026-01-26 | 2026-03-25 | C | CLOSED | 1 | 0 | IN
416 | WIR-Civil-320 | 0 | STR | ZONE : 3-4 Building : Q-C(11-12-15-16) | Pouring For screed ( ground floor ) |  |  | 2026-01-26 | 2026-01-31 | C | CLOSED | 1 | 0 | IN
417 | WIR-Civil-321 | 0 | STR | ZONE : 3-4 Building : Q-C(11-12-15-16) | Installation of H.C.S |  |  | 2026-01-26 | 2026-01-31 | D | CLOSED | 1 | 0 | IN
418 | WIR-Civil-322 | 0 | STR | ZONE : 3-4 Building : Q-C(11-12-15-16) | Steel works of Screed after H.C.S |  |  | 2026-01-26 | 2026-01-31 | D | CLOSED | 1 | 0 | IN
419 | WIR-Civil-323 | 0 | STR | ZONE :3-4 Building : Q-C(11-12-15-16) | Pouring For Screed |  |  | 2026-01-26 | 2026-01-31 | C | CLOSED | 1 | 0 | IN
| WIR-Civil-324 | 0 | STR |  | NCR CLOSING -013 |  |  | 2026-02-10 | 2026-10-03 | s
420 | WIR-Civil-324 | 1 | STR |  | NCR CLOSING -013 |  |  | 2026-02-10 | 2026-10-03 | B | CLOSED | 1 | 0 | IN
421 | WIR-Civil-325 | 0 | STR |  | الرد علي NCR-014 |  |  | 2026-02-10 |  | s | CLOSED | 1 | 0 | IN
422 | WIR-Civil-325 | 1 | STR |  | الرد علي NCR-014 |  |  |  | 2026-10-03 | C
423 | WIR-Civil-326 | 0 | STR | Building : VIP RECEPTION | Prevention Termites . Polythene Sheet |  |  | 2026-02-10 |  | B | CLOSED | 1 | 0 | IN
424 | WIR-Civil-327 | 0 | STR | Building : VIP RECEPTION | Form Work of P.C |  |  | 2026-02-10 |  | B | CLOSED | 1 | 0 | IN
425 | WIR-Civil-328 | 0 | STR | Building : VIP RECEPTION | Pouring For P.C |  |  | 2026-02-10 |  | C | CLOSED | 1 | 0 | IN
426 | WIR-Civil-329 | 0 | STR | Building : VIP RECEPTION | Form and Steel Work of R.C raft |  |  | 2026-02-10 |  | B | CLOSED | 1 | 0 | IN
427 | WIR-Civil-330 | 0 | STR | Building : VIP RECEPTION | Pouring For R.C raft |  |  | 2026-02-10 |  | C | CLOSED | 1 | 0 | IN
428 | WIR-Civil-331 | 0 | STR | Building : VIP RECEPTION | Surface Preparation for R.C RAFT Before Insulation |  |  | 2026-02-10 |  | B | CLOSED | 1 | 0 | IN
429 | WIR-Civil-332 | 0 | STR | Building : VIP RECEPTION | Insulation of R.C raft |  |  | 2026-02-10 |  | B | CLOSED | 1 | 0 | IN
430 | WIR-Civil-333 | 0 | STR | Building : VIP RECEPTION | Steel Work of Columns |  |  | 2026-02-10 |  | B | CLOSED | 1 | 0 | IN
431 | WIR-Civil-334 | 0 | STR | Building : VIP RECEPTION | Form Work of Columns |  |  | 2026-02-10 |  | B | CLOSED | 1 | 0 | IN
432 | WIR-Civil-335 | 0 | STR | Building : VIP RECEPTION | Pouring For Columns |  |  | 2026-02-10 |  | C | CLOSED | 1 | 0 | IN
433 | WIR-Civil-336 | 0 | STR | Building : VIP RECEPTION | Steel Work of Upper Beam and slab |  |  | 2026-02-10 |  | B | CLOSED | 1 | 0 | IN
434 | WIR-Civil-337 | 0 | STR | Building : VIP RECEPTION | Form Work of Upper Beam and slab |  |  | 2026-02-10 |  | B | CLOSED | 1 | 0 | IN
435 | WIR-Civil-338 | 0 | STR |  | closing NCR- 005 |  |  | 2026-02-13 | 2026-02-19 | B | CLOSED | 1 | 0 | IN
436 | WIR-Civil-339 | 0 | STR |  | closing NCR- 010 |  |  | 2026-02-13 |  | s | CLOSED | 1 | 0 | IN
437 | WIR-Civil-339 | 1 | STR |  | closing NCR- 010 |  |  | 2026-03-04 | 2026-03-04 | B | CLOSED | 1 | 0 | IN
438 | WIR-Civil-340 | 0 | STR |  | closing NCR- 017 |  |  | 2026-02-13 |  | s | CLOSED | 1 | 0 | IN
439 | WIR-Civil-340 | 1 | STR |  | closing NCR- 017 |  |  | 14/3/2026 | 2026-12-03 | B
440 | WIR-Civil-341 | 0 | STR |  | closing NCR- 019 |  |  | 2026-02-13 |  | C | CLOSED | 1 | 0 | IN
441 | WIR-Civil-342 | 0 | STR |  | closing NCR- 022 |  |  | 2026-02-13 |  | s | CLOSED | 1 | 0 | IN
442 | WIR-Civil-342 | 1 | STR |  | closing NCR- 022 |  |  | 2026-03-02 | 2026-02-03 | B | CLOSED | 1 | 0 | IN
443 | WIR-Civil-343 | 0 | STR |  | closing NCR- 010 |  |  | 2026-02-13 |  | UR | CLOSED | 1 | 0 | IN
444 | WIR-Civil-344 | 0 | STR |  | closing NCR- 018 |  |  | 2026-02-13 |  | s | CLOSED | 1 | 0 | IN
445 | WIR-Civil-344 | 1 | STR |  | closing NCR- 018 |  |  | 2026-03-02 | 2026-12-03 | B
446 | WIR-Civil-345 | 0 | STR |  | closing NCR- 020 |  |  | 2026-02-13 | 2026-10-03 | s | CLOSED | 1 | 0 | IN
| WIR-Civil-345 | 1 | STR |  | closing NCR- 020 |  |  |  |  | B
447 | WIR-Civil-346 | 0 | STR |  | closing NCR- 007 |  |  | 2026-02-13 |  | C | CLOSED | 1 | 0 | IN
448 | WIR-Civil-347 | 0 | STR |  | closing NCR- 008 |  |  | 2026-02-13 |  | s | CLOSED | 1 | 0 | IN
449 | WIR-Civil-347 | 1 | STR |  | closing NCR- 008 |  |  | 2026-03-04 | 2026-03-04 | B | CLOSED | 1 | 0 | IN
450 | WIR-Civil-348 | 0 | STR | CONTROL ROOM | Prevention Termites . Polythene Sheet |  |  | 2026-02-16 | 23/2/2026 | B | CLOSED | 1 | 0 | IN
451 | WIR-Civil-349 | 0 | STR | CONTROL ROOM | Form Work of P.C |  |  | 2026-02-16 | 23/2/2026 | B | CLOSED | 1 | 0 | IN
452 | WIR-Civil-350 | 0 | STR | CONTROL ROOM | Pouring For P.C |  |  | 2026-02-16 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
453 | WIR-Civil-351 | 0 | STR | CONTROL ROOM | Form and Steel Work of R.C raft |  |  | 2026-02-16 | 2026-03-02 | B | CLOSED | 1 | 0 | IN
454 | WIR-Civil-352 | 0 | STR | CONTROL ROOM | Pouring For R.C raft |  |  | 2026-02-16 |  | UR | CLOSED | 1 | 0 | IN
455 | WIR-Civil-353 | 0 | STR | CONTROL ROOM | Surface preparation for R.C footing before insulation |  |  | 2026-02-16 | 23/2/2026 | B | CLOSED | 1 | 0 | IN
456 | WIR-Civil-354 | 0 | STR | CONTROL ROOM | Insulation of R.C raft |  |  | 2026-02-16 | 23/2/2026 | B | CLOSED | 1 | 0 | IN
457 | WIR-Civil-355 | 0 | STR | CONTROL ROOM | Steel work of columns |  |  | 2026-02-16 | 23/2/2026 | B | CLOSED | 1 | 0 | IN
458 | WIR-Civil-356 | 0 | STR | CONTROL ROOM | Form work of Columns |  |  | 2026-02-16 | 23/2/2026 | B | CLOSED | 1 | 0 | IN
459 | WIR-Civil-357 | 0 | STR | CONTROL ROOM | Pouring of Columns |  |  | 2026-02-16 |  | UR | CLOSED | 1 | 0 | IN
460 | WIR-Civil-358 | 0 | STR | CONTROL ROOM | Steel work of upper beam and slab |  |  | 2026-02-16 | 23/2/2026 | B | CLOSED | 1 | 0 | IN
461 | WIR-Civil-359 | 0 | STR | CONTROL ROOM | Forml work of upper beam and slab |  |  | 2026-02-16 | 23/2/2026 | B | CLOSED | 1 | 0 | IN
462 | WIR-Civil-360 | 0 | STR | CONTROL ROOM | Pourinf doe upper beam and slab |  |  | 2026-02-16 |  | UR | CLOSED | 1 | 0 | IN
463 | WIR-Civil-361 | 0 | STR | CONTROL ROOM | Steel works and screed Upper slab |  |  | 2026-02-16 | 23/2/2026 | B | CLOSED | 1 | 0 | IN
464 | WIR-Civil-362 | 0 | STR | CONTROL ROOM | Pouring for screed Upper slab |  |  | 2026-02-16 | 23/2/2026 | B | CLOSED | 1 | 0 | IN
465 | WIR-Civil-363 | 0 | STR | CONTROL ROOM | Steel works of S.O.G |  |  | 2026-02-16 | 23/2/2026 | B | CLOSED | 1 | 0 | IN
466 | WIR-Civil-364 | 0 | STR | CONTROL ROOM | Pouring of S.O.G |  |  | 2026-02-16 |  | UR | CLOSED | 1 | 0 | IN
467 | WIR-Civil-365 | 0 | STR | MAINTENANCE | Prevention Termites-Polythene sheet |  |  | 2026-02-16 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
468 | WIR-Civil-366 | 0 | STR | MAINTENANCE | Form work of P.C |  |  | 2026-02-16 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
469 | WIR-Civil-367 | 0 | STR | MAINTENANCE | Pouring of P.c |  |  | 2026-02-16 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
470 | WIR-Civil-368 | 0 | STR | MAINTENANCE | Form and steel work of R.C raft |  |  | 2026-02-16 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
471 | WIR-Civil-369 | 0 | STR | MAINTENANCE | Pouring for R.C Raft |  |  | 2026-02-16 |  | UR | CLOSED | 1 | 0 | IN
472 | WIR-Civil-370 | 0 | STR | MAINTENANCE | Surface preparation for R.C footing before insulation |  |  | 2026-02-16 | 2026-03-01 | B | CLOSED | 1 | 0 | IN
473 | WIR-Civil-371 | 0 | STR | MAINTENANCE | Insulation of R.C raft |  |  | 2026-02-16 | 2026-03-01 | B | CLOSED | 1 | 0 | IN
474 | WIR-Civil-372 | 0 | STR | MAINTENANCE | Steel Work of Columns |  |  | 2026-02-16 | 2026-03-01 | B | CLOSED | 1 | 0 | IN
475 | WIR-Civil-373 | 0 | STR | MAINTENANCE | Form Work of Columns |  |  | 2026-02-16 | 2026-03-01 | B | CLOSED | 1 | 0 | IN
476 | WIR-Civil-374 | 0 | STR | MAINTENANCE | Pouring For Columns |  |  | 2026-02-16 |  | UR | CLOSED | 1 | 0 | IN
477 | WIR-Civil-375 | 0 | STR | MAINTENANCE | Steel Work of Upper Beam and slab |  |  | 2026-02-16 | 2026-03-01 | B | CLOSED | 1 | 0 | IN
478 | WIR-Civil-376 | 0 | STR | MAINTENANCE | Form Work of Upper Beam and slab |  |  | 2026-02-16 | 2026-03-01 | B | CLOSED | 1 | 0 | IN
479 | WIR-Civil-377 | 0 | STR | MAINTENANCE | Pouring For Upper Beam ands slab |  |  | 2026-02-16 | 2026-03-25 | B | CLOSED | 1 | 0 | IN
480 | WIR-Civil-378 | 0 | STR | MAINTENANCE | Steel works of Screed UPPER SLAB |  |  | 2026-02-16 | 2026-03-01 | B | CLOSED | 1 | 0 | IN
481 | WIR-Civil-379 | 0 | STR | MAINTENANCE | Pouring For screed UPPER SLAB |  |  | 2026-02-16 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
482 | WIR-Civil-380 | 0 | STR | MAINTENANCE | Steel works of S.O.G |  |  | 2026-02-16 | 2026-03-01 | B | CLOSED | 1 | 0 | IN
483 | WIR-Civil-381 | 0 | STR | MAINTENANCE | Pouring For S.O.G |  |  | 2026-02-16 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
484 | WIR-Civil-382 | 0 | STR | FIRST AID | Prevention Termites . Polythene Sheet |  |  | 2026-02-16 |  | UR | CLOSED | 1 | 0 | IN
485 | WIR-Civil-383 | 0 | STR | FIRST AID | Form Work of P.C |  |  | 2026-02-16 | 2026-03-08 | B | CLOSED | 1 | 0 | IN
486 | WIR-Civil-384 | 0 | STR | FIRST AID | Pouring For P.C |  |  | 2026-02-16 | 2026-03-08 | B | CLOSED | 1 | 0 | IN
487 | WIR-Civil-385 | 0 | STR | FIRST AID | Form and Steel Work of R.C raft |  |  | 2026-02-16 |  | UR | CLOSED | 1 | 0 | IN
488 | WIR-Civil-386 | 0 | STR | FIRST AID | Pouring For R.C raft |  |  | 2026-02-16 | 2026-03-08 | B | CLOSED | 1 | 0 | IN
489 | WIR-Civil-387 | 0 | STR | FIRST AID | Surface Preparation for R.C RAFT Before Insulation |  |  | 2026-02-16 | 2026-03-25 | B | CLOSED | 1 | 0 | IN
490 | WIR-Civil-388 | 0 | STR | FIRST AID | Insulation of R.C raft |  |  | 2026-02-16 | 2026-03-08 | B | CLOSED | 1 | 0 | IN
491 | WIR-Civil-389 | 0 | STR | FIRST AID | Steel Work of Columns |  |  | 2026-02-16 | 2026-02-19 | B | CLOSED | 1 | 0 | IN
492 | WIR-Civil-390 | 0 | STR | FIRST AID | Form Work of Columns |  |  | 2026-02-16 | 2026-03-08 | B | CLOSED | 1 | 0 | IN
493 | WIR-Civil-391 | 0 | STR | FIRST AID | Pouring For Columns |  |  | 2026-02-16 | 2026-03-08 | B | CLOSED | 1 | 0 | IN
494 | WIR-Civil-392 | 0 | STR | FIRST AID | Steel Work of Upper Beam and slab |  |  | 2026-02-16 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
495 | WIR-Civil-393 | 0 | STR | FIRST AID | Form Work of Upper Beam and slab |  |  | 2026-02-16 | 2026-02-03 | B | CLOSED | 1 | 0 | IN
496 | WIR-Civil-394 | 0 | STR | FIRST AID | Pouring For Upper Beam ands slab |  |  | 2026-02-16 | 2026-03-25 | B | CLOSED | 1 | 0 | IN
497 | WIR-Civil-395 | 0 | STR | FIRST AID | Steel works of Screed UPPER SLAB |  |  | 2026-02-16 | 2026-02-03 | B | CLOSED | 1 | 0 | IN
498 | WIR-Civil-396 | 0 | STR | FIRST AID | Pouring For screed UPPER SLAB |  |  | 2026-02-16 |  | UR | CLOSED | 1 | 0 | IN
499 | WIR-Civil-397 | 0 | STR | FIRST AID | Steel works of S.O.G |  |  | 2026-02-16 | 2026-03-08 | B | CLOSED | 1 | 0 | IN
500 | WIR-Civil-398 | 0 | STR | FIRST AID | Pouring For S.O.G |  |  | 2026-02-16 | 2026-02-19 | B | CLOSED | 1 | 0 | IN
501 | WIR-Civil-399 | 0 | STR | ANIMAL | Prevention Termites . Polythene Sheet |  |  | 2026-02-16 | 2026-03-08 | B | CLOSED | 1 | 0 | IN
502 | WIR-Civil-400 | 0 | STR | ANIMAL | Form Work of P.C |  |  | 2026-02-16 | 2026-03-08 | B | CLOSED | 1 | 0 | IN
503 | WIR-Civil-401 | 0 | STR | ANIMAL | Pouring For P.C |  |  | 2026-02-16 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
504 | WIR-Civil-402 | 0 | STR | ANIMAL | Form and Steel Work of R.C raft |  |  | 2026-02-16 | 2026-03-12 | B | CLOSED | 1 | 0 | IN
505 | WIR-Civil-403 | 0 | STR | ANIMAL | Pouring For R.C raft |  |  | 2026-02-16 |  | UR | CLOSED | 1 | 0 | IN
506 | WIR-Civil-404 | 0 | STR | ANIMAL | Surface Preparation for R.C RAFT Before Insulation |  |  | 2026-02-16 | 2026-03-08 | B | CLOSED | 1 | 0 | IN
507 | WIR-Civil-405 | 0 | STR | ANIMAL | Insulation of R.C raft |  |  | 2026-02-16 | 2026-03-08 | B | CLOSED | 1 | 0 | IN
508 | WIR-Civil-406 | 0 | STR | ANIMAL | Steel Work of Columns |  |  | 2026-02-16 | 2026-03-12 | B | CLOSED | 1 | 0 | IN
509 | WIR-Civil-407 | 0 | STR | ANIMAL | Form Work of Columns |  |  | 2026-02-16 | 2026-03-12 | B | CLOSED | 1 | 0 | IN
510 | WIR-Civil-408 | 0 | STR | ANIMAL | Pouring For Columns |  |  | 2026-02-16 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
511 | WIR-Civil-409 | 0 | STR | ANIMAL | Steel Work of Upper Beam and slab |  |  | 2026-02-16 | 2026-03-12 | C | CLOSED | 1 | 0 | IN
512 | WIR-Civil-410 | 0 | STR | ANIMAL | Form Work of Upper Beam and slab |  |  | 2026-02-16 | 2026-03-12 | C | CLOSED | 1 | 0 | IN
513 | WIR-Civil-411 | 0 | STR | ANIMAL | Pouring For Upper Beam ands slab |  |  | 2026-02-16 |  | UR | CLOSED | 1 | 0 | IN
514 | WIR-Civil-412 | 0 | STR | ANIMAL | Steel works of Screed UPPER SLAB |  |  | 2026-02-16 | 2026-03-08 | B | CLOSED | 1 | 0 | IN
515 | WIR-Civil-413 | 0 | STR | ANIMAL | Pouring For screed UPPER SLAB |  |  | 2026-02-16 | 2026-03-25 | C | CLOSED | 1 | 0 | IN
516 | WIR-Civil-414 | 0 | STR | ANIMAL | Steel works of S.O.G |  |  | 2026-02-16 | 2026-03-08 | B | CLOSED | 1 | 0 | IN
517 | WIR-Civil-415 | 0 | STR | ANIMAL | Pouring For S.O.G |  |  | 2026-02-16 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
518 | WIR-Civil-416 | 0 | STR | PLAR GROUND | Prevention Termites . Polythene Sheet |  |  |  | 2026-03-08 | B | CLOSED | 1 | 0 | IN
519 | WIR-Civil-417 | 0 | STR | PLAR GROUND | Form Work of P.C |  |  |  | 2026-03-08 | B | CLOSED | 1 | 0 | IN
520 | WIR-Civil-418 | 0 | STR | PLAR GROUND | Pouring For P.C |  |  |  |  | UR | CLOSED | 1 | 0 | IN
521 | WIR-Civil-419 | 0 | STR | PLAR GROUND | Form and Steel Work of R.C FOOTING |  |  |  | 2026-03-08 | B | CLOSED | 1 | 0 | IN
522 | WIR-Civil-420 | 0 | STR | PLAR GROUND | Pouring For R.C FOOTING |  |  |  |  | UR | CLOSED | 1 | 0 | IN
523 | WIR-Civil-421 | 0 | STR | PLAR GROUND | Surface Preparation for R.C FOOTING Before Insulation |  |  |  | 2026-03-08 | B | CLOSED | 1 | 0 | IN
524 | WIR-Civil-422 | 0 | STR | PLAR GROUND | Insulation of R.C FOOTING |  |  |  | 2026-03-08 | B | CLOSED | 1 | 0 | IN
525 | WIR-Civil-423 | 0 | STR | PLAR GROUND | STEEL WORK OF SOG |  |  |  | 2026-03-08 | C | CLOSED | 1 | 0 | IN
526 | WIR-Civil-424 | 0 | STR | PLAR GROUND | Pouring For S.O.G |  |  |  | 2026-03-08 | C | CLOSED | 1 | 0 | IN
527 | WIR-Civil-425 | 0 | STR | Q-G(01-02) | Prevention Termites . Polythene Sheet |  |  | 2026-02-03 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
528 | WIR-Civil-426 | 0 | STR | Q-G(01-02) | Form Work of P.C |  |  | 2026-02-03 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
529 | WIR-Civil-427 | 0 | STR | Q-G(01-02) | Pouring For P.C |  |  |  | 2026-03-10 | B | CLOSED | 1 | 0 | IN
530 | WIR-Civil-428 | 0 | STR | Q-G(01-02) | Form and Steel Work of R.C raft |  |  | 2026-02-03 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
531 | WIR-Civil-429 | 0 | STR | Q-G(01-02) | Form Work of P.C Footing |  |  | 2026-02-03 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
532 | WIR-Civil-430 | 0 | STR | Q-G(01-02) | Pouring For P.C Footing |  |  |  | 2026-03-10 | B | CLOSED | 1 | 0 | IN
533 | WIR-Civil-431 | 0 | STR | Q-G(01-02) | Form and Steel Work of R.C raft |  |  | 2026-02-03 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
534 | WIR-Civil-432 | 0 | STR | Q-G(01-02) | Pouring For R.C raft |  |  |  |  | UR | CLOSED | 1 | 0 | IN
535 | WIR-Civil-433 | 0 | STR | Q-G(01-02) | Surface Preparation for R.C Footing Before Insulation |  |  | 2026-02-03 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
536 | WIR-Civil-434 | 0 | STR | Q-G(01-02) | Insulation of R.C raft |  |  | 2026-02-03 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
537 | WIR-Civil-435 | 0 | STR | Q-G(01-02) | Steel structure working |  |  |  |  | UR | CLOSED | 1 | 0 | IN
538 | WIR-Civil-436 | 0 | STR | Q-G(01-02) | Pouring For Screed ( ground floor ) |  |  |  | 2026-03-25 | C | CLOSED | 1 | 0 | IN
539 | WIR-Civil-437 | 0 | STR | Q-G(01-02) | Installation of H.C.S |  |  |  |  | UR | CLOSED | 1 | 0 | IN
540 | WIR-Civil-438 | 0 | STR | Q-G(01-02) | Steel works of Screed after H.C.S |  |  |  |  | UR | CLOSED | 1 | 0 | IN
541 | WIR-Civil-439 | 0 | STR | Q-G(01-02) | Pouring For Screed |  |  |  | 2026-03-25 | C | CLOSED | 1 | 0 | IN
542 | WIR-Civil-440 | 0 | STR | CAMAL STATION | Prevention Termites . Polythene Sheet |  |  |  | 2026-03-02 | B | CLOSED | 1 | 0 | IN
543 | WIR-Civil-441 | 0 | STR | CAMAL STATION | Form Work of P.C Footing |  |  |  | 2026-03-02 | B | CLOSED | 1 | 0 | IN
544 | WIR-Civil-442 | 0 | STR | CAMAL STATION | Pouring For P.C Footing |  |  |  |  | UR | CLOSED | 1 | 0 | IN
545 | WIR-Civil-443 | 0 | STR | CAMAL STATION | Form and Steel Work of R.C raft |  |  |  | 2026-03-02 | B | CLOSED | 1 | 0 | IN
546 | WIR-Civil-444 | 0 | STR | CAMAL STATION | Pouring For R.C raft |  |  |  |  | UR | CLOSED | 1 | 0 | IN
547 | WIR-Civil-445 | 0 | STR | CAMAL STATION | Surface Preparation for R.C Footing Before Insulation |  |  |  | 2026-03-02 | B | CLOSED | 1 | 0 | IN
548 | WIR-Civil-446 | 0 | STR | CAMAL STATION | Insulation of R.C raft |  |  |  | 2026-03-02 | B | CLOSED | 1 | 0 | IN
549 | WIR-Civil-447 | 0 | STR | CAMAL STATION | Steel structure working |  |  |  |  | UR | CLOSED | 1 | 0 | IN
550 | WIR-Civil-448 | 0 | STR | CAMAL STATION | Pouring For Screed UPPER SANDIWISH PANAL |  |  |  | 2026-03-25 | C | CLOSED | 1 | 0 | IN
551 | WIR-Civil-449 | 0 | STR | CAMAL STATION | Installation of SANDIWISH PANAL |  |  |  | 2026-03-02 | B | CLOSED | 1 | 0 | IN
552 | WIR-Civil-450 | 0 | STR | CAMAL STATION | Steel works of Screed UPPER SANDAWISH PANEL |  |  |  | 2026-03-02 | B | CLOSED | 1 | 0 | IN
553 | WIR-Civil-451 | 0 | STR | CAMAL STATION | Steel works of S.O.G |  |  |  | 2026-03-02 | B | CLOSED | 1 | 0 | IN
554 | WIR-Civil-452 | 0 | STR | CAMAL STATION | Pouring For S.O.G |  |  |  | 2026-03-10 | B | CLOSED | 1 | 0 | IN
555 | WIR-Civil-453 | 0 | STR | LIBRARY | Prevention Termites . Polythene Sheet |  |  |  | 2026-03-08 | B | CLOSED | 1 | 0 | IN
556 | WIR-Civil-454 | 0 | STR | LIBRARY | Form Work of P.C |  |  |  | 2026-03-08 | B | CLOSED | 1 | 0 | IN
557 | WIR-Civil-455 | 0 | STR | LIBRARY | Pouring For P.C |  |  | 2026-02-03 | 2026-03-10 | B | CLOSED | 1 | 0 | IN
558 | WIR-Civil-456 | 0 | STR | LIBRARY | Form and Steel Work of R.C raft |  |  |  | 2026-03-08 | B | CLOSED | 1 | 0 | IN
559 | WIR-Civil-457 | 0 | STR | LIBRARY | Pouring For R.C raft |  |  |  |  | UR | CLOSED | 1 | 0 | IN
560 | WIR-Civil-458 | 0 | STR | LIBRARY | Surface Preparation for R.C RAFT Before Insulation |  |  |  | 2026-02-03 | B | CLOSED | 1 | 0 | IN
561 | WIR-Civil-459 | 0 | STR | LIBRARY | Insulation of R.C raft |  |  |  | 2026-02-03 | B | CLOSED | 1 | 0 | IN
562 | WIR-Civil-460 | 0 | STR | LIBRARY | Steel Work of Columns |  |  |  | 2026-02-03 | B | CLOSED | 1 | 0 | IN
563 | WIR-Civil-461 | 0 | STR | LIBRARY | Form Work of Columns |  |  |  | 2026-02-03 | B | CLOSED | 1 | 0 | IN
564 | WIR-Civil-462 | 0 | STR | LIBRARY | Pouring For Columns |  |  |  |  | UR | CLOSED | 1 | 0 | IN
565 | WIR-Civil-463 | 0 | STR | LIBRARY | Steel Work of Upper Beam and slab |  |  |  | 2026-02-03 | B | CLOSED | 1 | 0 | IN
566 | WIR-Civil-464 | 0 | STR | LIBRARY | Form Work of Upper Beam and slab |  |  |  | 2026-02-03 | B | CLOSED | 1 | 0 | IN
567 | WIR-Civil-465 | 0 | STR | LIBRARY | Pouring For Upper Beam ands slab |  |  |  | 2026-02-25 | C | CLOSED | 1 | 0 | IN
568 | WIR-Civil-466 | 0 | STR | LIBRARY | Steel works of Screed UPPER SLAB |  |  |  | 2026-03-08 | B | CLOSED | 1 | 0 | IN
569 | WIR-Civil-467 | 0 | STR | LIBRARY | Pouring For screed UPPER SLAB |  |  | 2026-02-03 | 2026-03-25 | B | CLOSED | 1 | 0 | IN
570 | WIR-Civil-468 | 0 | STR | LIBRARY | Steel works of S.O.G |  |  |  | 2026-03-08 | B | CLOSED | 1 | 0 | IN
571 | WIR-Civil-469 | 0 | STR | LIBRARY | Pouring For S.O.G |  |  |  | 2026-03-10 | B | CLOSED | 1 | 0 | IN
572 | WIR-Civil-470 | 0 | STR | Q-K(01-02-03-04-08-09-10-12-17-21-22-23-25-30) | Prevention Termites . Polythene Sheet |  |  |  | 2026-03-08 | B | CLOSED | 1 | 0 | IN
573 | WIR-Civil-471 | 0 | STR | Q-K(01-02-03-04-08-09-10-12-17-21-22-23-25-30) | Form Work of P.C Footing |  |  |  | 2026-03-08 | B | CLOSED | 1 | 0 | IN
574 | WIR-Civil-472 | 0 | STR | Q-K(01-02-03-04-08-09-10-12-17-21-22-23-25-30) | Pouring For P.C Footing |  |  |  | 2026-03-10 | B | CLOSED | 1 | 0 | IN
575 | WIR-Civil-473 | 0 | STR | Q-K(01-02-03-04-08-09-10-12-17-21-22-23-25-30) | Form and Steel Work of R.C raft |  |  |  | 2026-03-08 | B | CLOSED | 1 | 0 | IN
576 | WIR-Civil-474 | 0 | STR | Q-K(01-02-03-04-08-09-10-12-17-21-22-23-25-30) | Pouring For R.C raft |  |  |  |  | UR | CLOSED | 1 | 0 | IN
577 | WIR-Civil-475 | 0 | STR | Q-K(01-02-03-04-08-09-10-12-17-21-22-23-25-30) | Surface Preparation for R.C Footing Before Insulation |  |  |  | 2026-03-02 | B | CLOSED | 1 | 0 | IN
578 | WIR-Civil-476 | 0 | STR | Q-K(01-02-03-04-08-09-10-12-17-21-22-23-25-30) | Insulation of R.C raft |  |  |  | 2026-03-02 | B | CLOSED | 1 | 0 | IN
579 | WIR-Civil-477 | 0 | STR | Q-K(01-02-03-04-08-09-10-12-17-21-22-23-25-30) | Steel structure working |  |  |  |  | UR | CLOSED | 1 | 0 | IN
580 | WIR-Civil-478 | 0 | STR | Q-K(01-02-03-04-08-09-10-12-17-21-22-23-25-30) | Pouring For Screed ( ground floor ) |  |  |  |  | C | CLOSED | 1 | 0 | IN
581 | WIR-Civil-479 | 0 | STR | Q-K(01-02-03-04-08-09-10-12-17-21-22-23-25-30) | Installation of H.C.S |  |  |  |  | UR | CLOSED | 1 | 0 | IN
582 | WIR-Civil-480 | 0 | STR | Q-K(01-02-03-04-08-09-10-12-17-21-22-23-25-30) | Steel works of Screed after H.C.S |  |  |  |  | UR | CLOSED | 1 | 0 | IN
583 | WIR-Civil-481 | 0 | STR | Q-K(01-02-03-04-08-09-10-12-17-21-22-23-25-30) | Pouring For Screed |  |  |  |  | C | CLOSED | 1 | 0 | IN
584 | WIR-Civil-482 | 0 | STR | Zone 2 | Civil Final Surface Inspection for 5S External Finish |  |  |  | 2026-07-03 | s | CLOSED | 1 | 0 | IN
585 | WIR-Civil-482 | 1 | STR | Zone 2 | Civil Final Surface Inspection for 5S External Finish |  |  | 2026-02-03 | 2026-03-10 | B
586 | WIR-Civil-483 | 0 | STR | Zone 3 , Zone 4 | Civil Final Surface Inspection for 5S External Finish |  |  |  | 2026-07-03 | s | CLOSED | 1 | 0 | IN
587 | WIR-Civil-483 | 1 | STR | Zone 3 , Zone 4 | Civil Final Surface Inspection for 5S External Finish |  |  | 2026-02-03 | 2026-03-10 | B
588 | WIR-Civil-484 | 0 | STR | 3 parking all Project | Civil Final Surface Inspection for 5S External Finish |  |  |  | 2026-07-03 | s | CLOSED | 1 | 0 | IN
589 | WIR-Civil-484 | 0 | STR | 3 parking all Project | Civil Final Surface Inspection for 5S External Finish |  |  | 2026-02-03 | 2026-03-10 | B
590 | WIR-Civil-485 | 0 | STR | Main Road | Civil Final Surface Inspection for 5S External Finish |  |  |  | 2026-07-03 | s | CLOSED | 1 | 0 | IN
591 | WIR-Civil-485 | 1 | STR | Main Road | Civil Final Surface Inspection for 5S External Finish |  |  | 2026-02-03 | 2026-03-10 | B
592 | WIR-Civil-486 | 0 | STR |  | Closing NCR- 015 |  |  | 14/3/2026 | 2026-10-03 | B | CLOSED
593 | WIR-Civil-487 | 0 | STR |  | Closing NCR- 021 |  |  | 14/3/2026 | 2026-10-03 | s | CLOSED
594 | WIR-Civil-487 | 1 | STR |  | Closing NCR- 021 |  |  | 2026-02-03 | 2026-03-25 | B
595 | WIR-CIVIL-488 | 0 | STR | Zone 2 Fencing | Form Work of P.C Footing |  |  | 14/3/2026 | 2026-03-25 | B
596 | WIR-CIVIL-489 | 0 | STR | Zone 2 Fencing | Pouring for P.C footing |  |  | 14/3/2026 | 2026-03-25 | B
597 | WIR-CIVIL-490 | 0 | STR | Zone 2 Fencing | Form and Steel Work of R.C Footing |  |  | 14/3/2026 | 46106 | B
598 | WIR-CIVIL-491 | 0 | STR | Zone 2 Fencing | Pouring for R.C footing |  |  | 14/3/2026 | 46106 | B
599 | WIR-CIVIL-492 | 0 | STR | Zone 2 Fencing | Insulation of R.C Footing |  |  | 14/3/2026 | 2026-03-25 | B
600 | WIR-CIVIL-493 | 0 | STR | Zone 2 Fencing | Form and Steel Work of Grade Beam |  |  | 14/3/2026 | 2026-03-25 | B
601 | WIR-CIVIL-494 | 0 | STR | Zone 2 Fencing | Form and Steel col |  |  | 14/3/2026 | 2026-03-25 | B
602 | WIR-CIVIL-495 | 0 | STR | Zone 2 Fencing | Pouring For Grade Beam |  |  | 14/3/2026 | 2026-03-25 | C
603 | WIR-CIVIL-496 | 0 | STR | Zone 2 Fencing | Pouring of col |  |  | 14/3/2026 | 2026-03-25 | C
604 | WIR-CIVIL-497 | 0 | STR | Zone 2 Fencing | Form and Steel Work Upper Beam |  |  | 14/3/2026 | 2026-03-23 | B
605 | WIR-CIVIL-498 | 0 | STR | Zone 3 Fencing | Form Work of P.C Footing |  |  | 14/3/2026 | 2026-03-25 | B
606 | WIR-CIVIL-499 | 0 | STR | Zone 3 Fencing | Pouring for P.C footing |  |  | 14/3/2026 | 2026-03-23 | B
607 | WIR-CIVIL-500 | 0 | STR | Zone 3 Fencing | Form and Steel Work of R.C Footing |  |  | 14/3/2026 | 2026-03-23 | B
608 | WIR-CIVIL-501 | 0 | STR | Zone 3 Fencing | Pouring for R.C footing |  |  | 14/3/2026 | 2026-03-23 | B
609 | WIR-CIVIL-502 | 0 | STR | Zone 3 Fencing | Insulation of R.C Footing |  |  | 14/3/2026 | 2026-03-23 | B
610 | WIR-CIVIL-503 | 0 | STR | Zone 3 Fencing | Form and Steel Work of Grade Beam |  |  | 14/3/2026 | 2026-03-23 | B
611 | WIR-CIVIL-504 | 0 | STR | Zone 3 Fencing | Form and Steel col |  |  | 14/3/2026 | 2026-03-23 | B
612 | WIR-CIVIL-505 | 0 | STR | Zone 3 Fencing | Pouring For Grade Beam |  |  | 14/3/2026 |  | C
613 | WIR-CIVIL-506 | 0 | STR | Zone 3 Fencing | Pouring of col |  |  | 14/3/2026 |  | C
614 | WIR-CIVIL-507 | 0 | STR | Zone 3 Fencing | Form and Steel Work Upper Beam |  |  | 14/3/2026 | 46106 | B
615 | WIR-CIVIL-508 | 0 | STR | Zone 4 Fencing | Form Work of P.C Footing |  |  | 14/3/2026 | 2026-03-25 | B
616 | WIR-CIVIL-509 | 0 | STR | Zone 4 Fencing | Pouring for P.C footing |  |  | 14/3/2026 | 2026-03-25 | B
617 | WIR-CIVIL-510 | 0 | STR | Zone 4 Fencing | Form and Steel Work of R.C Footing |  |  | 14/3/2026 | 2026-03-25 | B
618 | WIR-CIVIL-511 | 0 | STR | Zone 4 Fencing | Pouring for R.C footing |  |  | 14/3/2026 | 2026-03-25 | B
619 | WIR-CIVIL-512 | 0 | STR |  | NCR Closing 003 |  |  | 14/3/2026 | 46093 | B
620 | WIR-CIVIL-513 | 0 | STR |  | NCR Closing 004 |  |  |  | 46093 | C
621 | WIR-CIVIL-514 | 0 | STR | Zone 4 Fencing | Form and Steel col |  |  | 14/3/2026 | 2026-03-25 | B
622 | WIR-CIVIL-515 | 0 | STR | Zone 4 Fencing | Pouring For Grade Beam |  |  | 14/3/2026 | 46106 | B
623 | WIR-CIVIL-516 | 0 | STR | Zone 4 Fencing | Pouring of col |  |  | 14/3/2026 | 46106 | C
624 | WIR-CIVIL-517 | 0 | STR | Zone 4 Fencing | Form and Steel Work Upper Beam |  |  | 14/3/2026 | 2026-03-25 | B
625 | WIR-CIVIL-518 | 0 | STR | CENTRAL MOSQUE | Form Work of P.C Footing |  |  | 14/3/2026 | 46097 | B
626 | WIR-CIVIL-519 | 0 | STR | CENTRAL MOSQUE | Pouring for P.C footing |  |  | 14/3/2026 | 46097 | B
627 | WIR-CIVIL-520 | 0 | STR | CENTRAL MOSQUE | Form and Steel Work of R.C Footing |  |  | 14/3/2026 | 46097 | B
628 | WIR-CIVIL-521 | 0 | STR | CENTRAL MOSQUE | Pouring for R.C footing |  |  | 14/3/2026 | 46097 | B
629 | WIR-CIVIL-522 | 0 | STR | CENTRAL MOSQUE | Insulation of R.C Footing |  |  | 14/3/2026 | 46097 | B
630 | WIR-CIVIL-523 | 0 | STR | CENTRAL MOSQUE | Form and Steel Work of Grade Beam |  |  | 14/3/2026 | 46097 | B
631 | WIR-CIVIL-524 | 0 | STR | CENTRAL MOSQUE | Form and Steel col |  |  | 14/3/2026 |  | UR
632 | WIR-CIVIL-525 | 0 | STR | CENTRAL MOSQUE | Pouring For Grade Beam |  |  | 14/3/2026 |  | UR
633 | WIR-CIVIL-526 | 0 | STR | CENTRAL MOSQUE | Pouring of col |  |  | 14/3/2026 | 46097 | B
634 | WIR-CIVIL-527 | 0 | STR | CENTRAL MOSQUE | Form and Steel Work Upper Beam |  |  | 14/3/2026 | 46097 | B
635 | WIR-CIVIL-528 | 0 | STR | CENTRAL MOSQUE | Form and Steel Mosque groundFloor |  |  | 14/3/2026 |  | UR
636 | WIR-CIVIL-529 | 0 | STR | CENTRAL MOSQUE | pouring R.C groundFloor |  |  | 14/3/2026 | 46097 | B
637 | WIR-CIVIL-530 | 0 | STR | CENTRAL MOSQUE | Steel work for s. o .g |  |  | 14/3/2026 | 46097 | B
638 | WIR-CIVIL-531 | 0 | STR | CENTRAL MOSQUE | Powring secreed Upper |  |  | 14/3/2026 | 46097 | B
639 | WIR-CIVIL-532 | 0 | STR | CENTRAL MOSQUE | Powring For S.o .g |  |  | 14/3/2026 | 46097 | B
640 | WIR-CIVIL-533 | 0 | STR | MINARET | Form Work of P.C Footing |  |  | 16/3/2026 | 46097 | B
641 | WIR-CIVIL-534 | 0 | STR | MINARET | Pouring for P.C footing |  |  | 16/3/2026 | 46097 | B
642 | WIR-CIVIL-535 | 0 | STR | MINARET | Form and Steel Work of R.C Footing |  |  | 16/3/2026 |  | UR
643 | WIR-CIVIL-536 | 0 | STR | MINARET | Pouring for R.C footing |  |  | 16/3/2026 |  | UR
644 | WIR-CIVIL-537 | 0 | STR | MINARET | Steel Structure work |  |  | 16/3/2026 | 46097 | B
645 | WIR-CIVIL-538 | 0 | STR | MINARET | Insulation of R.C Footing |  |  | 16/3/2026 | 46106 | B
619 | WIR-CIVIL-539 | 0 | STR | Zone 4 Fencing | Insulation of R.C Footing |  |  | 14/3/2026 | 2026-03-25 | B
620 | WIR-CIVIL-540 | 0 | STR | Zone 4 Fencing | Form and Steel Work of Grade Beam |  |  | 14/3/2026 | 2026-03-25 | B

## ARCH
Inspection Request - ARCH | [9 empty] | A | Approved |  | Date: | 2026-04-02
[10 empty] | B | Approved with notes
[10 empty] | C | Reject & Resubmit
[10 empty] | CC | Not Resubmitted
[10 empty] | UR | Under Review
DOCUMENT REFERENCE NO |  |  | Element | Location | DESCRIPTION | Attachment |  | Outgoing to Consultant |  | Code Action | Status | Progress | Over Duration | scan | Duration
No. | Reference | REV |  |  |  | Dwg | Report | Submission date | Received Date
1 | WIR-ARCH-001 | 0 |  |  | NCR Clossing 001 |  |  | 2025-12-23 | 2025-12-27 | S |  |  |  | IN | 2026-12-03
| WIR-ARCH-001 | 1 |  |  | NCR Clossing 001 |  |  | 2026-02-04 | 2026-02-04 | B
2 | WIR-ARCH-002 | 0 |  |  | NCR Clossing 002 |  |  | 2026-12-23 | 2026-01-01 | C |  |  |  | IN | 2026-12-03
3 | WIR-ARCH-002 | 1 |  |  | NCR Clossing 002 |  |  |  |  | UR
4 | WIR-ARCH-003 | 0 |  | Q-R01 | Inspection of the first fix plastring works |  |  | 2026-12-02 | 2026-02-15 | D |  |  |  | IN | 2026-12-03
5 | WIR-ARCH-004 | 0 |  | Q-R01 | Inspection of the Second fix plastring works |  |  | 2026-12-02 | 2026-02-15 | D |  |  |  | IN | 2026-12-03
6 | WIR-ARCH-005 | 0 |  | Q-R01 | Inspection of wall sealer paint works |  |  | 2026-12-02 | 2026-02-15 | C |  |  |  | IN | 2026-12-03
7 | WIR-ARCH-006 | 0 |  | Q-R01 | Inspection of the first coat putty works |  |  | 2026-12-02 | 2026-02-15 | C |  |  |  | IN
8 | WIR-ARCH-007 | 0 |  | Q-R01 | Inspection of the Second coat putty works |  |  | 2026-12-02 | 2026-02-15 | C |  |  |  | IN
9 | WIR-ARCH-008 | 0 |  | Q-R01 | Inspection of the Third coat putty works |  |  | 2026-02-12 | 2026-02-15 | C |  |  |  | IN
10 | WIR-ARCH-009 | 0 |  | Q-R01 | Inspection of the first coat wall painting works |  |  | 2026-02-12 | 2026-02-15 | C |  |  |  | IN
11 | WIR-ARCH-010 | 0 |  | Q-R01 | Inspection of the second coat wall painting works |  |  | 2026-02-12 | 2026-02-15 | C |  |  |  | IN
12 | WIR-ARCH-011 | 0 |  | Q-R01 | Inspection of the first fix of gybsm board |  |  | 2026-02-12 | 2026-02-15 | B |  |  |  | IN
13 | WIR-ARCH-012 | 0 |  | Q-R01 | Inspection of the second fix of gybsm board |  |  | 2026-02-12 | 2026-02-15 | B |  |  |  | IN
14 | WIR-ARCH-013 | 0 |  | Q-R03 | Inspection of the first fix plastring works |  |  | 2026-02-12 | 2026-02-15 | D |  |  |  | IN
15 | WIR-ARCH-014 | 0 |  | Q-R03 | Inspection of the second fix plastring works |  |  | 2026-02-12 | 2026-02-15 | D |  |  |  | IN
16 | WIR-ARCH-015 | 0 |  | Q-R03 | Inspection of wall sealer paint works |  |  | 2026-02-12 | 2026-02-15 | C |  |  |  | IN
17 | WIR-ARCH-016 | 0 |  | Q-R03 | Inspection of the first coat wall putty works |  |  | 2026-02-12 | 2026-02-15 | C |  |  |  | IN
18 | WIR-ARCH-017 | 0 |  | Q-R03 | Inspection of the Second coat wall putty works |  |  | 2026-02-12 | 2026-02-15 | C |  |  |  | IN
19 | WIR-ARCH-018 | 0 |  | Q-R03 | Inspection of the Third coat wall putty works |  |  | 2026-02-12 | 2026-02-15 | C |  |  |  | IN
20 | WIR-ARCH-019 | 0 |  | Q-R03 | Inspection of the first coat wall putty works |  |  | 2026-02-12 | 2026-02-15 | C |  |  |  | IN
21 | WIR-ARCH-020 | 0 |  | Q-R03 | Inspection of the Second coat wall putty works |  |  | 2026-02-12 | 2026-02-15 | C |  |  |  | IN
22 | WIR-ARCH-021 | 0 |  | Q-R03 | Inspection of the first course masonry alignment |  |  | 2026-02-12 | 2026-02-15 | B |  |  |  | IN
23 | WIR-ARCH-022 | 0 |  | Q-R03 | Inspection of block work for the buildings |  |  | 2026-02-12 | 2026-02-15 | B |  |  |  | IN
24 | WIR-ARCH-023 | 0 |  | Q-R05 | Inspection of the first fix plastering works |  |  | 2026-02-12 | 2026-02-15 | B |  |  |  | IN
25 | WIR-ARCH-024 | 0 |  | Q-R05 | Inspection of the second fix plastering works |  |  | 2026-02-12 | 2026-02-15 | B |  |  |  | IN
26 | WIR-ARCH-025 | 0 |  | Q-R05 | Inspection of wall sealer paint works |  |  | 2026-02-12 | 2026-02-15 | C |  |  |  | IN
27 | WIR-ARCH-026 | 0 |  | Q-R05 | Inspection of the first coat putty works |  |  | 2026-02-12 | 2026-02-15 | C |  |  |  | IN
28 | WIR-ARCH-027 | 0 |  | Q-R05 | Inspection of the second coat putty works |  |  | 2026-02-12 | 2026-02-15 | C |  |  |  | IN
29 | WIR-ARCH-028 | 0 |  | Q-R05 | Inspection of the Third coat putty works |  |  | 2026-02-12 | 2026-02-15 | C |  |  |  | IN
30 | WIR-ARCH-029 | 0 |  | Q-R05 | Inspection of the first coat wall painting works |  |  | 2026-02-12 | 2026-02-15 | C |  |  |  | IN
31 | WIR-ARCH-030 | 0 |  | Q-R05 | Inspection of the second coat wall painting works |  |  | 2026-02-12 | 2026-02-15 | C |  |  |  | IN
32 | WIR-ARCH-031 | 0 |  |  | Closing NCR 016 |  |  | 2026-01-13 | 2026-01-16 | B |  |  |  | IN
33 | WIR-ARCH-032 | 0 |  |  | Closing NCR 017 |  |  | 2026-01-13 | 2026-01-16 | B |  |  |  | IN
34 | WIR-ARCH-033 | 0 |  |  | Closing NCR 015 |  |  | 2026-01-13 | 2026-01-18 | C |  |  |  | IN
35 | WIR-ARCH-033 | 1 |  |  | Closing NCR 015 |  |  |  |  | UR |  |  |  | IN
36 | WIR-ARCH-034 | 0 |  |  | Closed Non Conformance Report No.( NCR-ARCH-021) |  |  |  |  | UR |  |  |  | IN
37 | WIR-ARCH-035 | 0 |  |  | Closed Non Conformance Report No.( NCR-ARCH-020) |  |  |  |  | UR |  |  |  | IN
38 | WIR-ARCH-036 | 0 |  |  | Closed Non Conformance Report No.( NCR-ARCH-03) |  |  |  |  | UR |  |  |  | IN
39 | WIR-ARCH-037 | 0 |  |  | Closed Non Conformance Report No.( NCR-ARCH-04) |  |  |  |  | B |  |  |  | IN
40 | WIR-ARCH-038 | 0 |  |  | Closed Non Conformance Report No.( NCR-ARCH-05) |  |  |  |  | B |  |  |  | IN
41 | WIR-ARCH-039 | 0 |  |  | Closed Non Conformance Report No.( NCR-ARCH-06) |  |  |  |  | B |  |  |  | IN
42 | WIR-ARCH-040 | 0 |  |  | Closed Non Conformance Report No.( NCR-ARCH-019) |  |  |  |  | UR |  |  |  | IN
43 | WIR-ARCH-041 | 0 |  |  | Closed Non Conformance Report No.( NCR-ARCH-08) |  |  |  |  | UR |  |  |  | IN
44 | WIR-ARCH-042 | 0 |  |  | Closed Non Conformance Report No.( NCR-ARCH-09) |  |  |  |  | UR |  |  |  | IN
45 | WIR-ARCH-043 | 0 |  |  | Closed Non Conformance Report No.( NCR-ARCH-010) |  |  |  |  | UR |  |  |  | IN
46 | WIR-ARCH-044 | 0 |  |  | Closed Non Conformance Report No.( NCR-ARCH-011) |  |  |  |  | UR |  |  |  | IN
47 | WIR-ARCH-045 | 0 |  |  | Closed Non Conformance Report No.( NCR-ARCH-012) |  |  |  |  | UR |  |  |  | IN
48 | WIR-ARCH-046 | 0 |  |  | Closed Non Conformance Report No.( NCR-ARCH-013) |  |  |  |  | UR |  |  |  | IN
49 | WIR-ARCH-047 | 0 |  |  | Closed Non Conformance Report No.( NCR-ARCH-014) |  |  |  |  | B |  |  |  | IN
50 | [9 empty] | UR |  |  |  | IN
51 | WIR-ARCH-051 | 0 |  |  | Closed Non Conformance Report No.( NCR-ARCH-018) |  |  |  |  | B |  |  |  | IN
52 | WIR-ARCH-052 | 0 |  |  | Closed Non Conformance Report No.( NCR-ARCH-022) |  |  |  |  | UR |  |  |  | IN
53 | WIR-ARCH-053 | 0 |  |  | Closed Non Conformance Report No.( NCR-ARCH-025) |  |  |  |  | UR |  |  |  | IN
54 | WIR-ARCH-054 | 0 |  | Q-R03 | Inspection of First course masonry alignment works |  |  |  |  | UR |  |  |  | IN
55 | WIR-ARCH-055 | 0 |  | Q-R03 | Inspection of blockwork for the building |  |  |  |  | UR |  |  |  | IN
56 | WIR-ARCH-056 | 0 |  | Q-R05 | Inspection of First course masonry alignment works |  |  |  |  | UR |  |  |  | IN
57 | WIR-ARCH-057 | 0 |  | Q-R05 | Inspection of blockwork for the building |  |  |  |  | UR |  |  |  | IN
58 | WIR-ARCH-058 | 0 |  | Q-C03 | Inspection of First course masonry alignment works |  |  |  |  | UR |  |  |  | IN
59 | WIR-ARCH-059 | 0 |  | Q-C03 | Inspection of blockwork for the building |  |  |  |  | UR |  |  |  | IN
60 | WIR-ARCH-060 | 0 |  | Q-C04 | Inspection of First course masonry alignment works |  |  |  |  | UR |  |  |  | IN
61 | WIR-ARCH-061 | 0 |  | Q-C04 | Inspection of blockwork for the building |  |  |  |  | UR |  |  |  | IN
62 | WIR-ARCH-062 | 0 |  | Q-C05 | Inspection of First course masonry alignment works |  |  |  |  | UR |  |  |  | IN
63 | WIR-ARCH-063 | 0 |  | Q-C05 | Inspection of blockwork for the building |  |  |  |  | UR |  |  |  | IN
64 | WIR-ARCH-064 | 0 |  | Q-C06 | Inspection of First course masonry alignment works |  |  |  |  | UR |  |  |  | IN
65 | WIR-ARCH-065 | 0 |  | Q-C06 | Inspection of blockwork for the building |  |  |  |  | UR |  |  |  | IN
66 | WIR-ARCH-066 | 0 |  | Q-C07 | Inspection of First course masonry alignment works |  |  |  |  | UR |  |  |  | IN
67 | WIR-ARCH-067 | 0 |  | Q-C07 | Inspection of blockwork for the building |  |  |  |  | UR |  |  |  | IN
68 | WIR-ARCH-068 | 0 |  | Q-C08 | Inspection of First course masonry alignment works |  |  |  |  | UR |  |  |  | IN
69 | WIR-ARCH-069 | 0 |  | Q-C08 | Inspection of blockwork for the building |  |  |  |  | UR |  |  |  | IN
70 | WIR-ARCH-070 | 0 |  | Q-C09 | Inspection of First course masonry alignment works |  |  |  |  | UR |  |  |  | IN
71 | WIR-ARCH-071 | 0 |  | Q-C09 | Inspection of blockwork for the building |  |  |  |  | UR |  |  |  | IN
72 | WIR-ARCH-072 | 0 |  | Q-C10 | Inspection of First course masonry alignment works |  |  |  |  | UR |  |  |  | IN
73 | WIR-ARCH-073 | 0 |  | Q-C10 | Inspection of blockwork for the building |  |  |  |  | UR |  |  |  | IN
74 | WIR-ARCH-074 | 0 |  | Q-C11 | Inspection of First course masonry alignment works |  |  |  |  | UR |  |  |  | IN
75 | WIR-ARCH-075 | 0 |  | Q-C11 | Inspection of blockwork for the building |  |  |  |  | UR |  |  |  | IN
76 | WIR-ARCH-076 | 0 |  | Q-C12 | Inspection of First course masonry alignment works |  |  |  |  | UR |  |  |  | IN
77 | WIR-ARCH-077 | 0 |  | Q-C12 | Inspection of blockwork for the building |  |  |  |  | UR |  |  |  | IN
78 | WIR-ARCH-078 | 0 |  | Q-C13 | Inspection of First course masonry alignment works |  |  |  |  | UR |  |  |  | IN
79 | WIR-ARCH-079 | 0 |  | Q-C13 | Inspection of blockwork for the building |  |  |  |  | UR |  |  |  | IN
80 | WIR-ARCH-080 | 0 |  | Q-C14 | Inspection of First course masonry alignment works |  |  |  |  | UR |  |  |  | IN
81 | WIR-ARCH-081 | 0 |  | Q-C14 | Inspection of blockwork for the building |  |  |  |  | UR |  |  |  | IN
82 | WIR-ARCH-082 | 0 |  | Q-C15 | Inspection of First course masonry alignment works |  |  |  |  | UR |  |  |  | IN
83 | WIR-ARCH-083 | 0 |  | Q-C15 | Inspection of blockwork for the building |  |  |  |  | UR |  |  |  | IN
84 | WIR-ARCH-084 | 0 |  | Q-C16 | Inspection of First course masonry alignment works |  |  |  |  | UR |  |  |  | IN
85 | WIR-ARCH-085 | 0 |  | Q-C16 | Inspection of blockwork for the building |  |  |  |  | UR |  |  |  | IN
86 | WIR-ARCH-086 | 0 |  | GA01 | Inspection of First course masonry alignment works |  |  | 25/3/2026 |  | UR |  |  |  | IN
87 | WIR-ARCH-087 | 0 |  | GA01 | Inspection of blockwork for the building |  |  | 25/3/2026 |  | UR |  |  |  | IN
88 | WIR-ARCH-088 | 0 |  | GA02 | Inspection of First course masonry alignment works |  |  | 25/3/2026 |  | UR |  |  |  | IN
89 | WIR-ARCH-089 | 0 |  | GA02 | Inspection of blockwork for the building |  |  | 25/3/2026 |  | UR |  |  |  | IN
90 | WIR-ARCH-090 | 0 |  | GA03 | Inspection of First course masonry alignment works |  |  | 25/3/2026 |  | UR |  |  |  | IN
91 | WIR-ARCH-091 | 0 |  | GA03 | Inspection of blockwork for the building |  |  | 25/3/2026 |  | UR |  |  |  | IN
92 | WIR-ARCH-092 | 0 |  | GA04 | Inspection of First course masonry alignment works |  |  | 25/3/2026 |  | UR |  |  |  | IN
93 | WIR-ARCH-093 | 0 |  | GA04 | Inspection of blockwork for the building |  |  | 25/3/2026 |  | UR |  |  |  | IN
94 | WIR-ARCH-094 | 0 |  | GA05 | Inspection of First course masonry alignment works |  |  | 25/3/2026 |  | UR |  |  |  | IN
95 | WIR-ARCH-095 | 0 |  | GA05 | Inspection of blockwork for the building |  |  | 25/3/2026 |  | UR |  |  |  | IN
96 | WIR-ARCH-096 | 0 |  | GA06 | Inspection of First course masonry alignment works |  |  | 25/3/2026 |  | UR |  |  |  | IN
97 | WIR-ARCH-097 | 0 |  | GA06 | Inspection of blockwork for the building |  |  | 25/3/2026 |  | UR |  |  |  | IN
98 | WIR-ARCH-098 | 0 |  | GA07 | Inspection of First course masonry alignment works |  |  | 25/3/2026 |  | UR |  |  |  | IN
99 | WIR-ARCH-099 | 0 |  | GA07 | Inspection of blockwork for the building |  |  | 25/3/2026 |  | UR |  |  |  | IN
100 | WIR-ARCH-100 | 0 |  | GA08 | Inspection of First course masonry alignment works |  |  | 25/3/2026 |  | UR |  |  |  | IN
101 | WIR-ARCH-101 | 0 |  | GA08 | Inspection of blockwork for the building |  |  | 25/3/2026 |  | UR |  |  |  | IN
102 | WIR-ARCH-102 | 0 |  | GA09 | Inspection of First course masonry alignment works |  |  | 25/3/2026 |  | UR |  |  |  | IN
103 | WIR-ARCH-103 | 0 |  | GA09 | Inspection of blockwork for the building |  |  | 25/3/2026 |  | UR |  |  |  | IN
104 | WIR-ARCH-104 | 0 |  | GA10 | Inspection of First course masonry alignment works |  |  | 25/3/2026 |  | UR |  |  |  | IN
105 | WIR-ARCH-105 | 0 |  | GA10 | Inspection of blockwork for the building |  |  | 25/3/2026 |  | UR |  |  |  | IN
106 | WIR-ARCH-106 | 0 |  | GA11 | Inspection of First course masonry alignment works |  |  | 25/3/2026 |  | UR |  |  |  | IN
107 | WIR-ARCH-107 | 0 |  | GA11 | Inspection of blockwork for the building |  |  | 25/3/2026 |  | UR |  |  |  | IN
108 | WIR-ARCH-108 | 0 |  | VS01 | Inspection of the first fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
109 | WIR-ARCH-109 | 0 |  | VS01 | Inspection of the 2ND fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
110 | WIR-ARCH-110 | 0 |  | VS02 | Inspection of the first fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
111 | WIR-ARCH-111 | 0 |  | VS02 | Inspection of the 2ND fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
112 | WIR-ARCH-112 | 0 |  | VS03 | Inspection of the first fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
113 | WIR-ARCH-113 | 0 |  | VS03 | Inspection of the 2ND fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
114 | WIR-ARCH-114 | 0 |  | VS04 | Inspection of the first fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
115 | WIR-ARCH-115 | 0 |  | VS04 | Inspection of the 2ND fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
116 | WIR-ARCH-116 | 0 |  | VS05 | Inspection of the first fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
117 | WIR-ARCH-117 | 0 |  | VS05 | Inspection of the 2ND fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
118 | WIR-ARCH-118 | 0 |  | VS06 | Inspection of the first fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
119 | WIR-ARCH-119 | 0 |  | VS06 | Inspection of the 2ND fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
120 | WIR-ARCH-120 | 0 |  | VS07 | Inspection of the first fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
121 | WIR-ARCH-121 | 0 |  | VS07 | Inspection of the 2ND fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
122 | WIR-ARCH-122 | 0 |  | VS08 | Inspection of the first fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
123 | WIR-ARCH-123 | 0 |  | VS08 | Inspection of the 2ND fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
124 | WIR-ARCH-124 | 0 |  | VS09 | Inspection of the first fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
125 | WIR-ARCH-125 | 0 |  | VS09 | Inspection of the 2ND fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
126 | WIR-ARCH-126 | 0 |  | VS10 | Inspection of the first fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
127 | WIR-ARCH-127 | 0 |  | VS10 | Inspection of the 2ND fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
128 | WIR-ARCH-128 | 0 |  | VS11 | Inspection of the first fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
129 | WIR-ARCH-129 | 0 |  | VS11 | Inspection of the 2ND fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
130 | WIR-ARCH-130 | 0 |  | VS12 | Inspection of the first fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
131 | WIR-ARCH-131 | 0 |  | VS12 | Inspection of the 2ND fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
132 | WIR-ARCH-132 | 0 |  | VS13 | Inspection of the first fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
133 | WIR-ARCH-133 | 0 |  | VS13 | Inspection of the 2ND fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
134 | WIR-ARCH-134 | 0 |  | VS14 | Inspection of the first fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
135 | WIR-ARCH-135 | 0 |  | VS14 | Inspection of the 2ND fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
136 | WIR-ARCH-136 | 0 |  | VS15 | Inspection of the first fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
137 | WIR-ARCH-137 | 0 |  | VS15 | Inspection of the 2ND fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
138 | WIR-ARCH-138 | 0 |  | VS16 | Inspection of the first fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
139 | WIR-ARCH-139 | 0 |  | VS16 | Inspection of the 2ND fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
140 | WIR-ARCH-140 | 0 |  | VS17 | Inspection of the first fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
141 | WIR-ARCH-141 | 0 |  | VS17 | Inspection of the 2ND fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
142 | WIR-ARCH-142 | 0 |  | VF01 | Inspection of the first fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
143 | WIR-ARCH-143 | 0 |  | VF01 | Inspection of the 2ND fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
144 | WIR-ARCH-144 | 0 |  | VF02 | Inspection of the first fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
145 | WIR-ARCH-145 | 0 |  | VF02 | Inspection of the 2ND fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
146 | WIR-ARCH-146 | 0 |  | VF03 | Inspection of the first fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
147 | WIR-ARCH-147 | 0 |  | VF03 | Inspection of the 2ND fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
148 | WIR-ARCH-148 | 0 |  | VF04 | Inspection of the first fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
149 | WIR-ARCH-149 | 0 |  | VF04 | Inspection of the 2ND fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
150 | WIR-ARCH-150 | 0 |  | VF05 | Inspection of the first fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
151 | WIR-ARCH-151 | 0 |  | VF05 | Inspection of the 2ND fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
152 | WIR-ARCH-152 | 0 |  | VF06 | Inspection of the first fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
153 | WIR-ARCH-153 | 0 |  | VF06 | Inspection of the 2ND fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
154 | WIR-ARCH-154 | 0 |  | VF07 | Inspection of the first fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
155 | WIR-ARCH-155 | 0 |  | VF07 | Inspection of the 2ND fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
156 | WIR-ARCH-156 | 0 |  | VF08 | Inspection of the first fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
157 | WIR-ARCH-157 | 0 |  | VF08 | Inspection of the 2ND fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
158 | WIR-ARCH-158 | 0 |  | VF09 | Inspection of the first fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
159 | WIR-ARCH-159 | 0 |  | VF09 | Inspection of the 2ND fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
160 | WIR-ARCH-160 | 0 |  | VF10 | Inspection of the first fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
161 | WIR-ARCH-161 | 0 |  | VF10 | Inspection of the 2ND fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
162 | WIR-ARCH-162 | 0 |  | ROYAL | Inspection of the first fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
163 | WIR-ARCH-163 | 0 |  | ROYAL | Inspection of the 2ND fix of CEMENT board |  |  | 25/3/2026 |  | UR |  |  |  | IN
164 | WIR-ARCH-164 | 0 |  | E04 | Inspection of First course masonry alignment works |  |  | 25/3/2026 |  | UR |  |  |  | IN
165 | WIR-ARCH-165 | 0 |  | E04 | Inspection of blockwork for the building |  |  | 25/3/2026 |  | UR |  |  |  | IN
166 | WIR-ARCH-166 | 0 |  | CAMEL | Inspection of First course masonry alignment works |  |  | 25/3/2026 |  | UR |  |  |  | IN
167 | WIR-ARCH-167 | 0 |  | CAMEL | Inspection of blockwork for the building |  |  | 25/3/2026 |  | UR |  |  |  | IN
168 | WIR-ARCH-168 | 0 |  | PR01 | Inspection of First course masonry alignment works |  |  | 25/3/2026 |  | UR |  |  |  | IN
169 | WIR-ARCH-169 | 0 |  | PR01 | Inspection of blockwork for the building |  |  | 25/3/2026 |  | UR |  |  |  | IN
170 | WIR-ARCH-170 | 0 |  | WC01 | Inspection of First course masonry alignment works |  |  | 25/3/2026 |  | UR |  |  |  | IN
171 | WIR-ARCH-171 | 0 |  | WC01 | Inspection of blockwork for the building |  |  | 25/3/2026 |  | UR |  |  |  | IN
172 | WIR-ARCH-172 | 0 |  | WC02 | Inspection of First course masonry alignment works |  |  | 25/3/2026 |  | UR |  |  |  | IN
173 | WIR-ARCH-173 | 0 |  | WC02 | Inspection of blockwork for the building |  |  | 25/3/2026 |  | UR |  |  |  | IN
174 | WIR-ARCH-174 | 0 | [11 empty] | IN
175 | WIR-ARCH-175 | 0 |  |  | Closing NCR 005 |  |  | 2026-02-15 | 2026-02-19 | C |  |  |  | IN
176 | WIR-ARCH-176 | 0 |  | Q-C16 | Inspection of the first fix of gepsum board |  |  |  |  | UR |  |  |  | IN
177 | WIR-ARCH-177 | 0 |  | Q-C16 | Inspection of the 2ND fix of gepsumboard |  |  |  |  | UR |  |  |  | IN
178 | WIR-ARCH-178 | 0 |  |  | Closing NCR 008 |  |  | 2026-02-15 | 2026-02-19 | C |  |  |  | IN
179 | WIR-ARCH-179 | 0 |  | k01 | Inspection of the first fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
180 | WIR-ARCH-180 | 0 |  | k01 | Inspection of the 2ND fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
181 | WIR-ARCH-181 | 0 |  | k02 | Inspection of the first fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
182 | WIR-ARCH-182 | 0 |  | k02 | Inspection of the 2ND fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
183 | WIR-ARCH-183 | 0 |  | k03 | Inspection of the first fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
184 | WIR-ARCH-184 | 0 |  | k03 | Inspection of the 2ND fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
185 | WIR-ARCH-185 | 0 |  | k04 | Inspection of the first fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
186 | WIR-ARCH-186 | 0 |  | k04 | Inspection of the 2ND fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
187 | WIR-ARCH-187 | 0 |  | k05 | Inspection of the first fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
188 | WIR-ARCH-188 | 0 |  | k05 | Inspection of the 2ND fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
189 | WIR-ARCH-189 | 0 |  | k06 | Inspection of the first fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
190 | WIR-ARCH-190 | 0 |  | k06 | Inspection of the 2ND fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
191 | WIR-ARCH-191 | 0 |  | k07 | Inspection of the first fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
192 | WIR-ARCH-192 | 0 |  | k07 | Inspection of the 2ND fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
193 | WIR-ARCH-193 | 0 |  | k08 | Inspection of the first fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
194 | WIR-ARCH-194 | 0 |  | k08 | Inspection of the 2ND fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
195 | WIR-ARCH-195 | 0 |  | k09 | Inspection of the first fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
196 | WIR-ARCH-196 | 0 |  | k09 | Inspection of the 2ND fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
197 | WIR-ARCH-197 | 0 |  | k10 | Inspection of the first fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
198 | WIR-ARCH-198 | 0 |  | k10 | Inspection of the 2ND fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
199 | WIR-ARCH-199 | 0 |  | k11 | Inspection of the first fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
200 | WIR-ARCH-200 | 0 |  | k11 | Inspection of the 2ND fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
201 | WIR-ARCH-201 | 0 |  | k12 | Inspection of the first fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
202 | WIR-ARCH-202 | 0 |  | k12 | Inspection of the 2ND fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
203 | WIR-ARCH-203 | 0 |  | k17 | Inspection of the first fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
204 | WIR-ARCH-204 | 0 |  | k17 | Inspection of the 2ND fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
205 | WIR-ARCH-205 | 0 |  | k18 | Inspection of the first fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
206 | WIR-ARCH-206 | 0 |  | k18 | Inspection of the 2ND fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
207 | WIR-ARCH-207 | 0 |  | k19 | Inspection of the first fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
208 | WIR-ARCH-208 | 0 |  | k19 | Inspection of the 2ND fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
209 | WIR-ARCH-209 | 0 |  | k20 | Inspection of the first fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
210 | WIR-ARCH-210 | 0 |  | k20 | Inspection of the 2ND fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
211 | WIR-ARCH-211 | 0 |  | k21 | Inspection of the first fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
212 | WIR-ARCH-212 | 0 |  | k21 | Inspection of the 2ND fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
213 | WIR-ARCH-213 | 0 |  | k22 | Inspection of the first fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
214 | WIR-ARCH-214 | 0 |  | k22 | Inspection of the 2ND fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
215 | WIR-ARCH-215 | 0 |  | k23 | Inspection of the first fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
216 | WIR-ARCH-216 | 0 |  | k23 | Inspection of the 2ND fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
217 | WIR-ARCH-217 | 0 |  | k24 | Inspection of the first fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
218 | WIR-ARCH-218 | 0 |  | k24 | Inspection of the 2ND fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
219 | WIR-ARCH-219 | 0 |  | k25 | Inspection of the first fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
220 | WIR-ARCH-220 | 0 |  | k25 | Inspection of the 2ND fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
221 | WIR-ARCH-221 | 0 |  | k30 | Inspection of the first fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
222 | WIR-ARCH-222 | 0 |  | k30 | Inspection of the 2ND fix of CEMENT board |  |  |  |  | UR |  |  |  | IN
223 | WIR-ARCH-223 | 0 |  | GA01 | Inspection of the first fix of gepsum board |  |  |  |  | UR |  |  |  | IN
224 | WIR-ARCH-224 | 0 |  | GA01 | Inspection of the 2ND fix of gepsumboard |  |  |  |  | UR |  |  |  | IN
225 | WIR-ARCH-225 | 0 |  | GA02 | Inspection of the first fix of gepsum board |  |  |  |  | UR |  |  |  | IN
226 | WIR-ARCH-226 | 0 |  | GA02 | Inspection of the 2ND fix of gepsumboard |  |  |  |  | UR |  |  |  | IN
227 | WIR-ARCH-227 | 0 |  | GA03 | Inspection of the first fix of gepsum board |  |  |  |  | UR |  |  |  | IN
228 | WIR-ARCH-228 | 0 |  | GA03 | Inspection of the 2ND fix of gepsumboard |  |  |  |  | UR |  |  |  | IN
229 | WIR-ARCH-229 | 0 |  | GA04 | Inspection of the first fix of gepsum board |  |  |  |  | UR |  |  |  | IN
230 | WIR-ARCH-230 | 0 |  | GA04 | Inspection of the 2ND fix of gepsumboard |  |  |  |  | UR |  |  |  | IN
231 | WIR-ARCH-231 | 0 |  | GA05 | Inspection of the first fix of gepsum board |  |  |  |  | UR |  |  |  | IN
232 | WIR-ARCH-232 | 0 |  | GA05 | Inspection of the 2ND fix of gepsumboard |  |  |  |  | UR |  |  |  | IN
233 | WIR-ARCH-233 | 0 |  | GA06 | Inspection of the first fix of gepsum board |  |  |  |  | UR |  |  |  | IN
234 | WIR-ARCH-234 | 0 |  | GA06 | Inspection of the 2ND fix of gepsumboard |  |  |  |  | UR |  |  |  | IN
235 | WIR-ARCH-235 | 0 |  | GA07 | Inspection of the first fix of gepsum board |  |  |  |  | UR |  |  |  | IN
236 | WIR-ARCH-236 | 0 |  | GA07 | Inspection of the 2ND fix of gepsumboard |  |  |  |  | UR |  |  |  | IN
237 | WIR-ARCH-237 | 0 |  | GA08 | Inspection of the first fix of gepsum board |  |  |  |  | UR |  |  |  | IN
238 | WIR-ARCH-238 | 0 |  | GA08 | Inspection of the 2ND fix of gepsumboard |  |  |  |  | UR |  |  |  | IN
239 | WIR-ARCH-239 | 0 |  | GA09 | Inspection of the first fix of gepsum board |  |  |  |  | UR |  |  |  | IN
240 | WIR-ARCH-240 | 0 |  | GA09 | Inspection of the 2ND fix of gepsumboard |  |  |  |  | UR |  |  |  | IN
241 | WIR-ARCH-241 | 0 |  | GA10 | Inspection of the first fix of gepsum board |  |  |  |  | UR |  |  |  | IN
242 | WIR-ARCH-242 | 0 |  | GA10 | Inspection of the 2ND fix of gepsumboard |  |  |  |  | UR |  |  |  | IN
243 | WIR-ARCH-243 | 0 |  | GA11 | Inspection of the first fix of gepsum board |  |  |  |  | UR |  |  |  | IN
244 | WIR-ARCH-244 | 0 |  | GA11 | Inspection of the 2ND fix of gepsumboard |  |  |  |  | UR |  |  |  | IN
245 | WIR-ARCH-245 | 0 |  | E04 | Inspection of the first fix of gepsum board |  |  |  |  | UR |  |  |  | IN
246 | WIR-ARCH-246 | 0 |  | E04 | Inspection of the 2ND fix of gepsumboard |  |  |  |  | UR |  |  |  | IN
247 | WIR-ARCH-247 | 0 |  | CAMEL | Inspection of the first fix of gepsum board |  |  |  |  | UR |  |  |  | IN
248 | WIR-ARCH-248 | 0 |  | CAMEL | Inspection of the 2ND fix of gepsumboard |  |  |  |  | UR |  |  |  | IN
249 | WIR-ARCH-249 | 0 |  | PR01 | Inspection of the first fix of gepsum board |  |  |  |  | UR |  |  |  | IN
250 | WIR-ARCH-250 | 0 |  | PR01 | Inspection of the 2ND fix of gepsumboard |  |  |  |  | UR |  |  |  | IN
251 | WIR-ARCH-251 | 0 |  | WC01 | Inspection of the first fix of gepsum board |  |  |  |  | UR |  |  |  | IN
252 | WIR-ARCH-252 | 0 |  | WC01 | Inspection of the 2ND fix of gepsumboard |  |  |  |  | UR |  |  |  | IN
253 | WIR-ARCH-253 | 0 |  | WC02 | Inspection of the first fix of gepsum board |  |  |  |  | UR |  |  |  | IN
254 | WIR-ARCH-254 | 0 |  | WC02 | Inspection of the 2ND fix of gepsumboard |  |  |  |  | UR |  |  |  | IN
255 | WIR-ARCH-255 | 0 |  | E01 | Inspection of First course masonry alignment works |  |  |  |  | UR |  |  |  | IN
256 | WIR-ARCH-256 | 0 |  | E01 | Inspection of blockwork for the building |  |  |  |  | UR |  |  |  | IN
257 | WIR-ARCH-257 | 0 |  | control room | Inspection of First course masonry alignment works |  |  |  |  | UR |  |  |  | IN
258 | WIR-ARCH-258 | 0 |  | control room | Inspection of blockwork for the building |  |  |  |  | UR |  |  |  | IN
259 | WIR-ARCH-259 | 0 |  | MAINTENANCE | Inspection of First course masonry alignment works |  |  |  |  | UR |  |  |  | IN
260 | WIR-ARCH-260 | 0 |  | MAINTENANCE | Inspection of blockwork for the building |  |  |  |  | UR |  |  |  | IN
261 | WIR-ARCH-261 | 0 |  | Q-C018 | Inspection of First course masonry alignment works |  |  |  |  | UR |  |  |  | IN
262 | WIR-ARCH-262 | 0 |  | Q-C019 | Inspection of blockwork for the building |  |  |  |  | UR |  |  |  | IN
263 | WIR-ARCH-263 | 0 |  | Q-C03 | Inspection of the first fix of gepsum board |  |  |  |  | UR |  |  |  | IN
264 | WIR-ARCH-264 | 0 |  | Q-C03 | Inspection of the 2ND fix of gepsumboard |  |  |  |  | UR |  |  |  | IN
265 | WIR-ARCH-265 | 0 |  | Q-C04 | Inspection of the first fix of gepsum board |  |  |  |  | UR |  |  |  | IN
266 | WIR-ARCH-266 | 0 |  | Q-C04 | Inspection of the 2ND fix of gepsumboard |  |  |  |  | UR |  |  |  | IN
267 | WIR-ARCH-267 | 0 |  | Q-C05 | Inspection of the first fix of gepsum board |  |  |  |  | UR |  |  |  | IN
268 | WIR-ARCH-268 | 0 |  | Q-C05 | Inspection of the 2ND fix of gepsumboard |  |  |  |  | UR |  |  |  | IN
269 | WIR-ARCH-269 | 0 |  | Q-C06 | Inspection of the first fix of gepsum board |  |  |  |  | UR |  |  |  | IN
270 | WIR-ARCH-270 | 0 |  | Q-C06 | Inspection of the 2ND fix of gepsumboard |  |  |  |  | UR |  |  |  | IN
271 | WIR-ARCH-271 | 0 |  | Q-C07 | Inspection of the first fix of gepsum board |  |  |  |  | UR |  |  |  | IN
272 | WIR-ARCH-272 | 0 |  | Q-C07 | Inspection of the 2ND fix of gepsumboard |  |  |  |  | UR |  |  |  | IN
273 | WIR-ARCH-273 | 0 |  | Q-C08 | Inspection of the first fix of gepsum board |  |  |  |  | UR |  |  |  | IN
274 | WIR-ARCH-274 | 0 |  | Q-C08 | Inspection of the 2ND fix of gepsumboard |  |  |  |  | UR |  |  |  | IN
275 | WIR-ARCH-275 | 0 |  | Q-C09 | Inspection of the first fix of gepsum board |  |  |  |  | UR |  |  |  | IN
276 | WIR-ARCH-276 | 0 |  | Q-C09 | Inspection of the 2ND fix of gepsumboard |  |  |  |  | UR |  |  |  | IN
277 | WIR-ARCH-277 | 0 |  | Q-C10 | Inspection of the first fix of gepsum board |  |  |  |  | UR |  |  |  | IN
278 | WIR-ARCH-278 | 0 |  | Q-C10 | Inspection of the 2ND fix of gepsumboard |  |  |  |  | UR |  |  |  | IN
279 | WIR-ARCH-279 | 0 |  | Q-C11 | Inspection of the first fix of gepsum board |  |  |  |  | UR |  |  |  | IN
280 | WIR-ARCH-280 | 0 |  | Q-C11 | Inspection of the 2ND fix of gepsumboard |  |  |  |  | UR |  |  |  | IN
281 | WIR-ARCH-281 | 0 |  | Q-C12 | Inspection of the first fix of gepsum board |  |  |  |  | UR |  |  |  | IN
282 | WIR-ARCH-282 | 0 |  | Q-C12 | Inspection of the 2ND fix of gepsumboard |  |  |  |  | UR |  |  |  | IN
283 | WIR-ARCH-283 | 0 |  | Q-C13 | Inspection of the first fix of gepsum board |  |  |  |  | UR |  |  |  | IN
284 | WIR-ARCH-284 | 0 |  | Q-C13 | Inspection of the 2ND fix of gepsumboard |  |  |  |  | UR |  |  |  | IN
285 | WIR-ARCH-285 | 0 |  | Q-C14 | Inspection of the first fix of gepsum board |  |  |  |  | UR |  |  |  | IN
286 | WIR-ARCH-286 | 0 |  | Q-C14 | Inspection of the 2ND fix of gepsumboard |  |  |  |  | UR |  |  |  | IN
287 | WIR-ARCH-287 | 0 |  | Q-C15 | Inspection of the first fix of gepsum board |  |  |  |  | UR |  |  |  | IN
288 | WIR-ARCH-288 | 0 |  | Q-C15 | Inspection of the 2ND fix of gepsumboard |  |  |  |  | UR |  |  |  | IN
289 | WIR-ARCH-289 | [12 empty] | IN
290 | WIR-ARCH-290 | [12 empty] | IN
291 | WIR-ARCH-291 | 0 | [11 empty] | IN
292 | WIR-ARCH-292 | 0 | [11 empty] | IN
293 | WIR-ARCH-293 | 0 | [11 empty] | IN
294 | WIR-ARCH-294 | 0 | [11 empty] | IN
295 | WIR-ARCH-295 | 0 | [11 empty] | IN
296 | WIR-ARCH-296 | 0 | [11 empty] | IN
297 | WIR-ARCH-297 | 0 | [11 empty] | IN
298 | WIR-ARCH-298 | 0 | [11 empty] | IN
299 | WIR-ARCH-299 | 0 | [11 empty] | IN
300 | WIR-ARCH-300 | 0 | [11 empty] | IN
301 | WIR-ARCH-301 | 0 | [11 empty] | IN
302 | WIR-ARCH-302 | 0 | [11 empty] | IN
303 | WIR-ARCH-303 | 0 | [11 empty] | IN
304 | WIR-ARCH-304 | 0 | [11 empty] | IN
305 | WIR-ARCH-305 | 0 | [11 empty] | IN
306 | WIR-ARCH-306 | 0 | [11 empty] | IN
307 | WIR-ARCH-307 | 0 | [11 empty] | IN
308 | WIR-ARCH-308 | 0 | [11 empty] | IN
309 | WIR-ARCH-309 | 0 | [11 empty] | IN
310 | WIR-ARCH-310 | 0 | [11 empty] | IN
311 | WIR-ARCH-311 | 0 | [11 empty] | IN
312 | WIR-ARCH-312 | 0 | [11 empty] | IN
313 | WIR-ARCH-313 | 0 | [11 empty] | IN
314 | WIR-ARCH-314 | 0 | [11 empty] | IN
315 | WIR-ARCH-315 | 0 | [11 empty] | IN
316 | WIR-ARCH-316 | 0 | [11 empty] | IN
317 | WIR-ARCH-317 | 0 | [11 empty] | IN
318 | WIR-ARCH-318 | 0 | [11 empty] | IN
319 | WIR-ARCH-319 | 0 | [11 empty] | IN
320 | WIR-ARCH-320 | 0 | [11 empty] | IN
321 | WIR-ARCH-321 | 0 | [11 empty] | IN
322 | WIR-ARCH-322 | 0 | [11 empty] | IN
323 | WIR-ARCH-323 | 0 | [11 empty] | IN
324 | WIR-ARCH-324 | 0 | [11 empty] | IN
325 | WIR-ARCH-325 | 0 | [11 empty] | IN
326 | WIR-ARCH-326 | 0 | [11 empty] | IN
327 | WIR-ARCH-327 | 0 | [11 empty] | IN
328 | WIR-ARCH-328 | 0 | [11 empty] | IN
329 | WIR-ARCH-329 | 0 | [11 empty] | IN
330 | WIR-ARCH-330 | 0 | [11 empty] | IN
331 | WIR-ARCH-331 | 0 | [11 empty] | IN
332 | WIR-ARCH-332 | 0 | [11 empty] | IN
333 | WIR-ARCH-333 | 0 | [11 empty] | IN
334 | WIR-ARCH-334 | 0 | [11 empty] | IN
335 | WIR-ARCH-335 | 0 | [11 empty] | IN
336 | WIR-ARCH-336 | 0 | [11 empty] | IN
337 | WIR-ARCH-337 | 0 | [11 empty] | IN
338 | WIR-ARCH-338 | 0 | [11 empty] | IN
339 | WIR-ARCH-339 | 0 | [11 empty] | IN
340 | WIR-ARCH-340 | 0 | [11 empty] | IN
341 | WIR-ARCH-341 | 0 | [11 empty] | IN
342 | WIR-ARCH-342 | 0 | [11 empty] | IN
343 | WIR-ARCH-343 | 0 | [11 empty] | IN
344 | WIR-ARCH-344 | 0 | [11 empty] | IN
345 | WIR-ARCH-345 | 0 | [11 empty] | IN
346 | WIR-ARCH-346 | 0 | [11 empty] | IN
347 | WIR-ARCH-347 | 0 | [11 empty] | IN
348 | WIR-ARCH-348 | 0 | [11 empty] | IN
349 | WIR-ARCH-349 | 0 | [11 empty] | IN
350 | WIR-ARCH-350 | 0 | [11 empty] | IN
351 | WIR-ARCH-351 | 0 | [11 empty] | IN
352 | WIR-ARCH-352 | 0 | [11 empty] | IN
353 | WIR-ARCH-353 | 0 | [11 empty] | IN
354 | WIR-ARCH-354 | 0 | [11 empty] | IN
355 | WIR-ARCH-355 | 0 | [11 empty] | IN
356 | WIR-ARCH-356 | 0 | [11 empty] | IN
357 | WIR-ARCH-357 | 0 | [11 empty] | IN
358 | WIR-ARCH-358 | 0 | [11 empty] | IN
359 | WIR-ARCH-359 | 0 | [11 empty] | IN
360 | WIR-ARCH-360 | 0 | [11 empty] | IN
361 | WIR-ARCH-361 | 0 | [11 empty] | IN
362 | WIR-ARCH-362 | 0 | [11 empty] | IN
363 | WIR-ARCH-363 | 0 | [11 empty] | IN
364 | WIR-ARCH-364 | 0 | [11 empty] | IN
365 | WIR-ARCH-365 | 0 | [11 empty] | IN
366 | WIR-ARCH-366 | 0 | [11 empty] | IN
367 | WIR-ARCH-367 | 0 | [11 empty] | IN
368 | WIR-ARCH-368 | 0 | [11 empty] | IN
369 | WIR-ARCH-369 | 0 | [11 empty] | IN
370 | WIR-ARCH-370 | 0 | [11 empty] | IN
371 | WIR-ARCH-371 | 0 | [11 empty] | IN
372 | WIR-ARCH-372 | 0 | [11 empty] | IN
373 | WIR-ARCH-373 | 0 | [11 empty] | IN
374 | WIR-ARCH-374 | 0 | [11 empty] | IN
375 | WIR-ARCH-375 | 0 | [11 empty] | IN
376 | WIR-ARCH-376 | 0 | [11 empty] | IN
377 | WIR-ARCH-377 | 0 | [11 empty] | IN
378 | WIR-ARCH-378 | 0 | [11 empty] | IN
379 | WIR-ARCH-379 | 0 | [11 empty] | IN
380 | WIR-ARCH-380 | 0 | [11 empty] | IN
381 | WIR-ARCH-381 | 0 | [11 empty] | IN
382 | WIR-ARCH-382 | 0 | [11 empty] | IN
383 | WIR-ARCH-383 | 0 | [11 empty] | IN
384 | WIR-ARCH-384 | 0 | [11 empty] | IN
385 | WIR-ARCH-385 | 0 | [11 empty] | IN
386 | WIR-ARCH-386 | 0 | [11 empty] | IN
387 | WIR-ARCH-387 | 0 | [11 empty] | IN
388 | WIR-ARCH-388 | 0 | [11 empty] | IN
389 | WIR-ARCH-389 | 0 | [11 empty] | IN
390 | WIR-ARCH-390 | 0 | [11 empty] | IN
391 | WIR-ARCH-391 | 0 | [11 empty] | IN
392 | WIR-ARCH-392 | 0 | [11 empty] | IN
393 | WIR-ARCH-393 | 0 | [11 empty] | IN
394 | WIR-ARCH-394 | 0 | [11 empty] | IN
395 | WIR-ARCH-395 | 0 | [11 empty] | IN
396 | WIR-ARCH-396 | 0 | [11 empty] | IN
397 | WIR-ARCH-397 | 0 | [11 empty] | IN
398 | WIR-ARCH-398 | 0 | [11 empty] | IN
399 | WIR-ARCH-399 | 0 | [11 empty] | IN
400 | WIR-ARCH-400 | 0 | [11 empty] | IN
401 | WIR-ARCH-401 | 0 | [11 empty] | IN
402 | WIR-ARCH-402 | 0 | [11 empty] | IN
403 | WIR-ARCH-403 | 0 | [11 empty] | IN
404 | WIR-ARCH-404 | 0 | [11 empty] | IN
405 | WIR-ARCH-405 | 0 | [11 empty] | IN
406 | WIR-ARCH-406 | 0 | [11 empty] | IN
407 | WIR-ARCH-407 | 0 | [11 empty] | IN
408 | WIR-ARCH-408 | 0 | [11 empty] | IN
409 | WIR-ARCH-409 | 0 | [11 empty] | IN
410 | WIR-ARCH-410 | 0 | [11 empty] | IN
411 | WIR-ARCH-411 | 0 | [11 empty] | IN
412 | WIR-ARCH-412 | 0 | [11 empty] | IN
413 | WIR-ARCH-413 | 0 | [11 empty] | IN
414 | WIR-ARCH-414 | 0 | [11 empty] | IN
415 | WIR-ARCH-415 | 0 | [11 empty] | IN
416 | WIR-ARCH-416 | 0 | [11 empty] | IN
417 | WIR-ARCH-417 | 0 | [11 empty] | IN
418 | WIR-ARCH-418 | 0 | [11 empty] | IN
419 | WIR-ARCH-419 | 0 | [11 empty] | IN
420 | WIR-ARCH-420 | 0 | [11 empty] | IN
421 | WIR-ARCH-421 | 0 | [11 empty] | IN
422 | WIR-ARCH-422 | 0 | [11 empty] | IN
423 | WIR-ARCH-423 | 0 | [11 empty] | IN
424 | WIR-ARCH-424 | 0 | [11 empty] | IN
425 | WIR-ARCH-425 | 0 | [11 empty] | IN
426 | WIR-ARCH-426 | 0 | [11 empty] | IN
427 | WIR-ARCH-427 | 0 | [11 empty] | IN
428 | WIR-ARCH-428 | 0 | [11 empty] | IN
429 | WIR-ARCH-429 | 0 | [11 empty] | IN
430 | WIR-ARCH-430 | 0 | [11 empty] | IN
431 | WIR-ARCH-431 | 0 | [11 empty] | IN
432 | WIR-ARCH-432 | 0 | [11 empty] | IN
433 | WIR-ARCH-433 | 0 | [11 empty] | IN
434 | WIR-ARCH-434 | 0 | [11 empty] | IN
435 | WIR-ARCH-435 | 0 | [11 empty] | IN
436 | WIR-ARCH-436 | 0 | [11 empty] | IN
437 | WIR-ARCH-437 | 0 | [11 empty] | IN
438 | WIR-ARCH-438 | 0 | [11 empty] | IN
439 | WIR-ARCH-439 | 0 | [11 empty] | IN
440 | WIR-ARCH-440 | 0 | [11 empty] | IN
441 | WIR-ARCH-441 | 0 | [11 empty] | IN
442 | WIR-ARCH-442 | 0 | [11 empty] | IN
443 | WIR-ARCH-443 | 0 | [11 empty] | IN
444 | WIR-ARCH-444 | 0 | [11 empty] | IN
445 | WIR-ARCH-445 | 0 | [11 empty] | IN
446 | WIR-ARCH-446 | 0 | [11 empty] | IN
447 | WIR-ARCH-447 | 0 | [11 empty] | IN
448 | WIR-ARCH-448 | 0 | [11 empty] | IN
449 | WIR-ARCH-449 | 0 | [11 empty] | IN
450 | WIR-ARCH-450 | 0 | [11 empty] | IN
451 | WIR-ARCH-451 | 0 | [11 empty] | IN
452 | WIR-ARCH-452 | 0 | [11 empty] | IN
453 | WIR-ARCH-453 | 0 | [11 empty] | IN
454 | WIR-ARCH-454 | 0 | [11 empty] | IN
455 | WIR-ARCH-455 | 0 | [11 empty] | IN
456 | WIR-ARCH-456 | 0 | [11 empty] | IN
457 | WIR-ARCH-457 | 0 | [11 empty] | IN
458 | WIR-ARCH-458 | 0 | [11 empty] | IN
459 | WIR-ARCH-459 | 0 | [11 empty] | IN
460 | WIR-ARCH-460 | 0 | [11 empty] | IN
461 | WIR-ARCH-461 | 0 | [11 empty] | IN
462 | WIR-ARCH-462 | 0 | [11 empty] | IN
463 | WIR-ARCH-463 | 0 | [11 empty] | IN
464 | WIR-ARCH-464 | 0 | [11 empty] | IN
465 | WIR-ARCH-465 | 0 | [11 empty] | IN
466 | WIR-ARCH-466 | 0 | [11 empty] | IN
467 | WIR-ARCH-467 | 0 | [11 empty] | IN
468 | WIR-ARCH-468 | 0 | [11 empty] | IN
469 | WIR-ARCH-469 | 0 | [11 empty] | IN
470 | WIR-ARCH-470 | 0 | [11 empty] | IN
471 | WIR-ARCH-471 | 0 | [11 empty] | IN
472 | WIR-ARCH-472 | 0 | [11 empty] | IN
473 | WIR-ARCH-473 | 0 | [11 empty] | IN
474 | WIR-ARCH-474 | 0 | [11 empty] | IN
475 | WIR-ARCH-475 | 0 | [11 empty] | IN
476 | WIR-ARCH-476 | 0 | [11 empty] | IN
477 | WIR-ARCH-477 | 0 | [11 empty] | IN
478 | WIR-ARCH-478 | 0 | [11 empty] | IN
479 | WIR-ARCH-479 | 0 | [11 empty] | IN
480 | WIR-ARCH-480 | 0 | [11 empty] | IN
481 | WIR-ARCH-481 | 0 | [11 empty] | IN
482 | WIR-ARCH-482 | 0 | [11 empty] | IN
483 | WIR-ARCH-483 | 0 | [11 empty] | IN
484 | WIR-ARCH-484 | 0 | [11 empty] | IN
485 | WIR-ARCH-485 | 0 | [11 empty] | IN
486 | WIR-ARCH-486 | 0 | [11 empty] | IN
487 | WIR-ARCH-487 | 0 | [11 empty] | IN
488 | WIR-ARCH-488 | 0 | [11 empty] | IN
489 | WIR-ARCH-489 | 0 | [11 empty] | IN
490 | WIR-ARCH-490 | 0 | [11 empty] | IN
491 | WIR-ARCH-491 | 0 | [11 empty] | IN
492 | WIR-ARCH-492 | 0 | [11 empty] | IN
493 | WIR-ARCH-493 | 0 | [11 empty] | IN
494 | WIR-ARCH-494 | 0 | [11 empty] | IN
495 | WIR-ARCH-495 | 0 | [11 empty] | IN
496 | WIR-ARCH-496 | 0 | [11 empty] | IN
497 | WIR-ARCH-497 | 0 | [11 empty] | IN
498 | WIR-ARCH-498 | 0 | [11 empty] | IN
499 | WIR-ARCH-499 | 0 | [11 empty] | IN
500 | WIR-ARCH-500 | 0 | [11 empty] | IN
501 | WIR-ARCH-501 | 0 | [11 empty] | IN
502 | WIR-ARCH-502 | 0 | [11 empty] | IN
503 | WIR-ARCH-503 | 0 | [11 empty] | IN
504 | WIR-ARCH-504 | 0 | [11 empty] | IN
505 | WIR-ARCH-505 | 0 | [11 empty] | IN
506 | WIR-ARCH-506 | 0 | [11 empty] | IN
507 | WIR-ARCH-507 | 0 | [11 empty] | IN
508 | WIR-ARCH-508 | 0 | [11 empty] | IN
509 | WIR-ARCH-509 | 0 | [11 empty] | IN
510 | WIR-ARCH-510 | 0 | [11 empty] | IN
511 | WIR-ARCH-511 | 0 | [11 empty] | IN
512 | WIR-ARCH-512 | 0 | [11 empty] | IN
513 | WIR-ARCH-513 | 0 | [11 empty] | IN
514 | WIR-ARCH-514 | 0 | [11 empty] | IN
515 | WIR-ARCH-515 | 0 | [11 empty] | IN
516 | WIR-ARCH-516 | 0 | [11 empty] | IN
517 | WIR-ARCH-517 | 0 | [11 empty] | IN
518 | WIR-ARCH-518 | 0 | [11 empty] | IN
519 | WIR-ARCH-519 | 0 | [11 empty] | IN
520 | WIR-ARCH-520 | 0 | [11 empty] | IN
521 | WIR-ARCH-521 | 0 | [11 empty] | IN
522 | WIR-ARCH-522 | 0 | [11 empty] | IN
523 | WIR-ARCH-523 | 0 | [11 empty] | IN
524 | WIR-ARCH-524 | 0 | [11 empty] | IN
525 | WIR-ARCH-525 | 0 | [11 empty] | IN
526 | WIR-ARCH-526 | 0 | [11 empty] | IN
527 | WIR-ARCH-527 | 0 | [11 empty] | IN
528 | WIR-ARCH-528 | 0 | [11 empty] | IN
529 | WIR-ARCH-529 | 0 | [11 empty] | IN
530 | WIR-ARCH-530 | 0 | [11 empty] | IN
531 | WIR-ARCH-531 | 0 | [11 empty] | IN
532 | WIR-ARCH-532 | 0 | [11 empty] | IN
533 | WIR-ARCH-533 | 0 | [11 empty] | IN
534 | WIR-ARCH-534 | 0 | [11 empty] | IN
535 | WIR-ARCH-535 | 0 | [11 empty] | IN
536 | WIR-ARCH-536 | 0 | [11 empty] | IN
537 | WIR-ARCH-537 | 0 | [11 empty] | IN
538 | WIR-ARCH-538 | 0 | [11 empty] | IN
539 | WIR-ARCH-539 | 0 | [11 empty] | IN
540 | WIR-ARCH-540 | 0 | [11 empty] | IN
541 | WIR-ARCH-541 | 0 | [11 empty] | IN
542 | WIR-ARCH-542 | 0 | [11 empty] | IN
543 | WIR-ARCH-543 | 0 | [11 empty] | IN
544 | WIR-ARCH-544 | 0 | [11 empty] | IN
545 | WIR-ARCH-545 | 0 | [11 empty] | IN
546 | WIR-ARCH-546 | 0 | [11 empty] | IN
547 | WIR-ARCH-547 | 0 | [11 empty] | IN
548 | WIR-ARCH-548 | 0 | [11 empty] | IN
549 | WIR-ARCH-549 | 0 | [11 empty] | IN
550 | WIR-ARCH-550 | 0 | [11 empty] | IN
551 | WIR-ARCH-551 | 0 | [11 empty] | IN
552 | WIR-ARCH-552 | 0 | [11 empty] | IN
553 | WIR-ARCH-553 | 0 | [11 empty] | IN
554 | WIR-ARCH-554 | 0 | [11 empty] | IN
555 | WIR-ARCH-555 | 0 | [11 empty] | IN
556 | WIR-ARCH-556 | 0 | [11 empty] | IN
557 | WIR-ARCH-557 | 0 | [11 empty] | IN
558 | WIR-ARCH-558 | 0 | [11 empty] | IN
559 | WIR-ARCH-559 | 0 | [11 empty] | IN
560 | WIR-ARCH-560 | 0 | [11 empty] | IN
561 | WIR-ARCH-561 | 0 | [11 empty] | IN
562 | WIR-ARCH-562 | 0 | [11 empty] | IN
563 | WIR-ARCH-563 | 0 | [11 empty] | IN
564 | WIR-ARCH-564 | 0 | [11 empty] | IN
565 | WIR-ARCH-565 | 0 | [11 empty] | IN
566 | WIR-ARCH-566 | 0 | [11 empty] | IN
567 | WIR-ARCH-567 | 0 | [11 empty] | IN
568 | WIR-ARCH-568 | 0 | [11 empty] | IN
569 | WIR-ARCH-569 | 0 | [11 empty] | IN
570 | WIR-ARCH-570 | 0 | [11 empty] | IN
571 | WIR-ARCH-571 | 0 | [11 empty] | IN
572 | WIR-ARCH-572 | 0 | [11 empty] | IN
573 | WIR-ARCH-573 | 0 | [11 empty] | IN
574 | WIR-ARCH-574 | 0 | [11 empty] | IN
575 | WIR-ARCH-575 | 0 | [11 empty] | IN
576 | WIR-ARCH-576 | 0 | [11 empty] | IN
577 | WIR-ARCH-577 | 0 | [11 empty] | IN
578 | WIR-ARCH-578 | 0 | [11 empty] | IN
579 | WIR-ARCH-579 | 0 | [11 empty] | IN
580 | WIR-ARCH-580 | 0 | [11 empty] | IN
581 | WIR-ARCH-581 | 0 | [11 empty] | IN
582 | WIR-ARCH-582 | 0 | [11 empty] | IN
583 | WIR-ARCH-583 | 0 | [11 empty] | IN
584 | WIR-ARCH-584 | 0 | [11 empty] | IN
585 | WIR-ARCH-585 | 0 | [11 empty] | IN
586 | WIR-ARCH-586 | 0 | [11 empty] | IN
587 | WIR-ARCH-587 | 0 | [11 empty] | IN
588 | WIR-ARCH-588 | 0 | [11 empty] | IN
589 | WIR-ARCH-589 | 0 | [11 empty] | IN
590 | WIR-ARCH-590 | 0 | [11 empty] | IN
591 | WIR-ARCH-591 | 0 | [11 empty] | IN
592 | WIR-ARCH-592 | 0 | [11 empty] | IN
593 | WIR-ARCH-593 | 0 | [11 empty] | IN
594 | WIR-ARCH-594 | 0 | [11 empty] | IN
595 | WIR-ARCH-595 | 0 | [11 empty] | IN
596 | WIR-ARCH-596 | 0 | [11 empty] | IN
597 | WIR-ARCH-597 | 0 | [11 empty] | IN
598 | WIR-ARCH-598 | 0 | [11 empty] | IN
599 | WIR-ARCH-599 | 0 | [11 empty] | IN
600 | WIR-ARCH-600 | 0 | [11 empty] | IN
601 | WIR-ARCH-601 | 0 | [11 empty] | IN
602 | WIR-ARCH-602 | 0 | [11 empty] | IN
603 | WIR-ARCH-603 | 0 | [11 empty] | IN
604 | WIR-ARCH-604 | 0 | [11 empty] | IN
605 | WIR-ARCH-605 | 0 | [11 empty] | IN
606 | WIR-ARCH-606 | 0 | [11 empty] | IN
607 | WIR-ARCH-607 | 0 | [11 empty] | IN
608 | WIR-ARCH-608 | 0 | [11 empty] | IN
609 | WIR-ARCH-609 | 0 | [11 empty] | IN
610 | WIR-ARCH-610 | 0 | [11 empty] | IN
611 | WIR-ARCH-611 | 0 | [11 empty] | IN
612 | WIR-ARCH-612 | 0 | [11 empty] | IN
613 | WIR-ARCH-613 | 0 | [11 empty] | IN
614 | WIR-ARCH-614 | 0 | [11 empty] | IN
615 | WIR-ARCH-615 | 0 | [11 empty] | IN
616 | WIR-ARCH-616 | 0 | [11 empty] | IN
617 | WIR-ARCH-617 | 0 | [11 empty] | IN
618 | WIR-ARCH-618 | 0 | [11 empty] | IN
619 | WIR-ARCH-619 | 0 | [11 empty] | IN
620 | WIR-ARCH-620 | 0 | [11 empty] | IN
621 | WIR-ARCH-621 | 0 | [11 empty] | IN
622 | WIR-ARCH-622 | 0 | [11 empty] | IN
623 | WIR-ARCH-623 | 0 | [11 empty] | IN
624 | WIR-ARCH-624 | 0 | [11 empty] | IN
625 | WIR-ARCH-625 | 0 | [11 empty] | IN
626 | WIR-ARCH-626 | 0 | [11 empty] | IN
627 | WIR-ARCH-627 | 0 | [11 empty] | IN
628 | WIR-ARCH-628 | 0 | [11 empty] | IN
629 | WIR-ARCH-629 | 0 | [11 empty] | IN
630 | WIR-ARCH-630 | 0 | [11 empty] | IN
631 | WIR-ARCH-631 | 0 | [11 empty] | IN
632 | WIR-ARCH-632 | 0 | [11 empty] | IN
633 | WIR-ARCH-633 | 0 | [11 empty] | IN
634 | WIR-ARCH-634 | 0 | [11 empty] | IN
635 | WIR-ARCH-635 | 0 | [11 empty] | IN
636 | WIR-ARCH-636 | 0 | [11 empty] | IN
637 | WIR-ARCH-637 | 0 | [11 empty] | IN
638 | WIR-ARCH-638 | 0 | [11 empty] | IN
639 | WIR-ARCH-639 | 0 | [11 empty] | IN
640 | WIR-ARCH-640 | 0 | [11 empty] | IN
641 | WIR-ARCH-641 | 0 | [11 empty] | IN
642 | WIR-ARCH-642 | 0 | [11 empty] | IN
643 | WIR-ARCH-643 | 0 | [11 empty] | IN
644 | WIR-ARCH-644 | 0 | [11 empty] | IN
645 | WIR-ARCH-645 | 0 | [11 empty] | IN
646 | WIR-ARCH-646 | 0 | [11 empty] | IN
647 | WIR-ARCH-647 | 0 | [11 empty] | IN
648 | WIR-ARCH-648 | 0 | [11 empty] | IN
649 | WIR-ARCH-649 | 0 | [11 empty] | IN
650 | WIR-ARCH-650 | 0 | [11 empty] | IN
651 | WIR-ARCH-651 | 0 | [11 empty] | IN
652 | WIR-ARCH-652 | 0 | [11 empty] | IN
653 | WIR-ARCH-653 | 0 | [11 empty] | IN
654 | WIR-ARCH-654 | 0 | [11 empty] | IN
655 | WIR-ARCH-655 | 0 | [11 empty] | IN
656 | WIR-ARCH-656 | 0 | [11 empty] | IN
657 | WIR-ARCH-657 | 0 | [11 empty] | IN
658 | WIR-ARCH-658 | 0 | [11 empty] | IN
659 | WIR-ARCH-659 | 0 | [11 empty] | IN
660 | WIR-ARCH-660 | 0 | [11 empty] | IN
661 | WIR-ARCH-661 | 0 | [11 empty] | IN
662 | WIR-ARCH-662 | 0 | [11 empty] | IN
663 | WIR-ARCH-663 | 0 | [11 empty] | IN
664 | WIR-ARCH-664 | 0 | [11 empty] | IN
665 | WIR-ARCH-665 | 0 | [11 empty] | IN
666 | WIR-ARCH-666 | 0 | [11 empty] | IN
667 | WIR-ARCH-667 | 0 | [11 empty] | IN
668 | WIR-ARCH-668 | 0 | [11 empty] | IN
669 | WIR-ARCH-669 | 0 | [11 empty] | IN
670 | WIR-ARCH-670 | 0 | [11 empty] | IN
671 | WIR-ARCH-671 | 0 | [11 empty] | IN
672 | WIR-ARCH-672 | 0 | [11 empty] | IN
673 | WIR-ARCH-673 | 0 | [11 empty] | IN
674 | WIR-ARCH-674 | 0 | [11 empty] | IN
675 | WIR-ARCH-675 | 0 | [11 empty] | IN
676 | WIR-ARCH-676 | 0 | [11 empty] | IN
677 | WIR-ARCH-677 | 0 | [11 empty] | IN
678 | WIR-ARCH-678 | 0 | [11 empty] | IN
679 | WIR-ARCH-679 | 0 | [11 empty] | IN
680 | WIR-ARCH-680 | 0 | [11 empty] | IN
681 | WIR-ARCH-681 | 0 | [11 empty] | IN
682 | WIR-ARCH-682 | 0 | [11 empty] | IN
683 | WIR-ARCH-683 | 0 | [11 empty] | IN
684 | WIR-ARCH-684 | 0 | [11 empty] | IN
685 | WIR-ARCH-685 | 0 | [11 empty] | IN
686 | WIR-ARCH-686 | 0 | [11 empty] | IN
687 | WIR-ARCH-687 | 0 | [11 empty] | IN
688 | WIR-ARCH-688 | 0 | [11 empty] | IN
689 | WIR-ARCH-689 | 0 | [11 empty] | IN
690 | WIR-ARCH-690 | 0 | [11 empty] | IN
691 | WIR-ARCH-691 | 0 | [11 empty] | IN
692 | WIR-ARCH-692 | 0 | [11 empty] | IN
693 | WIR-ARCH-693 | 0 | [11 empty] | IN
694 | WIR-ARCH-694 | 0 | [11 empty] | IN
695 | WIR-ARCH-695 | 0 | [11 empty] | IN
696 | WIR-ARCH-696 | 0 | [11 empty] | IN
697 | WIR-ARCH-697 | 0 | [11 empty] | IN
698 | WIR-ARCH-698 | 0 | [11 empty] | IN
699 | WIR-ARCH-699 | 0 | [11 empty] | IN
700 | WIR-ARCH-700 | 0 | [11 empty] | IN
701 | WIR-ARCH-701 | 0 | [11 empty] | IN
702 | WIR-ARCH-702 | 0 | [11 empty] | IN
703 | WIR-ARCH-703 | 0 | [11 empty] | IN
704 | WIR-ARCH-704 | 0 | [11 empty] | IN
705 | WIR-ARCH-705 | 0 | [11 empty] | IN
706 | WIR-ARCH-706 | 0 | [11 empty] | IN
707 | WIR-ARCH-707 | 0 | [11 empty] | IN
708 | WIR-ARCH-708 | 0 | [11 empty] | IN
709 | WIR-ARCH-709 | 0 | [11 empty] | IN
710 | WIR-ARCH-710 | 0 | [11 empty] | IN
711 | WIR-ARCH-711 | 0 | [11 empty] | IN
712 | WIR-ARCH-712 | 0 | [11 empty] | IN
713 | WIR-ARCH-713 | 0 | [11 empty] | IN
714 | WIR-ARCH-714 | 0 | [11 empty] | IN
715 | WIR-ARCH-715 | 0 | [11 empty] | IN
716 | WIR-ARCH-716 | 0 | [11 empty] | IN
717 | WIR-ARCH-717 | 0 | [11 empty] | IN
718 | WIR-ARCH-718 | 0 | [11 empty] | IN
719 | WIR-ARCH-719 | 0 | [11 empty] | IN
720 | WIR-ARCH-720 | 0 | [11 empty] | IN
721 | WIR-ARCH-721 | 0 | [11 empty] | IN
722 | WIR-ARCH-722 | 0 | [11 empty] | IN
723 | WIR-ARCH-723 | 0 | [11 empty] | IN
724 | WIR-ARCH-724 | 0 | [11 empty] | IN
725 | WIR-ARCH-725 | 0 | [11 empty] | IN
726 | WIR-ARCH-726 | 0 | [11 empty] | IN
727 | WIR-ARCH-727 | 0 | [11 empty] | IN
728 | WIR-ARCH-728 | 0 | [11 empty] | IN
729 | WIR-ARCH-729 | 0 | [11 empty] | IN
730 | WIR-ARCH-730 | 0 | [11 empty] | IN
731 | WIR-ARCH-731 | 0 | [11 empty] | IN
732 | WIR-ARCH-732 | 0 | [11 empty] | IN
733 | WIR-ARCH-733 | 0 | [11 empty] | IN
734 | WIR-ARCH-734 | 0 | [11 empty] | IN
735 | WIR-ARCH-735 | 0 | [11 empty] | IN
736 | WIR-ARCH-736 | 0 | [11 empty] | IN
737 | WIR-ARCH-737 | 0 | [11 empty] | IN
738 | WIR-ARCH-738 | 0 | [11 empty] | IN
739 | WIR-ARCH-739 | 0 | [11 empty] | IN
740 | WIR-ARCH-740 | 0 | [11 empty] | IN
741 | WIR-ARCH-741 | 0 | [11 empty] | IN
742 | WIR-ARCH-742 | 0 | [11 empty] | IN
743 | WIR-ARCH-743 | 0 | [11 empty] | IN
744 | WIR-ARCH-744 | 0 | [11 empty] | IN
745 | WIR-ARCH-745 | 0 | [11 empty] | IN
746 | WIR-ARCH-746 | 0 | [11 empty] | IN
747 | WIR-ARCH-747 | 0 | [11 empty] | IN
748 | WIR-ARCH-748 | 0 | [11 empty] | IN
749 | WIR-ARCH-749 | 0 | [11 empty] | IN
750 | WIR-ARCH-750 | 0 | [11 empty] | IN
751 | WIR-ARCH-751 | 0 | [11 empty] | IN
752 | WIR-ARCH-752 | 0 | [11 empty] | IN
753 | WIR-ARCH-753 | 0 | [11 empty] | IN
754 | WIR-ARCH-754 | 0 | [11 empty] | IN
755 | WIR-ARCH-755 | 0 | [11 empty] | IN
756 | WIR-ARCH-756 | 0 | [11 empty] | IN
757 | WIR-ARCH-757 | 0 | [11 empty] | IN
758 | WIR-ARCH-758 | 0 | [11 empty] | IN
759 | WIR-ARCH-759 | 0 | [11 empty] | IN
760 | WIR-ARCH-760 | 0 | [11 empty] | IN
761 | WIR-ARCH-761 | 0 | [11 empty] | IN
762 | WIR-ARCH-762 | 0 | [11 empty] | IN
763 | WIR-ARCH-763 | 0 | [11 empty] | IN
764 | WIR-ARCH-764 | 0 | [11 empty] | IN
765 | WIR-ARCH-765 | 0 | [11 empty] | IN
766 | WIR-ARCH-766 | 0 | [11 empty] | IN
767 | WIR-ARCH-767 | 0 | [11 empty] | IN
768 | WIR-ARCH-768 | 0 | [11 empty] | IN
769 | WIR-ARCH-769 | 0 | [11 empty] | IN
770 | WIR-ARCH-770 | 0 | [11 empty] | IN
771 | WIR-ARCH-771 | 0 | [11 empty] | IN
772 | WIR-ARCH-772 | 0 | [11 empty] | IN
773 | WIR-ARCH-773 | 0 | [11 empty] | IN
774 | WIR-ARCH-774 | 0 | [11 empty] | IN
775 | WIR-ARCH-775 | 0 | [11 empty] | IN
776 | WIR-ARCH-776 | 0 | [11 empty] | IN
777 | WIR-ARCH-777 | 0 | [11 empty] | IN
778 | WIR-ARCH-778 | 0 | [11 empty] | IN
779 | WIR-ARCH-779 | 0 | [11 empty] | IN
780 | WIR-ARCH-780 | 0 | [11 empty] | IN
781 | WIR-ARCH-781 | 0 | [11 empty] | IN
782 | WIR-ARCH-782 | 0 | [11 empty] | IN
783 | WIR-ARCH-783 | 0 | [11 empty] | IN
784 | WIR-ARCH-784 | 0 | [11 empty] | IN
785 | WIR-ARCH-785 | 0 | [11 empty] | IN
786 | WIR-ARCH-786 | 0 | [11 empty] | IN
787 | WIR-ARCH-787 | 0 | [11 empty] | IN
788 | WIR-ARCH-788 | 0 | [11 empty] | IN
789 | WIR-ARCH-789 | 0 | [11 empty] | IN
790 | WIR-ARCH-790 | 0 | [11 empty] | IN
791 | WIR-ARCH-791 | 0 | [11 empty] | IN
792 | WIR-ARCH-792 | 0 | [11 empty] | IN
793 | WIR-ARCH-793 | 0 | [11 empty] | IN
794 | WIR-ARCH-794 | 0 | [11 empty] | IN
795 | WIR-ARCH-795 | 0 | [11 empty] | IN
796 | WIR-ARCH-796 | 0 | [11 empty] | IN
797 | WIR-ARCH-797 | 0 | [11 empty] | IN
798 | WIR-ARCH-798 | 0 | [11 empty] | IN
799 | WIR-ARCH-799 | 0 | [11 empty] | IN
800 | WIR-ARCH-800 | 0 | [11 empty] | IN
801 | WIR-ARCH-801 | 0 | [11 empty] | IN
802 | WIR-ARCH-802 | 0 | [11 empty] | IN
803 | WIR-ARCH-803 | 0 | [11 empty] | IN
804 | WIR-ARCH-804 | 0 | [11 empty] | IN
805 | WIR-ARCH-805 | 0 | [11 empty] | IN
806 | WIR-ARCH-806 | 0 | [11 empty] | IN
807 | WIR-ARCH-807 | 0 | [11 empty] | IN
808 | WIR-ARCH-808 | 0 | [11 empty] | IN
809 | WIR-ARCH-809 | 0 | [11 empty] | IN
810 | WIR-ARCH-810 | 0 | [11 empty] | IN
811 | WIR-ARCH-811 | 0 | [11 empty] | IN
812 | WIR-ARCH-812 | 0 | [11 empty] | IN
813 | WIR-ARCH-813 | 0 | [11 empty] | IN
814 | WIR-ARCH-814 | 0 | [11 empty] | IN
815 | WIR-ARCH-815 | 0 | [11 empty] | IN
816 | WIR-ARCH-816 | 0 | [11 empty] | IN
817 | WIR-ARCH-817 | 0 | [11 empty] | IN
818 | WIR-ARCH-818 | 0 | [11 empty] | IN
819 | WIR-ARCH-819 | 0 | [11 empty] | IN
820 | WIR-ARCH-820 | 0 | [11 empty] | IN
821 | WIR-ARCH-821 | 0 | [11 empty] | IN
822 | WIR-ARCH-822 | 0 | [11 empty] | IN
823 | WIR-ARCH-823 | 0 | [11 empty] | IN
824 | WIR-ARCH-824 | 0 | [11 empty] | IN
825 | WIR-ARCH-825 | 0 | [11 empty] | IN
826 | WIR-ARCH-826 | 0 | [11 empty] | IN
827 | WIR-ARCH-827 | 0 | [11 empty] | IN
828 | WIR-ARCH-828 | 0 | [11 empty] | IN
829 | WIR-ARCH-829 | 0 | [11 empty] | IN
830 | WIR-ARCH-830 | 0 | [11 empty] | IN
831 | WIR-ARCH-831 | 0 | [11 empty] | IN
832 | WIR-ARCH-832 | 0 | [11 empty] | IN
833 | WIR-ARCH-833 | 0 | [11 empty] | IN
834 | WIR-ARCH-834 | 0 | [11 empty] | IN
835 | WIR-ARCH-835 | 0 | [11 empty] | IN
836 | WIR-ARCH-836 | 0 | [11 empty] | IN
837 | WIR-ARCH-837 | 0 | [11 empty] | IN
838 | WIR-ARCH-838 | 0 | [11 empty] | IN
839 | WIR-ARCH-839 | 0 | [11 empty] | IN
840 | WIR-ARCH-840 | 0 | [11 empty] | IN
841 | WIR-ARCH-841 | 0 | [11 empty] | IN
842 | WIR-ARCH-842 | 0 | [11 empty] | IN
843 | WIR-ARCH-843 | 0 | [11 empty] | IN
844 | WIR-ARCH-844 | 0 | [11 empty] | IN
845 | WIR-ARCH-845 | 0 | [11 empty] | IN
846 | WIR-ARCH-846 | 0 | [11 empty] | IN
847 | WIR-ARCH-847 | 0 | [11 empty] | IN
848 | WIR-ARCH-848 | 0 | [11 empty] | IN
849 | WIR-ARCH-849 | 0 | [11 empty] | IN
850 | WIR-ARCH-850 | 0 | [11 empty] | IN
851 | WIR-ARCH-851 | 0 | [11 empty] | IN
852 | WIR-ARCH-852 | 0 | [11 empty] | IN
853 | WIR-ARCH-853 | 0 | [11 empty] | IN
854 | WIR-ARCH-854 | 0 | [11 empty] | IN
855 | WIR-ARCH-855 | 0 | [11 empty] | IN
856 | WIR-ARCH-856 | 0 | [11 empty] | IN
857 | WIR-ARCH-857 | 0 | [11 empty] | IN
858 | WIR-ARCH-858 | 0 | [11 empty] | IN
859 | WIR-ARCH-859 | 0 | [11 empty] | IN
860 | WIR-ARCH-860 | 0 | [11 empty] | IN
861 | WIR-ARCH-861 | 0 | [11 empty] | IN
862 | WIR-ARCH-862 | 0 | [11 empty] | IN
863 | WIR-ARCH-863 | 0 | [11 empty] | IN
864 | WIR-ARCH-864 | 0 | [11 empty] | IN
865 | WIR-ARCH-865 | 0 | [11 empty] | IN
866 | WIR-ARCH-866 | 0 | [11 empty] | IN
867 | WIR-ARCH-867 | 0 | [11 empty] | IN
868 | WIR-ARCH-868 | 0 | [11 empty] | IN
869 | WIR-ARCH-869 | 0 | [11 empty] | IN
870 | WIR-ARCH-870 | 0 | [11 empty] | IN
871 | WIR-ARCH-871 | 0 | [11 empty] | IN
872 | WIR-ARCH-872 | 0 | [11 empty] | IN
873 | WIR-ARCH-873 | 0 | [11 empty] | IN
874 | WIR-ARCH-874 | 0 | [11 empty] | IN
875 | WIR-ARCH-875 | 0 | [11 empty] | IN
876 | WIR-ARCH-876 | 0 | [11 empty] | IN
877 | WIR-ARCH-877 | 0 | [11 empty] | IN
878 | WIR-ARCH-878 | 0 | [11 empty] | IN
879 | WIR-ARCH-879 | 0 | [11 empty] | IN
880 | WIR-ARCH-880 | 0 | [11 empty] | IN
881 | WIR-ARCH-881 | 0 | [11 empty] | IN
882 | WIR-ARCH-882 | 0 | [11 empty] | IN
883 | WIR-ARCH-883 | 0 | [11 empty] | IN
884 | WIR-ARCH-884 | 0 | [11 empty] | IN
885 | WIR-ARCH-885 | 0 | [11 empty] | IN
886 | WIR-ARCH-886 | 0 | [11 empty] | IN
887 | WIR-ARCH-887 | 0 | [11 empty] | IN
888 | WIR-ARCH-888 | 0 | [11 empty] | IN
889 | WIR-ARCH-889 | 0 | [11 empty] | IN
890 | WIR-ARCH-890 | 0 | [11 empty] | IN
891 | WIR-ARCH-891 | 0 | [11 empty] | IN
892 | WIR-ARCH-892 | 0 | [11 empty] | IN
893 | WIR-ARCH-893 | 0 | [11 empty] | IN
894 | WIR-ARCH-894 | 0 | [11 empty] | IN
895 | WIR-ARCH-895 | 0 | [11 empty] | IN
896 | WIR-ARCH-896 | 0 | [11 empty] | IN
897 | WIR-ARCH-897 | 0 | [11 empty] | IN
898 | WIR-ARCH-898 | 0 | [11 empty] | IN
899 | WIR-ARCH-899 | 0 | [11 empty] | IN
900 | WIR-ARCH-900 | 0 | [11 empty] | IN
901 | WIR-ARCH-901 | 0 | [11 empty] | IN
902 | WIR-ARCH-902 | 0 | [11 empty] | IN
903 | WIR-ARCH-903 | 0 | [11 empty] | IN
904 | WIR-ARCH-904 | 0 | [11 empty] | IN
905 | WIR-ARCH-905 | 0 | [11 empty] | IN
906 | WIR-ARCH-906 | 0 | [11 empty] | IN
907 | WIR-ARCH-907 | 0 | [11 empty] | IN
908 | WIR-ARCH-908 | 0 | [11 empty] | IN
909 | WIR-ARCH-909 | 0 | [11 empty] | IN
910 | WIR-ARCH-910 | 0 | [11 empty] | IN
911 | WIR-ARCH-911 | 0 | [11 empty] | IN
912 | WIR-ARCH-912 | 0 | [11 empty] | IN
913 | WIR-ARCH-913 | 0 | [11 empty] | IN
914 | WIR-ARCH-914 | 0 | [11 empty] | IN
915 | WIR-ARCH-915 | 0 | [11 empty] | IN
916 | WIR-ARCH-916 | 0 | [11 empty] | IN
917 | WIR-ARCH-917 | 0 | [11 empty] | IN
918 | WIR-ARCH-918 | 0 | [11 empty] | IN
919 | WIR-ARCH-919 | 0 | [11 empty] | IN
920 | WIR-ARCH-920 | 0 | [11 empty] | IN
921 | WIR-ARCH-921 | 0 | [11 empty] | IN
922 | WIR-ARCH-922 | 0 | [11 empty] | IN
Owner Logo
Consultant Logo

## ELEC
Inspection Request - ELEC | [9 empty] | A | Approved |  | Date: | 2026-04-02
[10 empty] | B | Approved with notes
[10 empty] | C | Reject & Resubmit
[10 empty] | CC | Not Resubmitted
[10 empty] | UR | Under Review
DOCUMENT REFERENCE NO |  |  | Element | Location | DESCRIPTION | Attachment |  | Outgoing to Consultant |  | Code Action | Status | Progress | Over Duration | scan | Attachement
No. | Reference | REV |  |  |  | Dwg | Report | Submission date | Received Date
1 | WIR-ELEC-001 | 0 | Electrical |  | Closing NCR 002 |  |  | 2025-12-21 | 2025-12-25 | B |  |  |  | IN
2 | WIR-ELEC-002 | 0 | Electrical |  | Closing NCR 003 |  |  | 2025-12-21 | 2025-12-27 | B |  |  |  | IN
3 | WIR-ELEC-003 | 0 | Electrical |  | Closing NCR 004 |  |  | 2025-12-23 | 2025-12-25 | B |  |  |  | IN
4 | WIR-ELEC-004 | 0 | Electrical |  | Inspection of sleeves for power cable and low current cable |  |  | 2026-01-13 | 2026-01-15 | C
5 | WIR-ELEC-005 | 0 | Electrical |  | Inspection of first fix for power lighting, low current(Wall celing |  |  | 2026-01-13 | 2026-01-15 | C
6 | WIR-ELEC-006 | 0 | Electrical |  | Inspection of wire pulling for lighting and power |  |  | 2026-01-13 | 2026-01-15 | C
7 | WIR-ELEC-007 | 0 | Electrical |  | Inspection of installation of lighting fixtures |  |  | 2026-01-13 | 2026-01-15 | C
8 | WIR-ELEC-008 | 0 | Electrical |  | Inspection of installation of lighting switches & power sockets |  |  | 2026-01-13 | 2026-01-15 | C
9 | WIR-ELEC-009 | 0 | Electrical |  | Inspction of fire alaram cable pulling |  |  | 2026-01-13 | 2026-01-15 | C
10 | WIR-ELEC-010 | 0 | Electrical |  | Inspection of installation of fire alaram devices |  |  | 2026-01-13 | 2026-01-15 | C
11 | WIR-ELEC-011 | 0 | Electrical |  | Inspection of fire alaram panel imnstallation |  |  | 2026-01-13 | 2026-01-13 | D
12 | WIR-ELEC-012 | 0 | Electrical |  | Inspection of fire alaram testing |  |  | 2026-01-13 | 2026-01-15 | C |  |  |  | IN | 3-1 | 17-0
13 | WIR-ELEC-013 | 0 | Electrical |  | Inspection of lighting fixtures testing |  |  | 2026-01-13 | 2026-01-15 | C |  |  |  | IN | 3-1 | 17-0 | 18-0
14 | WIR-ELEC-014 | 0 | Electrical |  | Inspection of distribution board testing |  |  | 2026-01-13 | 2026-01-15 | C |  |  |  | IN | 17-0 | 18-0
15 | WIR-ELEC-015 | 0 | Electrical |  | NCR CLOSING 019 |  |  | 2026-02-15 | 15/2/2026 | C |  |  |  | IN | 18-0
| WIR-ELEC-015 | 1 | Electrical |  | NCR CLOSING 019 |  |  |  |  | UR
16 | WIR-ELEC-016 | 0 | Electrical |  | NCR CLOSING 005 |  |  | 2026-02-15 | 2026-02-17 | C |  |  |  | IN | 17-0 | 18-0
| WIR-ELEC-016 | 1 | Electrical |  | NCR CLOSING 005 |  |  | 2026-02-15 | 2026-02-19 | C
17 | WIR-ELEC-017 | 0 | Electrical |  | NCR CLOSING 020 |  |  | 2026-02-15 | 15/2/2026 | C |  |  |  | IN | 4-1
18 | WIR-ELEC-018 | 0 | Electrical |  | NCR CLOSING 018 |  |  | 2026-02-15 | 2026-02-19 | B |  |  |  | IN
19 | WIR-ELEC-019 | 0 | Electrical |  | NCR CLOSING 001 |  |  | 2026-02-15 | 15/2/2026 | C |  |  |  | IN | 4-1
20 | WIR-ELEC-020 | 0 | Electrical |  | NCR CLOSING 013 |  |  | 2026-02-15 | 2026-02-19 | B |  |  |  | IN
21 | WIR-ELEC-021 | 0 | Electrical |  | NCR CLOSING 016 |  |  | 2026-02-15 | 2026-03-13 | B |  |  |  | IN | 18-0
22 | WIR-ELEC-022 | 0 | Electrical |  | NCR CLOSING 008 |  |  | 2026-02-15 | 2026-03-02 | B |  |  |  | IN | 17-0
23 | WIR-ELEC-023 | 0 | Electrical |  | NCR CLOSING 007 |  |  | 2026-02-15 | 2026-02-24 | B |  |  |  | IN
24 | WIR-ELEC-024 | 0 | Electrical |  | NCR CLOSING 017 |  |  | 2026-02-15 | 2026-02-24 | B |  |  |  | IN
25 | WIR-ELEC-025 | 0 | Electrical |  | NCR CLOSING 015 |  |  | 2026-02-15 | 2026-02-24 | B |  |  |  | IN
26 | WIR-ELEC-026 | 0 | Electrical |  | NCR CLOSING 021 |  |  | 31/3/2026 |  | UR |  |  |  | IN | 18-0
27 | WIR-ELEC-027 | 0 | Electrical |  | INSPACTION OF FIRST FIX OF LIGHTING,POWER SYSTEM INSTALLATION OF DB ENCLOSURE |  |  | 2026-02-17 | 2026-02-23 | B |  |  |  | IN | 17-0 | 18-0
28 | WIR-ELEC-028 | 0 | Electrical |  | INSTALTION OF ERTHING SYSTEM (CABLE POLLING ) ,ERTHING RODS ,PITS |  |  | 2026-02-17 |  | C |  |  |  | IN | 4-1
29 | WIR-ELEC-029 | 0 | Electrical |  | INSPACTION OF WIRE PULLING |  |  | 2026-02-17 | 2026-02-23 | B |  |  |  | IN | 4-1
30 | WIR-ELEC-030 | 0 | Electrical |  | INSTALTION OF ERTHING SYSTEM (CABLE POLLING ) ,ERTHING RODS ,PITS |  |  | 2026-02-17 | 2026-02-23 | C |  |  |  | IN | 4-1
31 | WIR-ELEC-031 | 0 | Electrical | Q-VF(01-02-03-04-05) Q-VS (1 - 2-3-4-5-6-7-8-0) | INSPACTION OF TERMINATION OF DB , INSTALLTION AND TERMINATION OF LIGHTING FITTINGS & WIRING ACCESSORIES |  |  | 2026-02-17 | 2026-02-23 | B |  |  |  | IN | 4-1
32 | WIR-ELEC-032 | 0 | Electrical | zone 4 q-fa01- q-r03 | INSPACTION OF WIRE PULLING |  |  | 2026-02-17 | 2026-02-23 | B |  |  |  | IN | 18-0
33 | WIR-ELEC-033 | 0 | Electrical |  | INSPACTION OF TERMINATION OF DB , INSTALLTION AND TERMINATION OF LIGHTING FITTINGS & WIRING ACCESSORIES |  |  | 2026-02-17 | 2026-02-23 | B |  |  |  | IN | 17-0
34 | WIR-ELEC-034 | 0 | Electrical | zone 4 q-fa01- q-r03 | INSTALTION OF ERTHING SYSTEM (CABLE POLLING ) ,ERTHING RODS ,PITS |  |  | 2026-02-17 | 2026-02-23 | B |  |  |  | IN | 3-1 | 17-0
35 | WIR-ELEC-035 | 0 | Electrical | Q+GA(01-02-03-04-05-06-07-08-09-10-11) | INSPACTION OF FIRST FIX OF LIGHTING,POWER SYSTEM INSTALLATION OF DB ENCLOSURE |  |  |  |  | UR
36 | WIR-ELEC-036 | 0 | Electrical | Q+GA(01-02-03-04-05-06-07-08-09-10-11) | INSPACTION OF WIRE PULLING |  |  |  |  | UR
37 | WIR-ELEC-037 | 0 | Electrical | Q+GA(01-02-03-04-05-06-07-08-09-10-11) | INSPACTION OF TERMINATION OF DB , INSTALLTION AND TERMINATION OF LIGHTING FITTINGS & WIRING ACCESSORIES |  |  |  |  | UR
38 | WIR-ELEC-038 | 0 | Electrical | Q+GA(01-02-03-04-05-06-07-08-09-10-11) | INSTALTION OF ERTHING SYSTEM (CABLE POLLING ) ,ERTHING RODS ,PITS |  |  |  |  | UR
39 | WIR-ELEC-39 | 0 | Electrical |  | INSPACTION OF FIRST FIX OF LIGHTING,POWER SYSTEM INSTALLATION OF DB ENCLOSURE |  |  | 2026-03-10 | 2026-03-10 | B |  |  |  | IN | 3-1 | 17-0 | 18-0
40 | WIR-ELEC-40 | 0 | Electrical | Q-VF(06-07-08-09-10) | INSPACTION OF WIRE PULLING |  |  | 2026-03-10 | 2026-03-10 | B |  |  |  | IN | 17-0 | 18-0
41 | WIR-ELEC-41 | 0 | Electrical | Q-VF(06-07-08-09-10) | INSPACTION OF TERMINATION OF DB , INSTALLTION AND TERMINATION OF LIGHTING FITTINGS & WIRING ACCESSORIES |  |  | 2026-03-10 | 2026-03-10 | B |  |  |  | IN | 18-0
42 | WIR-ELEC-42 | 0 | Electrical | Q-VF(06-07-08-09-10) | INSTALTION OF ERTHING SYSTEM (CABLE POLLING ) ,ERTHING RODS ,PITS |  |  | 2026-03-10 | 2026-03-10 | C |  |  |  | IN | 17-0 | 18-0
43 | WIR-ELEC-43 | 0 | Electrical | Q-VS(10-11-12-13-14-15-16-17) | INSPACTION OF FIRST FIX OF LIGHTING,POWER SYSTEM INSTALLATION OF DB ENCLOSURE |  |  | 2026-03-10 | 2026-03-10 | B |  |  |  | IN | 4-1
44 | WIR-ELEC-44 | 0 | Electrical | Q-VS(10-11-12-13-14-15-16-17) | INSPACTION OF WIRE PULLING |  |  | 2026-03-10 | 2026-03-10 | B |  |  |  | IN | 4-1
45 | WIR-ELEC-45 | 0 | Electrical | Q-VS(10-11-12-13-14-15-16-17) | INSPACTION OF TERMINATION OF DB , INSTALLTION AND TERMINATION OF LIGHTING FITTINGS & WIRING ACCESSORIES |  |  | 2026-03-10 | 2026-03-10 | B |  |  |  | IN | 4-1
46 | WIR-ELEC-46 | 0 | Electrical | Q-VS(10-11-12-13-14-15-16-17) | INSTALTION OF ERTHING SYSTEM (CABLE POLLING ) ,ERTHING RODS ,PITS |  |  | 2026-03-10 | 2026-03-10 | C |  |  |  | IN | 4-1
47 | WIR-ELEC-47 | 0 | Electrical | Q-FA02 | INSPACTION OF FIRST FIX OF LIGHTING,POWER SYSTEM INSTALLATION OF DB ENCLOSURE |  |  | 2026-03-10 | 2026-03-10 | B |  |  |  | IN | 18-0
48 | WIR-ELEC-48 | 0 | Electrical | Q-FA02 | INSPACTION OF WIRE PULLING |  |  | 2026-03-10 | 2026-03-10 | B |  |  |  | IN | 17-0
49 | WIR-ELEC-49 | 0 | Electrical | Q-FA02 | INSPACTION OF TERMINATION OF DB , INSTALLTION AND TERMINATION OF LIGHTING FITTINGS & WIRING ACCESSORIES |  |  | 2026-03-10 | 2026-03-10 | B |  |  |  | IN | 3-1 | 17-0
50 | WIR-ELEC-50 | 0 | Electrical | Q-FA02 | INSTALTION OF ERTHING SYSTEM (CABLE POLLING ) ,ERTHING RODS ,PITS |  |  | 2026-03-10 | 2026-03-10 | C |  |  |  | IN | 3-1 | 17-0 | 18-0
51 | WIR-ELEC-51 | 0 | Electrical | Q-R04 | INSPACTION OF FIRST FIX OF LIGHTING,POWER SYSTEM INSTALLATION OF DB ENCLOSURE |  |  | 2026-03-10 | 2026-03-10 | B |  |  |  | IN | 17-0 | 18-0
52 | WIR-ELEC-52 | 0 | Electrical | Q-R04 | INSPACTION OF WIRE PULLING |  |  | 2026-03-10 | 2026-03-10 | B |  |  |  | IN | 18-0
53 | WIR-ELEC-53 | 0 | Electrical | Q-R04 | INSPACTION OF TERMINATION OF DB , INSTALLTION AND TERMINATION OF LIGHTING FITTINGS & WIRING ACCESSORIES |  |  | 2026-03-10 | 2026-03-10 | B |  |  |  | IN | 17-0 | 18-0
54 | WIR-ELEC-54 | 0 | Electrical | Q-R04 | INSTALTION OF ERTHING SYSTEM (CABLE POLLING ) ,ERTHING RODS ,PITS |  |  | 2026-03-10 | 2026-03-10 | B |  |  |  | IN | 4-1
55 | WIR-ELEC-55 | 0 | Electrical | Q-WC02 | INSPACTION OF FIRST FIX OF LIGHTING,POWER SYSTEM INSTALLATION OF DB ENCLOSURE |  |  | 2026-03-16 | 2026-03-16 | B |  |  |  | IN | 4-1
56 | WIR-ELEC-56 | 0 | Electrical | Q-WC02 | INSPACTION OF WIRE PULLING |  |  | 2026-03-16 | 2026-03-16 | B |  |  |  | IN | 4-1
57 | WIR-ELEC-57 | 0 | Electrical | Q-WC02 | INSPACTION OF TERMINATION OF DB , INSTALLTION AND TERMINATION OF LIGHTING FITTINGS & WIRING ACCESSORIES |  |  | 2026-03-16 | 2026-03-16 | B |  |  |  | IN | 4-1
58 | WIR-ELEC-58 | 0 | Electrical | Q-WC02 | INSTALTION OF ERTHING SYSTEM (CABLE POLLING ) ,ERTHING RODS ,PITS |  |  | 2026-03-16 | 2026-03-16 | C |  |  |  | IN | 18-0
59 | WIR-ELEC-59 | 0 | Electrical | Q-WC01 | INSPACTION OF FIRST FIX OF LIGHTING,POWER SYSTEM INSTALLATION OF DB ENCLOSURE |  |  | 2026-03-16 | 2026-03-16 | B |  |  |  | IN | 17-0
60 | WIR-ELEC-60 | 0 | Electrical | Q-WC01 | INSPACTION OF WIRE PULLING |  |  | 2026-03-16 | 2026-03-16 | B |  |  |  | IN | 3-1 | 17-0
61 | WIR-ELEC-61 | 0 | Electrical | Q-WC01 | INSPACTION OF TERMINATION OF DB , INSTALLTION AND TERMINATION OF LIGHTING FITTINGS & WIRING ACCESSORIES |  |  | 2026-03-16 | 2026-03-16 | B |  |  |  | IN | 3-1 | 17-0 | 18-0
62 | WIR-ELEC-62 | 0 | Electrical | Q-WC01 | INSTALTION OF ERTHING SYSTEM (CABLE POLLING ) ,ERTHING RODS ,PITS |  |  | 2026-03-16 | 2026-03-16 | C |  |  |  | IN | 17-0 | 18-0
63 | WIR-ELEC-63 | 0 | Electrical |  | CLOSING NCR-006 |  |  | 2026-03-16 |  | UR |  |  |  | #REF! | 18-0
64 | WIR-ELEC-64 | 0 | Electrical |  | CLOSING NCR-020 |  |  | 16/3/2026 | 2026-03-16 | C |  |  |  | IN | 17-0 | 18-0
| WIR-ELEC-64 | 1 | Electrical |  | CLOSING NCR-020 |  |  | 2026-03-31 |  | UR
65 | WIR-ELEC-65 | 0 | Electrical |  | CLOSING NCR-010 |  |  | 18/3/2026 | 26/3/2026 | B |  |  |  | IN | 4-1
66 | WIR-ELEC-66 | 0 | Electrical |  | CLOSING NCR-011 |  |  | 18/3/2026 | 26/3/2026 | B |  |  |  | IN | 4-1
67 | WIR-ELEC-67 | 0 | Electrical |  | CLOSING NCR-012 |  |  | 18/3/2026 | 26/3/2026 | B |  |  |  | IN | 4-1
68 | WIR-ELEC-68 | 0 | Electrical |  | CLOSING NCR-012 |  |  | 18/3/2026 | 46107 | B |  |  |  | IN | 4-1
69 | WIR-ELEC-69 | 0 | Electrical |  | CLOSING NCR-014 |  |  | 18/3/2026 | 46107 | B |  |  |  | IN | 18-0
70 | WIR-ELEC-70 | 0 | Electrical | CAMEL STATION | This request is to review and comment on the following INSPECTION OF INSTALLATION OF 1 FIX OF FIRE ALARM SYSTEM . |  |  | 25/3/2026 | 46109 | B |  |  |  | IN | 17-0
71 | WIR-ELEC-71 | 0 | Electrical | CAMEL STATION | This request is to review and comment on the following INSPECTION OF WIRE PULLING OF LIGHTING AND POWER SYSTEM . |  |  | 25/3/2026 | 46109 | B |  |  |  | IN | 3-1 | 17-0
72 | WIR-ELEC-72 | 0 | Electrical | CAMEL STATION | This request is to review and comment on the following INSPECTION OF INSTALLATION OF 2 FIX OF FIRE ALARM SYSTEM . |  |  | 25/3/2026 | 46109 | B
73 | WIR-ELEC-73 | 0 | Electrical | CAMEL STATION | This request is to review and comment on the following INSPECTION OF INSTALLATION OF 3 FIX OF FIRE ALARM SYSTEM . |  |  | 25/3/2026 | 46109 | B
74 | WIR-ELEC-74 | 0 | Electrical | CAMEL STATION | This request is to review and comment on the following INSPECTION OF TERMINATION OF DB , INSTALLTION AND TERMINATION OF LIGHTING FITTINGS & WIRING ACCESSORIES |  |  | 25/3/2026 | 46109 | B
75 | WIR-ELEC-75 | 0 | Electrical | CAMEL STATION | This request is to review and comment on the following INSTALATION OF ERTHING SYSTEM (CABLE POLLING ) ,ERTHING RODS ,PITS AND LIGHTNING SYSTEM . |  |  | 25/3/2026 | 46111 | B
76 | WIR-ELEC-76 | 0 | Electrical | CAMEL STATION | This request is to review and comment on the following INSPECTION OF INSTALLATION OF FIRST FIX OF LIGHTING,POWER SYSTEM INSTALLATION OF DB ENCLOSURE . |  |  | 25/3/2026 |  | UR
77 | WIR-ELEC-77 | 0 | Electrical | Q-K05/ Q-K06 / Q-K18/ Q-K19 | This request is to review and comment on the following INSPECTION OF FIRST FIX OF LIGHTING,POWER SYSTEM INSTALLATION OF DB ENCLOSURE |  |  | 25/3/2026 | 2026-03-28 | B
78 | WIR-ELEC-78 | 0 | Electrical | Q-K05/ Q-K06 / Q-K18/ Q-K19 | This request is to review and comment on the following INSPECTION OF INSTALLATION OF 1 FIX OF LOW CURRENT SYSTEM AND FIRE ALARM SYSTEM . |  |  | 25/3/2026 | 2026-03-28 | B
79 | WIR-ELEC-79 | 0 | Electrical | Q-K05/ Q-K06 / Q-K18/ Q-K19 | This request is to review and comment on the following INSPECTION OF INSTALLATION OF WIRE PULLING OF LIGHTING AND POWER SYSTEM . |  |  | 25/3/2026 | 2026-03-28 | B
80 | WIR-ELEC-80 | 0 | Electrical | Q-K05/ Q-K06 / Q-K18/ Q-K19 | This request is to review and comment on the following INSPECTION OF INSTALLATION 2 FIX OF FIRE ALARM SYSTEM . |  |  | 25/3/2026 | 2026-03-28 | B
81 | WIR-ELEC-81 | 0 | Electrical | Q-K05/ Q-K06 / Q-K18/ Q-K19 | This request is to review and comment on the following INSPECTION OFINSTALLATION OF 3 FIX OF FIRE ALARM SYSTEM . |  |  | 25/3/2026 | 2026-03-30 | B
82 | WIR-ELEC-82 | 0 | Electrical | Q-K05/ Q-K06 / Q-K18/ Q-K19 | This request is to review and comment on the following INSPECTION OF TERMINATION OF DB , INSTALLTION AND TERMINATION OF LIGHTING FITTINGS & WIRING ACCESSORIES |  |  | 25/3/2026 | 2026-03-28 | B
83 | WIR-ELEC-83 | 0 | Electrical | Q-K05/ Q-K06 / Q-K18/ Q-K19 | This request is to review and comment on the following INSPECTION OF INSTALLATION OF ERTHING SYSTEM (CABLE POLLING ) ,ERTHING RODS ,PITS AND LIGHTNING SYSTEM . |  |  | 25/3/2026 |  | UR
84 | WIR-ELEC-84 | 0 | Electrical | Q-K7 /Q-K20 | Inspection of installation of 1 fix of low current system and fire alarm system |  |  | 25/3/2026 | 2026-03-28 | B
85 | WIR-ELEC-85 | 0 | Electrical | Q-K7 /Q-K20 | Inspection of installation 2 fix of fire alaram system |  |  | 25/3/2026 | 2026-03-28 | B
86 | WIR-ELEC-86 | 0 | Electrical | Q-K7 /Q-K20 | Inspection of installation of 3 fix of fire alarm system |  |  | 25/3/2026 | 2026-03-30 | B
87 | WIR-ELEC-87 | 0 | Electrical | Q-K7 /Q-K20 | This request is to review and comment on the following INSTELTION OF ERTHING SYSTEM (CABLE POLLING ) ,ERTHING RODS ,PITS AND Lightning System . |  |  | 25/3/2026 |  | UR
88 | WIR-ELEC-88 | 0 | Electrical | Q-K7 /Q-K20 | Inspection of installation of first fix of lighting power system installation of DB Enclouser |  |  | 25/3/2026 | 2026-03-28 | B
89 | WIR-ELEC-89 | 0 | Electrical | Q-K7 /Q-K20 | Inspection of installation wore pulling of lighting and power system |  |  | 25/3/2026 | 2026-03-28 | B
90 | WIR-ELEC-90 | 0 | Electrical | Q-K7 /Q-K20 | Inspection of terminatation of DB, installation and termination lighting fittings & wiring accessories |  |  | 25/3/2026 | 2026-03-28 | B
91 | WIR-ELEC-91 | 0 | Electrical | Q-K24 /Q-K11 | Inspection of installation of 1 fix of low current system and fire alarm system |  |  | 25/3/2026 | 2026-03-28 | B
92 | WIR-ELEC-92 | 0 | Electrical | Q-K24 /Q-K11 | Inspection of installation 2 fix of fire alaram system |  |  | 25/3/2026 | 2026-03-28 | B
93 | WIR-ELEC-93 | 0 | Electrical | Q-K24 /Q-K11 | Inspection of installation of 3 fix of fire alarm system |  |  | 25/3/2026 | 2026-03-30 | B
94 | WIR-ELEC-94 | 0 | Electrical | Q-K24 /Q-K11 | Inspection of installation first fix of lighting power sytem installation of DB enclouser |  |  | 25/3/2026 | 2026-03-28 | B
95 | WIR-ELEC-95 | 0 | Electrical | Q-K24 /Q-K11 | Inspection of wire pulling for lighting and power system |  |  | 25/3/2026 | 2026-03-28 | B
96 | WIR-ELEC-96 | 0 | Electrical | Q-K24 /Q-K11 | Inspection of terminatation of DB, installation and termination lighting fittings & wiring accessories |  |  | 25/3/2026 | 2026-03-28 | B
97 | WIR-ELEC-97 | 0 | Electrical | Q-K24 /Q-K11 | This request is to review and comment on the following INSTALLTION OF ERTHING SYSTEM (CABLE POLLING ) ,ERTHING RODS ,PITS AND Lightning System . |  |  | 25/3/2026 |  | UR
98 | WIR-ELEC-98 | 0 | Electrical | Q-K01/Q-K02/Q-K03/Q-K04/Q-K08/ Q-K09/ Q-K10/Q-K12/Q-K17/Q-K30/Q-K21/ Q-K22/Q-K23/Q-K25 | This request is to review and comment on the following INSPECTION OF INSTALLATION OF 1FIX OF lOW CURRENT AND FIRE ALARM SYETEM . |  |  | 25/3/2026 | 2026-03-28 | B
99 | WIR-ELEC-99 | 0 | Electrical | Q-K01/Q-K02/Q-K03/Q-K04/Q-K08/ Q-K09/ Q-K10/Q-K12/Q-K17/Q-K30/Q-K21/ Q-K22/Q-K23/Q-K25 | This request is to review and comment on the following INSPECTION OF INSTALLATION OF 2FIX OF FIRE ALARM SYETEM . |  |  | 25/3/2026 | 2026-03-28 | B
100 | WIR-ELEC-100 | 0 | Electrical | Q-K01/Q-K02/Q-K03/Q-K04/Q-K08/ Q-K09/ Q-K10/Q-K12/Q-K17/Q-K30/Q-K21/ Q-K22/Q-K23/Q-K25 | This request is to review and comment on the following INSPECTION OF INSTALLATION OF 3FIX OF FIRE ALARM SYETEM . |  |  | 25/3/2026 | 2026-03-30 | B
101 | WIR-ELEC-101 | 0 | Electrical | Q-K01/Q-K02/Q-K03/Q-K04/Q-K08/ Q-K09/ Q-K10/Q-K12/Q-K17/Q-K30/Q-K21/ Q-K22/Q-K23/Q-K25 | This request is to review and comment on the following INSPECTION OF FIRST FIX OF LIGHTING,POWER SYSTEM INSTALLATION OF DB ENCLOSURE |  |  | 25/3/2026 | 2026-03-28 | B
102 | WIR-ELEC-102 | 0 | Electrical | Q-K01/Q-K02/Q-K03/Q-K04/Q-K08/ Q-K09/ Q-K10/Q-K12/Q-K17/Q-K30/Q-K21/ Q-K22/Q-K23/Q-K25 | This request is to review and comment on the following INSPECTION OF WIRE PULLING of Lighting and Power system . |  |  | 25/3/2026 | 2026-03-28 | B
103 | WIR-ELEC-103 | 0 | Electrical | Q-K01/Q-K02/Q-K03/Q-K04/Q-K08/ Q-K09/ Q-K10/Q-K12/Q-K17/Q-K30/Q-K21/ Q-K22/Q-K23/Q-K25 | This request is to review and comment on the following INSPECTION OF TERMINATION OF DB , INSTALLTION AND TERMINATION OF LIGHTING FITTINGS & WIRING ACCESSORIES |  |  | 25/3/2026 | 2026-03-28 | B
104 | WIR-ELEC-104 | 0 | Electrical | Q-K01/Q-K02/Q-K03/Q-K04/Q-K08/ Q-K09/ Q-K10/Q-K12/Q-K17/Q-K30/Q-K21/ Q-K22/Q-K23/Q-K25 | This request is to review and comment on the following INSTALLTION OF ERTHING SYSTEM (CABLE POLLING ) ,ERTHING RODS ,PITS AND LIGHTNING SYSTEM . |  |  | 25/3/2026 |  | UR
105 | WIR-ELEC-105 | 0 | Electrical | Gathering R05 | Inspection of installation of 1 fix of low current system and fire alarm system |  |  | 25/3/2026 | 2026-03-28 | B
106 | WIR-ELEC-106 | 0 | Electrical | Gathering R05 | Inspection of installation first fix of lighting power sytem installation of DB enclouser |  |  | 25/3/2026 | 2026-03-28 | B
107 | WIR-ELEC-107 | 0 | Electrical | Gathering R05 | Inspection of installation 2 fix of fire alaram system |  |  | 25/3/2026 | 2026-03-28 | B
108 | WIR-ELEC-108 | 0 | Electrical | Gathering R05 | Inspection of wire pulling of lighting and power system |  |  | 25/3/2026 | 2026-03-28 | B
109 | WIR-ELEC-109 | 0 | Electrical | Gathering R05 | Inspection of terminatation of DB, installation and termination lighting fittings & wiring accessories |  |  | 25/3/2026 | 2026-03-28 | B
110 | WIR-ELEC-110 | 0 | Electrical | Gathering R05 | INSTALLTION OF ERTHING SYSTEM (CABLE POLLING ) ,ERTHING RODS ,PITS AND LIGHTNING SYSTEM . |  |  | 25/3/2026 |  | UR
111 | WIR-ELEC-111 | 0 | Electrical | Anam E01 | Inspection of installation first fix of lighting power sytem installation of DB enclouser |  |  | 29/3/2026 | 2026-03-30 | B
112 | WIR-ELEC-112 | 0 | Electrical | Anam E01 | Inspection of installation of 1 Fix of Fire alaram system |  |  | 29/3/2026 | 2026-03-30 | B
113 | WIR-ELEC-113 | 0 | Electrical | Anam E01 | Inspection of wire pulling of lighting and power system |  |  | 29/3/2026 | 2026-03-30 | B
114 | WIR-ELEC-114 | 0 | Electrical | Anam E01 | Inspection of installation 2 fix of fire alaram system |  |  | 29/3/2026 | 2026-03-30 | B
115 | WIR-ELEC-115 | 0 | Electrical | Anam E01 | Inspection of terminatation of DB, installation and termination lighting fittings & wiring accessories |  |  | 29/3/2026 | 2026-03-30 | B
116 | WIR-ELEC-116 | 0 | Electrical | Anam E01 | Inspection of installation 3 fix of fire alaram system |  |  | 29/3/2026 | 2026-03-30 | B
117 | WIR-ELEC-117 | 0 | Electrical | Anam E01 | This request is to review and comment on the following INSPECTION OF INSTALLATION OF FIRST FIX OF LIGHTING,POWER SYSTEM INSTALLATION OF DB ENCLOSURE . |  |  | 29/3/2026 |  | UR
118 | WIR-ELEC-118 | 0 | Electrical | CENTRAL MOSQUE | Inspection of installation first fix of lighting power sytem installation of DB enclouser |  |  | 29/3/2026 | 2026-03-30 | B
119 | WIR-ELEC-119 | 0 | Electrical | CENTRAL MOSQUE | Inspection of installation of 1 Fix of Fire alaram system |  |  | 29/3/2026 | 2026-03-30 | B
120 | WIR-ELEC-120 | 0 | Electrical | CENTRAL MOSQUE | Inspection of installation of 2 Fix of Fire alaram system |  |  | 29/3/2026 | 2026-03-30 | B
121 | WIR-ELEC-121 | 0 | Electrical | CENTRAL MOSQUE | Inspection of wire pulling |  |  | 29/3/2026 | 2026-03-30 | B
122 | WIR-ELEC-122 | 0 | Electrical | CENTRAL MOSQUE | Inspection of 3 Fix of Fire alaram system |  |  | 29/3/2026 | 2026-03-30 | B
123 | WIR-ELEC-123 | 0 | Electrical | CENTRAL MOSQUE | Inspection of terminatation of DB, installation and termination lighting fittings & wiring accessories |  |  | 29/3/2026 | 2026-03-30 | B
124 | WIR-ELEC-124 | 0 | Electrical | CENTRAL MOSQUE | This request is to review and comment on the following INSPECTION OF INSTALLATION OF FIRST FIX OF LIGHTING,POWER SYSTEM INSTALLATION OF DB ENCLOSURE . |  |  | 29/3/2026 |  | UR
125 | WIR-ELEC-125 | 0 | Electrical | CENTRAL MOSQUE | This request is to review and comment on the following INSPECTION OF FIRST FIX OF LIGHTING,POWER SYSTEM INSTALLATION OF DB ENCLOSURE |  |  | 29/3/2026 |  | UR
126 | WIR-ELEC-126 | 0 | Electrical | CONTROL ROOM | This request is to review and comment on the following INSTALLATION OF 1 FIX OF LOW CURRENT AND FIRE ALARM SYSTEM . |  |  | 29/3/2026 |  | UR
127 | WIR-ELEC-127 | 0 | Electrical | CONTROL ROOM | This request is to review and comment on the following INSTALLATION OF 2FIX OF FIRE ALARM SYSTEM . |  |  | 29/3/2026 |  | UR
128 | WIR-ELEC-128 | 0 | Electrical | CONTROL ROOM | This request is to review and comment on the following INSPECTION OF WIRE PULLING |  |  | 29/3/2026 |  | UR
129 | WIR-ELEC-129 | 0 | Electrical | CONTROL ROOM | This request is to review and comment on the following INSTALLATION OF 3FIX OF FIRE ALARM SYSTEM . |  |  | 29/3/2026 |  | UR
130 | WIR-ELEC-130 | 0 | Electrical | CONTROL ROOM | This request is to review and comment on the following INSPECTION OF TERMINATION OF DB , INSTALLTION AND TERMINATION OF LIGHTING FITTINGS & WIRING ACCESSORIES |  |  | 29/3/2026 |  | UR
131 | WIR-ELEC-131 | 0 | Electrical | CONTROL ROOM | This request is to review and comment on the following INSTALATION OF ERTHING SYSTEM (CABLE POLLING ) ,ERTHING RODS ,PITS AND LIGHTNING SYSTEM . |  |  | 29/3/2026 |  | UR
132 | WIR-ELEC-132 | 0 | Electrical | LANDSCAPE ZONE 2 | This request is to review and comment on the following INSPECTION FOR CABLE PULLING FOR FIRE ALARM SYSTEM . |  |  | 29/3/2026 |  | UR
133 | WIR-ELEC-133 | 0 | Electrical | LANDSCAPE ZONE 2 | This request is to review and comment on the following INSPECTION FOR EXTENTION CONDUIT LAYING FOR FIRE ALARM SYSTEM . |  |  | 29/3/2026 |  | UR
134 | WIR-ELEC-134 | 0 | Electrical | LANDSCAPE ZONE 3 | This request is to review and comment on the following INSPECTION FOR CABLE PULLING FOR FIRE ALARM SYSTEM . |  |  | 29/3/2026 |  | UR
135 | WIR-ELEC-135 | 0 | Electrical | LANDSCAPE ZONE 3 | This request is to review and comment on the following INSPECTION FOR EXTENTION CONDUIT LAYING FOR FIRE ALARM SYSTEM . |  |  | 29/3/2026 |  | UR
136 | WIR-ELEC-136 | 0 | Electrical | LANDSCAPE ZONE 4 | This request is to review and comment on the following INSPECTION FOR CABLE PULLING FOR FIRE ALARM SYSTEM . |  |  | 29/3/2026 |  | UR
137 | WIR-ELEC-137 | 0 | Electrical | LANDSCAPE ZONE 4 | This request is to review and comment on the following INSPECTION FOR EXTENTION CONDUIT LAYING FOR FIRE ALARM SYSTEM . |  |  | 29/3/2026 |  | UR
138 | WIR-ELEC-138 | 0 | Electrical | LANDSCAPE ZONE 2 | This request is to review and comment on the following INSPECTION FOR CABLE PULLING FOR SOUND SYSTEM . |  |  | 29/3/2026 |  | UR
139 | WIR-ELEC-139 | 0 | Electrical | LANDSCAPE ZONE 2 | This request is to review and comment on the following INSPECTION FOR EXTENTION CONDUIT LAYING FOR SOUND SYSTEM . |  |  | 29/3/2026 |  | UR
140 | WIR-ELEC-140 | 0 | Electrical | LANDSCAPE ZONE 2 | This request is to review and comment on the following INSPECTION FOR INSALLATION OF SPEAKERS . |  |  | 29/3/2026 |  | UR
141 | WIR-ELEC-141 | 0 | Electrical | LANDSCAPE ZONE 3 | This request is to review and comment on the following INSPECTION FOR CABLE PULLING FOR SOUND SYSTEM . |  |  | 29/3/2026 |  | UR
142 | WIR-ELEC-142 | 0 | Electrical | LANDSCAPE ZONE 3 | This request is to review and comment on the following INSPECTION FOR EXTENTION CONDUIT LAYING FOR SOUND SYSTEM . |  |  | 29/3/2026 |  | UR
143 | WIR-ELEC-143 | 0 | Electrical | LANDSCAPE ZONE 3 | This request is to review and comment on the following INSPECTION FOR INSALLATION OF SPEAKERS . |  |  | 29/3/2026 |  | UR
144 | WIR-ELEC-144 | 0 | Electrical | LANDSCAPE ZONE 4 | This request is to review and comment on the following INSPECTION FOR CABLE PULLLING FOR SOUND SYSTEM . |  |  | 29/3/2026 |  | UR
145 | WIR-ELEC-145 | 0 | Electrical | LANDSCAPE ZONE 4 | This request is to review and comment on the following INSPECTION FOR EXTENTION CONDUIT LAYING FOR SOUND SYSTEM . |  |  | 29/3/2026 |  | UR
146 | WIR-ELEC-146 | 0 | Electrical | LANDSCAPE ZONE 4 | This request is to review and comment on the following INSPECTION FOR INSALLATION OF SPEAKERS . |  |  | 29/3/2026 |  | UR
147 | WIR-ELEC-147 | 0 | Electrical | LANDSCAPE ZONE 2 | This request is to review and comment on the following INSPECTION FOR CABLE PULLING FOR EXTERNAL LIGHTING SYSTEM . |  |  | 29/3/2026 |  | UR
148 | WIR-ELEC-148 | 0 | Electrical | LANDSCAPE ZONE 2 | This request is to review and comment on the following INSPECTION FOR EXTENTION CONDUIT LAYING FOR EXTERNAL LIGHTING SYSTEM . |  |  | 29/3/2026 |  | UR
149 | WIR-ELEC-149 | 0 | Electrical | LANDSCAPE ZONE 2 | This request is to review and comment on the following INSPECTION FOR INSTALLATION OF DB PANNEL FOR EXTERNAL LIGHTING SYSTEM . |  |  | 29/3/2026 |  | UR
150 | WIR-ELEC-150 | 0 | Electrical | LANDSCAPE ZONE 2 | This request is to review and comment on the following INSPECTION FOR Lighting Fixtures INSALLATION FOR EXTERNAL LIGHTING SYSTEM . |  |  | 29/3/2026 |  | UR
151 | WIR-ELEC-151 | 0 | Electrical | LANDSCAPE ZONE 3 | This request is to review and comment on the following INSPECTION FOR CABLE PULLING FOR EXTERNAL LIGHTING SYSTEM . |  |  | 29/3/2026 |  | UR
152 | WIR-ELEC-152 | 0 | Electrical | LANDSCAPE ZONE 3 | This request is to review and comment on the following INSPECTION FOR EXTENTION CONDUIT LAYING FOR EXTERNAL LIGHTING SYSTEM . |  |  | 29/3/2026 |  | UR
153 | WIR-ELEC-153 | 0 | Electrical | LANDSCAPE ZONE 3 | This request is to review and comment on the following INSPECTION FOR INSTALLATION OF DB PANNEL FOR EXTERNAL LIGHTING SYSTEM . |  |  | 29/3/2026 |  | UR
154 | WIR-ELEC-154 | 0 | Electrical | LANDSCAPE ZONE 3 | This request is to review and comment on the following INSPECTION FOR Lighting Fixtures INSALLATION FOR EXTERNAL LIGHTING SYSTEM . |  |  | 29/3/2026 |  | UR
155 | WIR-ELEC-155 | 0 | Electrical | LANDSCAPE ZONE 4 | This request is to review and comment on the following INSPECTION FOR CABLE PULLING FOR EXTERNAL LIGHTING SYSTEM . |  |  | 29/3/2026 |  | UR
156 | WIR-ELEC-156 | 0 | Electrical | LANDSCAPE ZONE 4 | This request is to review and comment on the following INSPECTION FOR EXTENTION CONDUIT LAYING FOR EXTERNAL LIGHTING SYSTEM . |  |  | 29/3/2026 |  | UR
157 | WIR-ELEC-157 | 0 | Electrical | LANDSCAPE ZONE 4 | This request is to review and comment on the following INSPECTION FOR INSTALLATION OF DB PANNEL FOR EXTERNAL LIGHTING SYSTEM . |  |  | 29/3/2026 |  | UR
158 | WIR-ELEC-158 | 0 | Electrical | LANDSCAPE ZONE 4 | This request is to review and comment on the following INSPECTION FOR Lighting Fixtures INSALLATION FOR EXTERNAL LIGHTING SYSTEM . |  |  | 29/3/2026 |  | UR
159 | WIR-ELEC-159 | 0 | Electrical | Commercial C18 LIBRARY | This request is to review and comment on the following INSPECTION OF INSTALLATION OF 1 FIX OF LOW CURRENT AND FIRE ALARM SYSTEM . |  |  | 29/3/2026 |  | UR
160 | WIR-ELEC-160 | 0 | Electrical | Commercial C18 LIBRARY | This request is to review and comment on the following INSPECTION OF WIRE PULLING OF LIGHTING AND POWER SYSTEM . |  |  | 29/3/2026 |  | UR
161 | WIR-ELEC-161 | 0 | Electrical | Commercial C18 LIBRARY | This request is to review and comment on the following INSPECTION OF INSTALLATION OF 2 FIX OF FIRE ALARM SYSTEM . |  |  | 29/3/2026 |  | UR
162 | WIR-ELEC-162 | 0 | Electrical | Commercial C18 LIBRARY | This request is to review and comment on the following INSPECTION OF INSTALLATION OF 3 FIX OF FIRE ALARM SYSTEM . |  |  | 29/3/2026 |  | UR
163 | WIR-ELEC-163 | 0 | Electrical | Commercial C18 LIBRARY | This request is to review and comment on the following INSPECTION OF TERMINATION OF DB , INSTALLTION AND TERMINATION OF LIGHTING FITTINGS & WIRING ACCESSORIES |  |  | 29/3/2026 |  | UR
164 | WIR-ELEC-164 | 0 | Electrical | Commercial C18 LIBRARY | This request is to review and comment on the following INSTALATION OF ERTHING SYSTEM (CABLE POLLING ) ,ERTHING RODS ,PITS AND LIGHTNING SYSTEM . |  |  | 29/3/2026 |  | UR
165 | WIR-ELEC-165 | 0 | Electrical | Commercial C18 LIBRARY | This request is to review and comment on the following INSPECTION OF INSTALLATION OF FIRST FIX OF LIGHTING,POWER SYSTEM INSTALLATION OF DB ENCLOSURE . |  |  | 29/3/2026 |  | UR
166 | WIR-ELEC-166 | 0 | Electrical | VIP Lounge R03 | This request is to review and comment on the following INSPECTION OF INSTALLATION OF 1 FIX OF LOW CURRENT AND FIRE ALARM SYSTEM . |  |  | 29/3/2026 |  | UR
167 | WIR-ELEC-167 | 0 | Electrical | VIP Lounge R03 | This request is to review and comment on the following INSPECTION OF WIRE PULLING OF LIGHTING AND POWER SYSTEM . |  |  | 29/3/2026 |  | UR
168 | WIR-ELEC-168 | 0 | Electrical | VIP Lounge R03 | This request is to review and comment on the following INSPECTION OF INSTALLATION OF 2 FIX OF FIRE ALARM SYSTEM . |  |  | 29/3/2026 |  | UR
169 | WIR-ELEC-169 | 0 | Electrical | VIP Lounge R03 | This request is to review and comment on the following INSPECTION OF INSTALLATION OF 3 FIX OF FIRE ALARM SYSTEM . |  |  | 29/3/2026 |  | UR
170 | WIR-ELEC-170 | 0 | Electrical | VIP Lounge R03 | This request is to review and comment on the following INSPECTION OF TERMINATION OF DB , INSTALLTION AND TERMINATION OF LIGHTING FITTINGS & WIRING ACCESSORIES |  |  | 29/3/2026 |  | UR
171 | WIR-ELEC-171 | 0 | Electrical | VIP Lounge R03 | This request is to review and comment on the following INSTALATION OF ERTHING SYSTEM (CABLE POLLING ) ,ERTHING RODS ,PITS AND LIGHTNING SYSTEM . |  |  | 29/3/2026 |  | UR
172 | WIR-ELEC-172 | 0 | Electrical | VIP Lounge R03 | This request is to review and comment on the following INSPECTION OF INSTALLATION OF FIRST FIX OF LIGHTING,POWER SYSTEM INSTALLATION OF DB ENCLOSURE . |  |  | 29/3/2026 |  | UR
173 | WIR-ELEC-173 | 0 | Electrical | Q-G02 | This request is to review and comment on the following INSPECTION OF FIRST FIX OF LIGHTING,POWER SYSTEM INSTALLATION OF DB ENCLOSURE . |  |  | 29/3/2026 |  | UR
174 | WIR-ELEC-174 | 0 | Electrical | Q-G02 | This request is to review and comment on the following INSTALLATION OF 1FIX OF LOW CURRENT SYSTEM AND FIRE ALARM SYSTEM . |  |  | 29/3/2026 |  | UR
175 | WIR-ELEC-175 | 0 | Electrical | Q-G02 | This request is to review and comment on the following INSPECTION OF WIRE PULLING |  |  | 29/3/2026 |  | UR
176 | WIR-ELEC-176 | 0 | Electrical | Q-G02 | This request is to review and comment on the following INSTALLATION OF 2FIX OF FIRE ALARM SYSTEM . |  |  | 29/3/2026 |  | UR
177 | WIR-ELEC-177 | 0 | Electrical | Q-G02 | This request is to review and comment on the following INSPECTION OF TERMINATION OF DB , INSTALLTION AND TERMINATION OF LIGHTING FITTINGS & WIRING ACCESSORIES |  |  | 29/3/2026 |  | UR
178 | WIR-ELEC-178 | 0 | Electrical | Q-G02 | This request is to review and comment on the following INSTALLATION OF 3FIX OF FIRE ALARM SYSTEM . |  |  | 29/3/2026 |  | UR
179 | WIR-ELEC-179 | 0 | Electrical | Q-G02 | This request is to review and comment on the following INSTALATION OF ERTHING SYSTEM (CABLE POLLING ) ,ERTHING RODS , PITS AND LIGHTNING SYSTEM . |  |  | 29/3/2026 |  | UR
180 | WIR-ELEC-180 | 0 | Electrical | Reception R01 | This request is to review and comment on the following INSPECTION OF INSTALLATION OF 1 FIX OF LOW CURRENT AND FIRE ALARM SYSTEM . |  |  | 29/3/2026 |  | UR
181 | WIR-ELEC-181 | 0 | Electrical | Reception R01 | This request is to review and comment on the following INSPECTION OF WIRE PULLING OF LIGHTING AND POWER SYSTEM . |  |  | 29/3/2026 |  | UR
182 | WIR-ELEC-182 | 0 | Electrical | Reception R01 | This request is to review and comment on the following INSPECTION OF INSTALLATION OF 2 FIX OF FIRE ALARM SYSTEM . |  |  | 29/3/2026 |  | UR
183 | WIR-ELEC-183 | 0 | Electrical | Reception R01 | This request is to review and comment on the following INSPECTION OF INSTALLATION OF 3 FIX OF FIRE ALARM SYSTEM . |  |  | 29/3/2026 |  | UR
184 | WIR-ELEC-184 | 0 | Electrical | Reception R01 | This request is to review and comment on the following INSPECTION OF TERMINATION OF DB , INSTALLTION AND TERMINATION OF LIGHTING FITTINGS & WIRING ACCESSORIES |  |  | 29/3/2026 |  | UR
185 | WIR-ELEC-185 | 0 | Electrical | Reception R01 | This request is to review and comment on the following INSTALATION OF ERTHING SYSTEM (CABLE POLLING ) ,ERTHING RODS ,PITS AND LIGHTNING SYSTEM . |  |  | 29/3/2026 |  | UR
186 | WIR-ELEC-186 | 0 | Electrical | Reception R01 | This request is to review and comment on the following INSPECTION OF INSTALLATION OF FIRST FIX OF LIGHTING,POWER SYSTEM INSTALLATION OF DB ENCLOSURE . |  |  | 29/3/2026 |  | UR
187 | WIR-ELEC-187 | 0 | Electrical | Work Shop E04 | This request is to review and comment on the following INSPECTION OF INSTALLATION OF 1 FIX OF LOW CURRENT AND FIRE ALARM SYSTEM . |  |  | 29/3/2026 |  | UR
188 | WIR-ELEC-188 | 0 | Electrical | Work Shop E04 | This request is to review and comment on the following INSPECTION OF WIRE PULLING OF LIGHTING AND POWER SYSTEM . |  |  | 29/3/2026 |  | UR
189 | WIR-ELEC-189 | 0 | Electrical | Work Shop E04 | This request is to review and comment on the following INSPECTION OF INSTALLATION OF 2 FIX OF FIRE ALARM SYSTEM . |  |  | 29/3/2026 |  | UR
190 | WIR-ELEC-190 | 0 | Electrical | Work Shop E04 | This request is to review and comment on the following INSPECTION OF INSTALLATION OF 3 FIX OF FIRE ALARM SYSTEM . |  |  | 29/3/2026 |  | UR
191 | WIR-ELEC-191 | 0 | Electrical | Work Shop E04 | This request is to review and comment on the following INSPECTION OF TERMINATION OF DB , INSTALLTION AND TERMINATION OF LIGHTING FITTINGS & WIRING ACCESSORIES |  |  | 29/3/2026 |  | UR
192 | WIR-ELEC-192 | 0 | Electrical | Work Shop E04 | This request is to review and comment on the following INSTALATION OF ERTHING SYSTEM (CABLE POLLING ) ,ERTHING RODS ,PITS AND LIGHTNING SYSTEM . |  |  | 29/3/2026 |  | UR
193 | WIR-ELEC-193 | 0 | Electrical | Work Shop E04 | This request is to review and comment on the following INSPECTION OF INSTALLATION OF FIRST FIX OF LIGHTING,POWER SYSTEM INSTALLATION OF DB ENCLOSURE . |  |  | 29/3/2026 |  | UR
194 | WIR-ELEC-194 | 0 | Electrical | Maintenance Store | This request is to review and comment on the following INSTALLATION OF 1 FIX OF LOW CURRENT SYSTEM AND FIRE ALARM SYSTEM . |  |  | 29/3/2026 |  | UR
195 | WIR-ELEC-195 | 0 | Electrical | Maintenance Store | This request is to review and comment on the following INSPECTION OF FIRST FIX OF LIGHTING,POWER SYSTEM INSTALLATION OF DB ENCLOSURE |  |  | 29/3/2026 |  | UR
196 | WIR-ELEC-196 | 0 | Electrical | Maintenance Store | This request is to review and comment on the following INSTALLATION OF 3 FIX OF FIRE ALARM SYSTEM . |  |  | 29/3/2026 |  | UR
197 | WIR-ELEC-197 | 0 | Electrical | Maintenance Store | This request is to review and comment on the following INSPECTION OF WIRE PULLING |  |  | 29/3/2026 |  | UR
198 | WIR-ELEC-198 | 0 | Electrical | Maintenance Store | This request is to review and comment on the following INSPECTION OF WIRE PULLING |  |  | 29/3/2026 |  | UR
199 | WIR-ELEC-199 | 0 | Electrical | Maintenance Store | This request is to review and comment on the following 3d FIX OF FIRE ALARM SYSTEM . |  |  | 29/3/2026 |  | UR
200 | WIR-ELEC-200 | 0 | Electrical | Maintenance Store | This request is to review and comment on the following INSPECTION OF TERMINATION OF DB , INSTALLTION AND TERMINATION OF LIGHTING FITTINGS & WIRING ACCESSORIES. |  |  | 29/3/2026 |  | UR
201 | WIR-ELEC-201 | 0 | Electrical | Maintenance Store | This request is to review and comment on the following INSTALATION OF ERTHING SYSTEM (CABLE POLLING ) ,ERTHING RODS ,PITS and Lightning system . |  |  | 29/3/2026 |  | UR
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
Owner Logo
Consultant Logo
Owner Logo
Consultant Logo

## MECH
Inspection Request - MECH | [9 empty] | A | Approved |  | Date: | 2026-04-02
[10 empty] | B | Approved with notes
[10 empty] | C | Reject & Resubmit
[10 empty] | CC | Not Resubmitted
[10 empty] | UR | Under Review
DOCUMENT REFERENCE NO |  |  | Element | Location | DESCRIPTION | Attachment |  | Outgoing to Consultant |  | Code Action | Status | Progress | Over Duration | scan | Duration
No | Referance | Rev |  |  |  | Dwg | Report | Submission date | Received Date
1 | WIR-MECH-001 | 0 |  | Zone: 04 Building:VF-01 | drainage pipes in concrete | 1 | 5 | 2025-11-13 | 2025-11-18 | B | CLOSED | 5 | 0 | IN | 2025-11-14
2 | WIR-MECH-002 | 0 |  | Zone: 04 Building:VF-02 | drainage pipes in concrete | 1 | 5 | 2025-11-13 | 2025-11-18 | B | CLOSED | 5 | 0 | IN | 2025-11-14
3 | WIR-MECH-003 | 0 |  | Zone: 04 Building:VF-03 | drainage pipes in concrete | 1 | 5 | 2025-11-13 | 2025-11-18 | B | CLOSED | 5 | 0 | IN | 2025-11-14
4 | WIR-MECH-004 | 0 |  | Zone: 04 Building:VF-04 | drainage pipes in concrete | 1 | 5 | 2025-11-13 | 2025-11-18 | B | CLOSED | 5 | 0 | IN | 2025-11-14
5 | WIR-MECH-005 | 0 |  | Zone: 04 Building:VF-05 | drainage pipes in concrete | 1 | 5 | 2025-11-13 | 2025-11-18 | B | CLOSED | 5 | 0 | IN | 2025-11-14
6 | WIR-MECH-006 | 0 |  | Zone: 04 Building:VF-06 | drainage pipes in concrete | 1 | 5 | 2025-11-13 | 2025-11-18 | B | CLOSED | 5 | 0 | IN
7 | WIR-MECH-007 | 0 |  | Zone: 04 Building:VF-07 | drainage pipes in concrete | 1 | 5 | 2025-11-13 | 2025-11-18 | B | CLOSED | 5 | 0 | IN
8 | WIR-MECH-008 | 0 |  | Zone: 04 Building:VF-08 | drainage pipes in concrete | 1 | 5 | 2025-11-13 | 2025-11-18 | B | CLOSED | 5 | 0 | IN
9 | WIR-MECH-009 | 0 |  | Zone: 04 Building:VF-09 | drainage pipes in concrete | 1 | 5 | 2025-11-17 | 2025-11-18 | B | CLOSED | 1 | 0 | IN
10 | WIR-MECH-010 | 0 |  | Zone: 04 Building:VF-10 | drainage pipes in concrete | 1 | 5 | 2025-11-17 | 2025-11-18 | B | CLOSED | 1 | 0 | IN
11 | WIR-MECH-011 | 0 |  | Zone: 04 Building:VS-01/VS-02 | drainage pipes in concrete | 1 | 5 | 2025-11-17 | 2025-11-18 | B | CLOSED | 1 | 0 | IN
12 | WIR-MECH-012 | 0 |  | Zone: 04 Building:VS-03/VS-04 | drainage pipes in concrete | 1 | 5 | 2025-11-17 | 2025-11-18 | B | CLOSED | 1 | 0 | IN
13 | WIR-MECH-013 | 0 |  | Zone: 04 Building:VS-05 | drainage pipes in concrete | 1 | 5 | 2025-11-17 | 2025-11-18 | B | CLOSED | 1 | 0 | IN
14 | WIR-MECH-014 | 0 |  | Zone: 04 Building:VS-06/VS07 | drainage pipes in concrete | 1 | 5 | 2025-11-17 | 2025-11-18 | B | CLOSED | 1 | 0 | IN
15 | WIR-MECH-015 | 0 |  | Zone: 04 Building:VS-08/VS-09 | drainage pipes in concrete | 1 | 5 | 2025-11-29 | 2025-12-14 | B | CLOSED | 15 | 0 | IN
16 | WIR-MECH-016 | 0 |  | Zone: 03 Building:VS-10/VS11 | drainage pipes in concrete | 1 | 5 | 2025-11-29 | 2025-12-14 | B | CLOSED | 15 | 0 | IN
17 | WIR-MECH-017 | 0 |  | Zone: 03 Building:VS-12-VS-13 | drainage pipes in concrete | 1 | 5 | 2025-11-29 | 2025-12-14 | B | CLOSED | 15 | 0 | IN
18 | WIR-MECH-018 | 0 |  | Zone: 03 Building:VS-14/VS-15 | drainage pipes in concrete | 1 | 5 | 2025-11-29 | 2025-12-14 | B | CLOSED | 15 | 0 | IN
19 | WIR-MECH-019 | 0 |  | Zone: 03,04 Building:GATE01 | drainage pipes in concrete with house connections | 1 | 5 | 2025-12-04 | 2025-12-14 | B | CLOSED | 10 | 0 | IN
20 | WIR-MECH-020 | 0 |  | Zone: 02 Building:GATE02 | drainage pipes in concrete with house connections | 1 | 5 | 2025-12-04 | 2025-12-14 | B | CLOSED | 10 | 0 | IN
21 | WIR-MECH-021 | 0 |  | Zone: 03 Building:VV-01 | drainage pipes in concrete with house connections | 1 | 5 | 2025-12-04 | 2025-12-14 | B | CLOSED | 10 | 0 | IN
22 | WIR-MECH-022 | 0 |  | Zone: 04 Building:VS-05 | drainage pipes in concrete with house connections | 1 | 5 | 2025-12-04 | 2025-12-14 | C | CLOSED | 10 | 0 | IN
23 | WIR-MECH-023 | 0 |  | Zone: 04 Building:VS-05 | Installation and test for water supply network | 1 | 5 | 2025-12-04 | 2025-12-14 | C | CLOSED | 10 | 0 | IN
24 | WIR-MECH-024 | 0 |  | Zone: 04 Building:VS-01/VS-02 | Installation and test for Under tiles drainage pipes and Drainage in walls with house connections | 1 | 5 | 2025-12-04 | 2025-12-14 | B | CLOSED | 10 | 0 | IN
25 | WIR-MECH-025 | 0 |  | Zone: 04 Building:VS-03/VS-04 | Installation and test for Under tiles drainage pipes and Drainage in walls with house connections | 1 | 5 | 2025-12-04 | 2025-12-14 | B | CLOSED | 10 | 0 | IN
26 | WIR-MECH-026 | 0 |  | Zone: 04 Building:VS-01/VS-02 | Under tiles drainage pipes and Drainage in walls with house connections | 1 | 5 | 2025-12-09 | 2025-12-14 | B | CLOSED | 5 | 0 | IN
27 | WIR-MECH-027 | 0 |  | Zone: 04 Building:VS-03/VS-04 | Under tiles drainage pipes and Drainage in walls with house connections | 1 | 5 | 2025-12-09 | 2025-12-14 | B | CLOSED | 5 | 0 | IN
28 | WIR-MECH-028 | 0 |  | Zone: 04 Building:VS-06/VS07 | Under tiles drainage pipes and Drainage in walls with house connections | 1 | 5 | 2025-12-09 | 2025-12-14 | B | CLOSED | 5 | 0 | IN
29 | WIR-MECH-029 | 0 |  | Zone: 04 Building:VS-08/VS-09 | Under tiles drainage pipes and Drainage in walls with house connections | 1 | 5 | 2025-12-09 | 2025-12-14 | B | CLOSED | 5 | 0 | IN
30 | WIR-MECH-030 | 0 |  | Zone: 03 Building:VS-10/VS11 | Under tiles drainage pipes and Drainage in walls with house connections | 1 | 5 | 2025-12-09 | 2025-12-14 | B | CLOSED | 5 | 0 | IN
31 | WIR-MECH-031 | 0 |  | Zone: 03 Building:VS-12-VS-13 | Under tiles drainage pipes and Drainage in walls with house connections | 1 | 5 | 2025-12-09 | 2025-12-14 | B | CLOSED | 5 | 0 | IN
32 | WIR-MECH-032 | 0 |  | Zone: 03 Building:VS-14/VS-15 | Under tiles drainage pipes and Drainage in walls with house connections | 1 | 5 | 2025-12-09 | 2025-12-14 | B | CLOSED | 5 | 0 | IN
33 | WIR-MECH-033 | 0 |  | Zone: 03 Building:VS-16/VS-17 | Under tiles drainage pipes and Drainage in walls with house connections | 1 | 5 | 2025-12-09 | 2025-12-14 | B | CLOSED | 5 | 0 | IN
34 | WIR-MECH-034 | 0 |  | Zone: 04 Building:VS-01/VS-02 | water supply network | 1 | 5 | 2025-12-09 | 2025-12-14 | C | CLOSED | 5 | 0 | IN
35 | WIR-MECH-034 | 1 |  | Zone: 04 Building:VS-01/VS-02 | Installation of water supply network with all valves & WHA for Qaha VS-01/VS-02 |  |  |  |  | UR |  |  |  | IN
36 | WIR-MECH-035 | 0 |  | Zone: 04 Building:VS-03/VS-04 | water supply network | 1 | 5 | 2025-12-09 | 2025-12-14 | C | CLOSED | 5 | 0 | IN
37 | WIR-MECH-035 | 1 |  | Zone: 04 Building:VS-03/VS-04 | Installation of water supply network with all valves & WHA for Qaha VS-03/VS-04 |  |  |  |  | UR
38 | WIR-MECH-036 | 0 |  | Zone: 04 Building:VS-06/VS07 | water supply network | 1 | 5 | 2025-12-09 | 2025-12-14 | C | CLOSED | 5 | 0 | IN
39 | WIR-MECH-036 | 1 |  | Zone: 04 Building:VS-06/VS07 | Installation of water supply network with all valves & WHA for Qaha VS-06/VS-07 |  |  |  |  | UR
40 | WIR-MECH-037 | 0 |  | Zone: 04 Building:VS-08/VS-09 | water supply network | 1 | 5 | 2025-12-09 | 2025-12-14 | C | CLOSED | 5 | 0 | IN
41 | WIR-MECH-037 | 1 |  | Zone: 04 Building:VS-08/VS-09 | Installation of water supply network with all valves & WHA for Qaha VS-08/VS-09 |  |  |  |  | UR
42 | WIR-MECH-038 | 0 |  | Zone: 03 Building:VS-10/VS11 | water supply network | 1 | 5 | 2025-12-09 | 2025-12-14 | C | CLOSED | 5 | 0 | IN
43 | WIR-MECH-038 | 1 |  | Zone: 03 Building:VS-10/VS11 | Installation of water supply network with all valves & WHA for Qaha VS-10/VS11 |  |  |  |  | UR
44 | WIR-MECH-039 | 0 |  | Zone: 03 Building:VS-12-VS-13 | water supply network | 1 | 5 | 2025-12-09 | 2025-12-14 | C | CLOSED | 5 | 0 | IN
45 | WIR-MECH-039 | 1 |  | Zone: 03 Building:VS-12-VS-13 | Installation of water supply network with all valves & WHA for Qaha VS-12/VS13 |  |  |  |  | UR
46 | WIR-MECH-040 | 0 |  | Zone: 03 Building:VS-14/VS-15 | water supply network | 1 | 5 | 2025-12-09 | 2025-12-14 | C | CLOSED | 5 | 0 | IN
47 | WIR-MECH-040 | 1 |  | Zone: 03 Building:VS-14/VS-15 | Installation of water supply network with all valves & WHA for Qaha VS-14/VS-15 |  |  |  |  | UR
48 | WIR-MECH-041 | 0 |  | Zone: 03 Building:VS-16/VS-17 | water supply network | 1 | 5 | 2025-12-09 | 2025-12-14 | C | CLOSED | 5 | 0 | IN
49 | WIR-MECH-041 | 1 |  | Zone: 03 Building:VS-16/VS-17 | Installation of water supply network with all valves & WHA for Qaha VS-16/VS-17 |  |  |  |  | UR
50 | WIR-MECH-042 | 0 |  | Zone: 04 Building:VF-01 | Under tiles drainage pipes and Drainage in walls with house connections | 1 | 5 | 2025-12-09 | 2025-12-14 | B | CLOSED | 5 | 0 | IN
51 | WIR-MECH-043 | 0 |  | Zone: 04 Building:VF-02 | Under tiles drainage pipes and Drainage in walls with house connections | 1 | 5 | 2025-12-09 | 2025-12-14 | B | CLOSED | 5 | 0 | IN
52 | WIR-MECH-044 | 0 |  | Zone: 04 Building:VF-03 | Under tiles drainage pipes and Drainage in walls with house connections | 1 | 5 | 2025-12-09 | 2025-12-14 | B | CLOSED | 5 | 0 | IN
53 | WIR-MECH-045 | 0 |  | Zone: 04 Building:VF-04 | Under tiles drainage pipes and Drainage in walls with house connections | 1 | 5 | 2025-12-09 | 2025-12-14 | B | CLOSED | 5 | 0 | IN
54 | WIR-MECH-046 | 0 |  | Zone: 04 Building:VF-05 | Under tiles drainage pipes and Drainage in walls with house connections | 1 | 5 | 2025-12-09 | 2025-12-14 | B | CLOSED | 5 | 0 | IN
55 | WIR-MECH-047 | 0 |  | Zone: 03 Building:VF-06 | Under tiles drainage pipes and Drainage in walls with house connections | 1 | 5 | 2025-12-09 | 2025-12-14 | B | CLOSED | 5 | 0 | IN
56 | WIR-MECH-048 | 0 |  | Zone: 03 Building:VF-07 | Under tiles drainage pipes and Drainage in walls with house connections | 1 | 5 | 2025-12-09 | 2025-12-14 | B | CLOSED | 5 | 0 | IN
57 | WIR-MECH-049 | 0 |  | Zone: 03 Building:VF-08 | Under tiles drainage pipes and Drainage in walls with house connections | 1 | 5 | 2025-12-09 | 2025-12-14 | B | CLOSED | 5 | 0 | IN
58 | WIR-MECH-050 | 0 |  | Zone: 03 Building:VF-09 | Under tiles drainage pipes and Drainage in walls with house connections | 1 | 5 | 2025-12-09 | 2025-12-14 | B | CLOSED | 5 | 0 | IN
59 | WIR-MECH-051 | 0 |  | Zone: 03 Building:VF-10 | Under tiles drainage pipes and Drainage in walls with house connections | 1 | 5 | 2025-12-09 | 2025-12-14 | B | CLOSED | 5 | 0 | IN
60 | WIR-MECH-052 | 0 |  | Zone: 04 Building:VF-01 | water supply network | 1 | 5 | 2025-12-09 | 2025-12-14 | C | CLOSED | 5 | 0 | IN
61 | WIR-MECH-52 | 1 |  | Zone: 04 Building:VF-01 | Installation of water supply network with all valves & WHA for Qaha VF-01 |  |  |  |  | UR |  |  |  | IN
62 | WIR-MECH-053 | 0 |  | Zone: 04 Building:VF-02 | water supply network | 1 | 5 | 2025-12-09 | 2025-12-14 | C | CLOSED | 5 | 0 | IN
63 | WIR-MECH-053 | 1 |  | Zone: 04 Building:VF-02 | Installation of water supply network with all valves & WHA for Qaha VF-02 |  |  |  |  | UR |  |  |  | IN
64 | WIR-MECH-054 | 0 |  | Zone: 04 Building:VF-03 | water supply network | 1 | 5 | 2025-12-09 | 2025-12-14 | C | CLOSED | 5 | 0 | IN
65 | WIR-MECH-054 | 1 |  | Zone: 04 Building:VF-03 | Installation of water supply network with all valves & WHA for Qaha VF-03 |  |  |  |  | UR |  |  |  | IN
66 | WIR-MECH-055 | 0 |  | Zone: 04 Building:VF-04 | water supply network | 1 | 5 | 2025-12-09 | 2025-12-14 | C | CLOSED | 5 | 0 | IN
67 | WIR-MECH-055 | 1 |  | Zone: 04 Building:VF-04 | Installation of water supply network with all valves & WHA for Qaha VF-04 |  |  |  |  | UR |  |  |  | IN
68 | WIR-MECH-056 | 0 |  | Zone: 04 Building:VF-05 | water supply network | 1 | 5 | 2025-12-09 | 2025-12-14 | C | CLOSED | 5 | 0 | IN
69 | WIR-MECH-056 | 1 |  | Zone: 04 Building:VF-05 | Installation of water supply network with all valves & WHA for Qaha VF-05 |  |  |  |  | UR
70 | WIR-MECH-057 | 0 |  | Zone: 03 Building:VF-06 | water supply network | 1 | 5 | 2025-12-09 | 2025-12-14 | C | CLOSED | 5 | 0 | IN
71 | WIR-MECH-057 | 1 |  | Zone: 03 Building:VF-06 | Installation of water supply network with all valves & WHA for Qaha VF-06 |  |  |  |  | UR |  |  |  | IN
72 | WIR-MECH-058 | 0 |  | Zone: 03 Building:VF-07 | water supply network | 1 | 5 | 2025-12-09 | 2025-12-14 | C | CLOSED | 5 | 0 | IN
73 | WIR-MECH-058 | 1 |  | Zone: 03 Building:VF-07 | Installation of water supply network with all valves & WHA for Qaha VF-07 |  |  |  |  | UR
74 | WIR-MECH-059 | 0 |  | Zone: 03 Building:VF-10 | water supply network | 1 | 5 | 2025-12-09 | 2025-12-14 | C | CLOSED | 5 | 0 | IN
75 | WIR-MECH-059 | 1 |  | Zone: 03 Building:VF-10 | Installation of water supply network with all valves & WHA for Qaha VF-10 |  |  |  |  | UR
76 | WIR-MECH-060 | 0 |  | Zone: 03 Building:VF-08 | water supply network | 1 | 5 | 2025-12-09 |  | UR | PENDING | 114 | 0 | IN
77 | WIR-MECH-060 | 1 |  | Zone: 03 Building:VF-08 | Installation of water supply network with all valves & WHA for Qaha VF-08 |  |  |  |  | UR
78 | WIR-MECH-061 | 0 |  | Zone: 03 Building:VF-09 | water supply network | 1 | 5 | 2025-12-09 | 2025-12-14 | C | CLOSED | 5 | 0 | IN
79 | WIR-MECH-061 | 1 |  | Zone: 03 Building:VF-09 | Installation of water supply network with all valves & WHA for Qaha VF-09 |  |  |  |  | UR
80 | WIR-MECH-062 | 0 |  | Zone: 02 Building:GA-01 | drainage pipes in walls with vent pipes | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
81 | WIR-MECH-063 | 0 |  | Zone: 02 Building:GA-10 | drainage pipes in walls with vent pipes | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
82 | WIR-MECH-064 | 0 |  | Zone: 02 Building:GA-11 | drainage pipes in walls with vent pipes | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
83 | WIR-MECH-065 | 0 |  | Zone: 02 Building:GA-02 | drainage pipes in walls with vent pipes | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
84 | WIR-MECH-066 | 0 |  | Zone: 02 Building:GA-03 | drainage pipes in walls with vent pipes | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
85 | WIR-MECH-067 | 0 |  | Zone: 02 Building:GA-04 | drainage pipes in walls with vent pipes | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
86 | WIR-MECH-068 | 0 |  | Zone: 02 Building:GA-05 | drainage pipes in walls with vent pipes | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
87 | WIR-MECH-069 | 0 |  | Zone: 02 Building:GA-06 | drainage pipes in walls with vent pipes | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
88 | WIR-MECH-070 | 0 |  | Zone: 02 Building:GA-07 | drainage pipes in walls with vent pipes | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
89 | WIR-MECH-071 | 0 |  | Zone: 02 Building:GA-08 | drainage pipes in walls with vent pipes | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
90 | WIR-MECH-072 | 0 |  | Zone: 02 Building:GA-09 | drainage pipes in walls with vent pipes | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
91 | WIR-MECH-073 | 0 |  | Zone: 04 Building:Kiosk-01 | drainage pipes in concrete with house connections | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
92 | WIR-MECH-074 | 0 |  | Zone: 02 Building:GA-06 | underground drainage pipes & SOG with house connections | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
93 | WIR-MECH-075 | 0 |  | Zone: 02 Building:GA-07 | underground drainage pipes & SOG with house connections | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
94 | WIR-MECH-076 | 0 |  | Zone: 02 Building:GA-08 | underground drainage pipes & SOG with house connections | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
95 | WIR-MECH-077 | 0 |  | Zone: 02 Building:GA-09 | underground drainage pipes & SOG with house connections | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
96 | WIR-MECH-078 | 0 |  | Zone: 02 Building:GA-10 | underground drainage pipes & SOG with house connections | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
97 | WIR-MECH-079 | 0 |  | Zone: 02 Building:GA-11 | underground drainage pipes & SOG with house connections | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
98 | WIR-MECH-080 | 0 |  | Zone: 02 Building:Kiosk-08 | drainage pipes in concrete with house connections | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
99 | WIR-MECH-081 | 0 |  | Zone: 02 Building:Kiosk-09 | drainage pipes in concrete with house connections | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
100 | WIR-MECH-082 | 0 |  | Zone: 02 Building:Kiosk-10 | drainage pipes in concrete with house connections | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
101 | WIR-MECH-083 | 0 |  | Zone: 02 Building:Kiosk-12 | drainage pipes in concrete with house connections | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
102 | WIR-MECH-084 | 0 |  | Zone: 02 Building:Kiosk-02 | drainage pipes in concrete with house connections | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
103 | WIR-MECH-085 | 0 |  | Zone: 02 Building:Kiosk-12 | drainage pipes in concrete with house connections | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
104 | WIR-MECH-086 | 0 |  | Zone: 02 Building:GA-01 | drainage pipes in concrete with house connections | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
105 | WIR-MECH-087 | 0 |  | Zone: 02 Building:GA-10 | drainage pipes in concrete with house connections | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
106 | WIR-MECH-088 | 0 |  | Zone: 02 Building:GA-11 | drainage pipes in concrete with house connections | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
107 | WIR-MECH-089 | 0 |  | Zone: 02 Building:GA-02 | drainage pipes in concrete with house connections | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
108 | WIR-MECH-090 | 0 |  | Zone: 02 Building:GA-03 | drainage pipes in concrete with house connections | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
109 | WIR-MECH-091 | 0 |  | Zone: 02 Building:GA-04 | drainage pipes in concrete with house connections | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
110 | WIR-MECH-092 | 0 |  | Zone: 02 Building:GA-05 | drainage pipes in concrete with house connections | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
111 | WIR-MECH-093 | 0 |  | Zone: 02 Building:GA-06 | drainage pipes in concrete with house connections | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
112 | WIR-MECH-094 | 0 |  | Zone: 02 Building:GA-07 | drainage pipes in concrete with house connections | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
113 | WIR-MECH-095 | 0 |  | Zone: 02 Building:GA-08 | drainage pipes in concrete with house connections | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
114 | WIR-MECH-096 | 0 |  | Zone: 02 Building:GA-09 | drainage pipes in concrete with house connections | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
115 | WIR-MECH-097 | 0 |  | Zone: 04 Building:Kiosk-01 | drainage pipes in concrete with house connections | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
116 | WIR-MECH-098 | 0 |  | Zone: 02 Building:GA-06 | drainage pipes in concrete with house connections | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
117 | WIR-MECH-099 | 0 |  | Zone: 02 Building:GA-07 | drainage pipes in concrete with house connections | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
118 | WIR-MECH-100 | 0 |  | Zone: 02 Building:GA-08 | drainage pipes in concrete with house connections | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
119 | WIR-MECH-101 | 0 |  | Zone: 02 Building:GA-09 | drainage pipes in concrete with house connections | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
120 | WIR-MECH-102 | 0 |  | Zone: 02 Building:GA-10 | drainage pipes in concrete with house connections | 1 | 5 | 2026-12-10 | 2026-12-15 | B | CLOSED | 5 | 0 | IN
121 | WIR-MECH-103 | 0 |  | kiosk 09 | drainage pipes in walls with vent pipes |  |  | 2026-12-14 | 2026-12-15 | B | CLOSED | 1 | 0 | IN
122 | WIR-MECH-104 | 0 |  | kiosk 10 | drainage pipes in walls with vent pipes |  |  | 2026-12-14 | 2026-12-15 | B | CLOSED | 1 | 0 | IN
123 | WIR-MECH-105 | 0 |  | kiosk 12 | drainage pipes in walls with vent pipes |  |  | 2026-12-14 | 2026-12-15 | B | CLOSED | 1 | 0 | IN
124 | WIR-MECH-106 | 0 |  | kiosk 17 | drainage pipes in walls with vent pipes |  |  | 2026-12-14 | 2026-12-15 | B | CLOSED | 1 | 0 | IN
125 | WIR-MECH-107 | 0 |  | kiosk 21 | drainage pipes in walls with vent pipes |  |  | 2026-12-14 | 2026-12-15 | B | CLOSED | 1 | 0 | IN
126 | WIR-MECH-108 | 0 |  | kiosk 22 | drainage pipes in walls with vent pipes |  |  | 2026-12-14 | 2026-12-15 | B | CLOSED | 1 | 0 | IN
127 | WIR-MECH-109 | 0 |  | kiosk 23 | drainage pipes in walls with vent pipes |  |  | 2026-12-14 | 2026-12-15 | B | CLOSED | 1 | 0 | IN
128 | WIR-MECH-110 | 0 |  | kiosk 25 | drainage pipes in walls with vent pipes |  |  | 2026-12-14 | 2026-12-15 | B | CLOSED | 1 | 0 | IN
129 | WIR-MECH-111 | 0 |  | kiosk 30 | drainage pipes in walls with vent pipes |  |  | 2026-12-14 | 2026-12-15 | B | CLOSED | 1 | 0 | IN
130 | WIR-MECH-112 | 0 |  | QC03 | drainage pipes in concrete with house connections |  |  | 2026-12-14 | 2026-12-15 | B | CLOSED | 1 | 0 | IN
131 | WIR-MECH-113 | 0 |  | QC04 | drainage pipes in concrete with house connections |  |  | 2026-12-14 | 2026-12-15 | B | CLOSED | 1 | 0 | IN
132 | WIR-MECH-114 | 0 |  | QC10 | drainage pipes in concrete with house connections |  |  | 2026-12-14 | 2026-12-15 | B | CLOSED | 1 | 0 | IN
133 | WIR-MECH-115 | 0 |  | QC13 | drainage pipes in concrete with house connections |  |  | 2026-12-14 | 2026-12-15 | B | CLOSED | 1 | 0 | IN
134 | WIR-MECH-116 | 0 |  | QC14 | drainage pipes in concrete with house connections |  |  | 2026-12-14 | 2026-12-15 | B | CLOSED | 1 | 0 | IN
135 | WIR-MECH-117 | 0 |  | R03 | drainage pipes in concrete with house connections |  |  | 2026-12-14 | 2026-12-15 | B | CLOSED | 1 | 0 | IN
136 | WIR-MECH-118 | 0 |  | R04 | drainage pipes in concrete with house connections |  |  | 2026-12-14 | 2026-12-15 | B | CLOSED | 1 | 0 | IN
137 | WIR-MECH-119 | 0 |  | VS-16 .VS-17 | Under tiles drainage pipes and Drainage in walls with house connections |  |  | 2026-12-14 | 2026-12-15 | B | CLOSED | 1 | 0 | IN
138 | WIR-MECH-120 | 0 |  | VS-16 .VS-17 | Under tiles drainage pipes and Drainage in walls with house connections |  |  | 2026-12-14 | 2026-12-15 | B | CLOSED | 1 | 0 | IN
139 | WIR-MECH-121 | 0 |  | R01 | Under tiles drainage pipes and Drainage in walls with house connections |  |  | 2026-12-14 | 2026-12-15 | B | CLOSED | 1 | 0 | IN
140 | WIR-MECH-122 | 0 |  | E01 | Under tiles drainage pipes and Drainage in walls with house connections |  |  | 2026-12-14 | 2026-12-15 | B | CLOSED | 1 | 0 | IN
141 | WIR-MECH-123 | 0 |  | FA-01 | Under tiles drainage pipes and Drainage in walls with house connections |  |  | 2026-12-14 | 2026-12-15 | B | CLOSED | 1 | 0 | IN
142 | WIR-MECH-124 | 0 |  | FA-02 | Under tiles drainage pipes and Drainage in walls with house connections |  |  | 2026-12-14 | 2026-12-15 | B | CLOSED | 1 | 0 | IN
143 | WIR-MECH-125 | 0 |  | FA-03 | Under tiles drainage pipes and Drainage in walls with house connections |  |  | 2026-12-14 | 2026-12-15 | B | CLOSED | 1 | 0 | IN
144 | WIR-MECH-126 | 0 |  | R05 | Under tiles drainage pipes and Drainage in walls with house connections |  |  | 2026-12-14 | 2026-12-15 | B | CLOSED | 1 | 0 | IN
145 | WIR-MECH-127 | 0 |  | QC-18 | Under tiles drainage pipes and Drainage in walls with house connections |  |  | 2026-12-14 | 2026-12-15 | B | CLOSED | 1 | 0 | IN
146 | WIR-MECH-128 | 0 |  | QC-11 | Under tiles drainage pipes and Drainage in walls with house connections |  |  | 2026-12-14 | 2026-12-15 | B | CLOSED | 1 | 0 | IN
147 | WIR-MECH-129 | 0 |  | QC-12 | Under tiles drainage pipes and Drainage in walls with house connections |  |  | 2026-12-14 | 2026-12-15 | B | CLOSED | 1 | 0 | IN
148 | WIR-MECH-130 | 0 |  | QC-15 | Under tiles drainage pipes and Drainage in walls with house connections |  |  | 2026-12-14 | 2026-12-15 | B | CLOSED | 1 | 0 | IN
149 | WIR-MECH-131 | 0 |  | QC-16 | Under tiles drainage pipes and Drainage in walls with house connections |  |  | 2026-12-14 | 2026-12-15 | B | CLOSED | 1 | 0 | IN
150 | WIR-MECH-132 | 0 |  | WC-01 | Under tiles drainage pipes and Drainage in walls with house connections |  |  | 2026-12-14 | 2026-12-15 | B | CLOSED | 1 | 0 | IN
151 | WIR-MECH-133 | 0 |  | WC-02 | Under tiles drainage pipes and Drainage in walls with house connections |  |  | 2026-12-14 | 2026-12-15 | B | CLOSED | 1 | 0 | IN
152 | WIR-MECH-134 | 0 |  | Zone: 02 Building:GA-01 | REQUEST: Installation and test for underground drainage pipes & SOG with house connections for Qaha GA-01 |  |  | 2026-02-04 | 2026-02-05 | B | CLOSED | 1 | 0 | IN
153 | WIR-MECH-135 | 0 |  | Zone: 02 Building:GA-02 | REQUEST: Installation and test for underground drainage pipes & SOG with house connections for Qaha GA-02 |  |  | 2026-02-04 | 2026-02-05 | B | CLOSED | 1 | 0 | IN
154 | WIR-MECH-136 | 0 |  | Zone: 02 Building:GA-03 | REQUEST: Installation and test for underground drainage pipes & SOG with house connections for Qaha GA-03 |  |  | 2026-02-04 | 2026-02-05 | B | CLOSED | 1 | 0 | IN
155 | WIR-MECH-137 | 0 |  | Zone: 02 Building:GA-04 | REQUEST: Installation and test for underground drainage pipes & SOG with house connections for Qaha GA-04 |  |  | 2026-02-04 | 2026-02-05 | B | CLOSED | 1 | 0 | IN
156 | WIR-MECH-138 | 0 |  | Zone: 02 Building:GA-07 | REQUEST: Installation and test for underground drainage pipes & SOG with house connections for Qaha GA-07 |  |  | 2026-02-04 | 2026-02-05 | B | CLOSED | 1 | 0 | IN
157 | WIR-MECH-139 | 0 |  | Zone: 02 Building:GA-05 | REQUEST: Installation and test for underground drainage pipes & SOG with house connections for Qaha GA-05 |  |  | 2026-02-04 | 2026-02-05 | B | CLOSED | 1 | 0 | IN
158 | WIR-MECH-140 | 0 |  | REQUEST: Installation and test for underground drainage pipes & SOG with house connections for Qaha GA-05 | REQUEST: Installation and test for underground drainage pipes & SOG with house connections for Qaha GA-06 |  |  | 2026-02-04 | 2026-02-05 | B | CLOSED | 1 | 0 | IN
159 | WIR-MECH-141 | 0 |  | Zone: 02 Building:GA-08 | REQUEST: Installation and test for underground drainage pipes & SOG with house connections for Qaha GA-08 |  |  | 2026-02-04 | 2026-02-05 | B | CLOSED | 1 | 0 | IN
160 | WIR-MECH-142 | 0 |  | Zone: 02 Building:GA-09 | REQUEST: Installation and test for underground drainage pipes & SOG with house connections for Qaha GA-09 |  |  | 2026-02-04 | 2026-02-05 | B | CLOSED | 1 | 0 | IN
161 | WIR-MECH-143 | 0 |  | Zone: 02 Building:GA-10 | REQUEST: Installation and test for underground drainage pipes & SOG with house connections for Qaha GA-10 |  |  | 2026-02-04 | 2026-02-05 | B | CLOSED | 1 | 0 | IN
162 | WIR-MECH-144 | 0 |  | Zone: 02 Building:GA-11 | REQUEST: Installation and test for underground drainage pipes & SOG with house connections for Qaha GA-11 |  |  | 2026-02-04 | 2026-02-05 | B | CLOSED | 1 | 0 | IN
163 | WIR-MECH-145 | 0 |  | Zone: 04 Building:Kiosk-01 | REQUEST: Installation and test for drainage pipes in concrete with house connections for Qaha Kiosk-01 |  |  | 2026-02-04 | 2026-02-05 | B | CLOSED | 1 | 0 | IN
164 | WIR-MECH-146 | 0 |  | Zone: 04 Building:Kiosk-02 | REQUEST: Installation and test for drainage pipes in concrete with house connections for Qaha Kiosk-02 |  |  | 2026-02-04 | 2026-02-05 | B | CLOSED | 1 | 0 | IN
165 | WIR-MECH-147 | 0 |  | Zone: 03 Building:Kiosk-03 | REQUEST: Installation and test for drainage pipes in concrete with house connections for Qaha Kiosk-03 |  |  | 2026-02-04 | 2026-02-05 | B | CLOSED | 1 | 0 | IN
166 | WIR-MECH-148 | 0 |  | Zone: 03 Building:Kiosk-04 | REQUEST: Installation and test for drainage pipes in concrete with house connections for Qaha Kiosk-04 |  |  | 2026-02-04 | 2026-02-05 | B | CLOSED | 1 | 0 | IN
167 | WIR-MECH-149 | 0 |  | Zone: 02 Building:Kiosk-08 | REQUEST: Installation and test for drainage pipes in concrete with house connections for Qaha Kiosk-08 |  |  | 2026-02-04 | 2026-02-05 | B | CLOSED | 1 | 0 | IN
168 | WIR-MECH-150 | 0 |  | Zone: 02 Building:Kiosk-09 | REQUEST: Installation and test for drainage pipes in concrete with house connections for Qaha Kiosk-09 |  |  | 2026-02-04 | 2026-02-05 | B | CLOSED | 1 | 0 | IN
169 | WIR-MECH-151 | 0 |  | Zone: 02 Building:Kiosk-10 | REQUEST: Installation and test for drainage pipes in concrete with house connection for Qaha Kiosk-10 |  |  | 2026-02-11 | 2026-02-14 | B | CLOSED | 3 | 0 | IN
170 | WIR-MECH-152 | 0 |  | Zone: 02 Building:Kiosk-12 | Installation and test for drainage pipes in concrete with house connection for Qaha Kiosk-12 |  |  | 2026-02-04 | 2026-02-05 | B | CLOSED | 1 | 0 | IN
171 | WIR-MECH-153 | 0 |  | Zone: 02 Building: Kiosk-17 | Installation and test for drainage pipes in concrete with house connections for Qaha Kiosk-17 |  |  | 2026-02-04 | 2026-02-05 | B | CLOSED | 1 | 0 | IN
172 | WIR-MECH-154 | 0 |  | Zone: 02 Building:Kiosk-21 | Installation and test for drainage pipes in concrete with house connections for Qaha Kiosk-21 |  |  | 2026-02-04 | 2026-02-05 | B | CLOSED | 1 | 0 | IN
173 | WIR-MECH-155 | 0 |  | Zone: 04 Building:QC-10 | Installation and test for drainage pipes in concrete with house connections for Qaha C-10 |  |  | 2026-02-11 | 2026-02-12 | B | CLOSED | 1 | 0 | IN
174 | WIR-MECH-156 | 0 |  | Zone: 02 Building:Kiosk-22 | Installation and test for drainage pipes in concrete with house connections for Qaha Kiosk-22 |  |  | 2026-02-11 | 2026-02-12 | B | CLOSED | 1 | 0 | IN
175 | WIR-MECH-157 | 0 |  | Zone: 04 Building:R03 | Installation and test for drainage pipes in concrete with house connection for Qaha VIP lounge-R03 |  |  | 2026-02-11 | 2026-02-12 | B | CLOSED | 1 | 0 | IN
176 | WIR-MECH-158 | 0 |  | Zone: 03 Building:R04 | Installation and test for drainage pipes in concrete with house connection for Qaha VIP lounge-R04 |  |  | 2026-02-11 | 2026-02-12 | B | CLOSED | 1 | 0 | IN
177 | WIR-MECH-159 | 0 |  | Zone: 04 Building:R01 | Installation and test for drainage pipes in concrete with house connection for Qaha VIP Reception |  |  | 2026-02-11 | 2026-02-12 | B | CLOSED | 1 | 0 | IN
178 | WIR-MECH-160 | 0 |  | Zone: 02 Building:Kiosk-23 | Installation and test for drainage pipes in concrete with house connections for Qaha Kiosk-23 |  |  | 2026-02-11 | 2026-02-12 | B | CLOSED | 1 | 0 | IN
179 | WIR-MECH-161 | 0 |  | Zone: 02 Building:Kiosk-25 | Installation and test for drainage pipes in concrete with house connections for Qaha Kiosk-25 |  |  | 2026-02-11 | 2026-02-12 | B | CLOSED | 1 | 0 | IN
180 | WIR-MECH-162 | 0 |  | Zone: 02 Building:Kiosk-30 | Installation and test for drainage pipes in concrete with house connections for Qaha Kiosk-30 |  |  | 2026-02-11 | 2026-02-12 | B | CLOSED | 1 | 0 | IN
181 | WIR-MECH-163 | 0 |  | Zone: 03 Building:VS-16/VS-17 | Installation and test for Under tiles drainage pipes and Drainage in walls with house connections for Qaha VS-16/VS-17 |  |  | 2026-02-11 | 2026-02-12 | B | CLOSED | 1 | 0 | IN
182 | WIR-MECH-164 | 0 |  | Zone: 03 Building:QC-13 | Installation and test for drainage pipes in concrete with house connections for Qaha C-13 |  |  | 2026-02-11 | 2026-02-12 | B | CLOSED | 1 | 0 | IN
183 | WIR-MECH-165 | 0 |  | Zone: 04 Building:QC-09 | Installation and test for drainage pipes in concrete with house connections for Qaha C-09 |  |  | 2026-02-11 | 2026-02-12 | B | CLOSED | 1 | 0 | IN
184 | WIR-MECH-166 | 0 |  | Zone: 03 Building:QC-14 | Installation and test for drainage pipes in concrete with house connections for Qaha C-14 |  |  | 2026-02-11 | 2026-02-12 | B | CLOSED | 1 | 0 | IN
185 | WIR-MECH-167 | 0 |  | Zone: 03 Building:QC-04 | Installation and test for drainage pipes in concrete with house connections for Qaha C-04 |  |  | 2026-02-11 | 2026-02-12 | B | CLOSED | 1 | 0 | IN
186 | WIR-MECH-168 | 0 |  | Zone: 04 Building:QC-03 | Installation and test for drainage pipes in concrete with house connections for Qaha C-03 |  |  | 2026-02-11 | 2026-02-12 | B | CLOSED | 1 | 0 | IN
187 | WIR-MECH-169 | 0 |  | Zone: 04 Building:Kiosk-01 | Installation and test for drainage pipes in walls with vent pipes for Qaha Kiosk-01 |  |  | 2026-02-11 |  | ur | PENDING | 50 | 0 | IN
188 | WIR-MECH-170 | 0 |  | Zone: 04, Building: Kiosk-02 | Installation and test for drainage pipes in walls with vent pipes for Qaha Kiosk-02 |  |  | 2026-02-11 |  | ur | PENDING | 50 | 0 | IN
189 | WIR-MECH-171 | 0 |  | Zone: 03 Building:Kiosk-03 | Installation and test for drainage pipes in walls with vent pipes for Qaha Kiosk-03 |  |  | 2026-02-11 |  | ur | PENDING | 50 | 0 | IN
190 | WIR-MECH-172 | 0 |  | Zone: 03, Building: Kiosk-04 | Installation and test for drainage pipes in walls with vent pipes for Qaha Kiosk-04 |  |  | 2026-02-11 |  | ur | PENDING | 50 | 0 | IN
191 | WIR-MECH-173 | 0 |  | Zone: 02 Building:Kiosk-08 | Installation and test for drainage pipes in walls with vent pipes for Qaha Kiosk-08 |  |  | 2026-02-11 |  | ur | PENDING | 50 | 0 | IN
192 | WIR-MECH-174 | 0 |  | Zone: 02 Building:Kiosk-09 | Installation and test for drainage pipes in walls with vent pipes for Qaha Kiosk-09 |  |  | 2026-02-11 |  | ur | PENDING | 50 | 0 | IN
193 | WIR-MECH-175 | 0 |  | Zone: 02, Building: Kiosk-10 | Installation and test for drainage pipes in walls with vent pipes for Qaha Kiosk-10 |  |  | 2026-02-11 |  | ur | PENDING | 50 | 0 | IN
194 | WIR-MECH-176 | 0 |  | Zone: 02, Building: Kiosk-12 | Installation and test for drainage pipes in walls with vent pipes for Qaha Kiosk-12 |  |  | 2026-02-11 |  | ur | PENDING | 50 | 0 | IN
195 | WIR-MECH-177 | 0 |  | Zone: 02 Building:Kiosk-17 | Installation and test for drainage pipes in walls with vent pipes for Qaha Kiosk-17 |  |  | 2026-02-11 |  | ur | PENDING | 50 | 0 | IN
196 | WIR-MECH-178 | 0 |  | Zone: 02 Building:Kiosk-21 | Installation and test for drainage pipes in walls with vent pipes for Qaha Kiosk-21 |  |  | 2026-02-11 |  | ur | PENDING | 50 | 0 | IN
197 | WIR-MECH-179 | 0 |  | Zone: 02, Building: Kiosk-22 | Installation and test for drainage pipes in walls with vent pipes for Qaha Kiosk-22 |  |  | 2026-02-11 |  | ur | PENDING | 50 | 0 | IN
198 | WIR-MECH-180 | 0 |  | Zone: 02 Building:Kiosk-23 | Installation and test for drainage pipes in walls with vent pipes for Qaha Kiosk-23 |  |  | 2026-02-11 |  | ur | PENDING | 50 | 0 | IN
199 | WIR-MECH-181 | 0 |  | Zone: 02 Building: Kiosk-25 | Installation and test for drainage pipes in walls with vent pipes for Qaha Kiosk-25 |  |  | 2026-02-11 |  | ur | PENDING | 50 | 0 | IN
200 | WIR-MECH-182 | 0 |  | Zone: 02 Building:Kiosk-30 | Installation and test for drainage pipes in walls with vent pipes for Qaha Kiosk-30 |  |  | 2026-02-11 |  | ur | PENDING | 50 | 0 | IN
201 | WIR-MECH-183 | 0 |  | Zone: 02, Building: GA-01 | Installation and test for drainage pipes in walls with vent pipes for Qaha GA-01 |  |  | 2026-02-11 |  | ur | PENDING | 50 | 0 | IN
202 | WIR-MECH-184 | 0 |  | Zone: 02, Building: GA-02 | Installation and test for drainage pipes in walls with vent pipes for Qaha GA-02 |  |  | 2026-02-11 |  | ur | PENDING | 50 | 0 | IN
203 | WIR-MECH-185 | 0 |  | Zone: 02, Building: GA-03 | Installation and test for drainage pipes in walls with vent pipes for Qaha GA-03 |  |  | 2026-02-11 |  | ur | PENDING | 50 | 0 | IN
204 | WIR-MECH-186 | 0 |  | Zone: 02, Building: GA-04 | Installation and test for drainage pipes in walls with vent pipes for Qaha GA-04 |  |  | 2026-02-11 |  | ur | PENDING | 50 | 0 | IN
205 | WIR-MECH-187 | 0 |  | Zone: 02, Building: GA-06 | Installation and test for drainage pipes in walls with vent pipes for Qaha GA-06 |  |  | 2026-02-11 |  | ur | PENDING | 50 | 0 | IN
206 | WIR-MECH-188 | 0 |  | Zone: 02, Building: GA-07 | Installation and test for drainage pipes in walls with vent pipes for Qaha GA-07 |  |  | 2026-02-11 |  | ur | PENDING | 50 | 0 | IN
207 | WIR-MECH-189 | 0 |  | Zone: 02 Building:GA-08 | Installation and test for drainage pipes in walls with vent pipes for Qaha GA-08 |  |  | 2026-02-11 |  | ur | PENDING | 50 | 0 | IN
208 | WIR-MECH-190 | 0 |  | Zone: 02 Building: GA-09 | Installation and test for drainage pipes in walls with vent pipes for Qaha GA-09 |  |  | 2026-02-11 |  | ur | PENDING | 50 | 0 | IN
209 | WIR-MECH-191 | 0 |  | Zone: 02, Building: GA-10 | Installation and test for drainage pipes in walls with vent pipes for Qaha GA-10 |  |  | 2026-02-11 |  | ur | PENDING | 50 | 0 | IN
210 | WIR-MECH-192 | 0 |  | Zone: 02 Building: GA-11 | Installation and test for drainage pipes in walls with vent pipes for Qaha GA-11 |  |  | 2026-02-11 |  | ur | PENDING | 50 | 0 | IN
211 | WIR-MECH-193 | 0 |  | Zone: 02 Building:GA-05 | Installation and test for drainage pipes in walls with vent pipes for Qaha GA-05 |  |  | 2026-02-11 |  | ur | PENDING | 50 | 0 | IN
212 | WIR-MECH-194 | 0 |  | Zone: 04 Building:QC-07 | Installation and test for drainage pipes in walls with vent pipes for Qaha C-07 |  |  | 8-فبراير | 9-فبراير | b | CLOSED | #VALUE! | 0 | IN
213 | WIR-MECH-195 | 0 |  | Zone: 03 Building:QC-08 | Installation and test for drainage pipes in walls with vent pipes for Qaha C-08 |  |  | 8-فبراير | 9-فبراير | b | CLOSED | #VALUE! | 0 | IN
214 | WIR-MECH-196 | 0 |  | Zone: 04 Building:QC-05 | REQUEST: Installation and test for drainage pipes in walls with vent pipes for Qaha C-05 |  |  | 8-فبراير | 9-فبراير | b | CLOSED | #VALUE! | 0 | IN
215 | WIR-MECH-197 | 0 |  | Zone: 03 Building:QC-06 | REQUEST: Installation and test for drainage pipes in walls with vent pipes for Qaha C-06 |  |  | 8-فبراير | 9-فبراير | b | CLOSED | #VALUE! | 0 | IN
216 | WIR-MECH-198 | 0 |  | Zone: 02 Building:Kiosk-20 | REQUEST: Installation and test for drainage pipes in walls with vent pipes for Qaha Kiosk-20 |  |  | 8-فبراير | 9-فبراير | b | CLOSED | #VALUE! | 0 | IN
217 | WIR-MECH-199 | 0 |  | Zone: 02 Building:Kiosk-24 | REQUEST: Installation and test for drainage pipes in walls with vent pipes for Qaha Kiosk-24 |  |  | 8-فبراير | 9-فبراير | b | CLOSED | #VALUE! | 0 | IN
218 | WIR-MECH-200 | 0 |  | Zone: 02 Building: Maintenance store | REQUEST: Installation and test for drainage pipes in walls with vent pipes for Maintenance Store. |  |  | 8-فبراير | 9-فبراير | b | CLOSED | #VALUE! | 0 | IN
219 | WIR-MECH-201 | 0 |  | Zone: 02 Building:Kiosk-11 | REQUEST: Installation and test for drainage pipes in walls with vent pipes for Qaha Kiosk-11 |  |  | 8-فبراير | 9-فبراير | b | CLOSED | #VALUE! | 0 | IN
220 | WIR-MECH-202 | 0 |  | Zone: 02 Building:Kiosk-18 | REQUEST: Installation and test for drainage pipes in walls with vent pipes for Qaha Kiosk-18 |  |  | 8-فبراير | 9-فبراير | b | CLOSED | #VALUE! | 0 | IN
221 | WIR-MECH-203 | 0 |  | Zone: 02 Building:Kiosk-19 | REQUEST: Installation and test for drainage pipes in walls with vent pipes for Qaha Kiosk-19 |  |  | 8-فبراير | 9-فبراير | b | CLOSED | #VALUE! | 0 | IN
222 | WIR-MECH-204 | 0 |  | Zone: 02 Building:Kiosk-05 | REQUEST: Installation and test for drainage pipes in walls with vent pipes for Qaha Kiosk-05 |  |  | 8-فبراير | 9-فبراير | b | CLOSED | #VALUE! | 0 | IN
223 | WIR-MECH-205 | 0 |  | Zone: 02 Building:Kiosk-06 | REQUEST: Installation and test for drainage pipes in walls with vent pipes for Qaha Kiosk-06 |  |  | 8-فبراير |  | ur | PENDING | #VALUE! | 0 | IN
224 | WIR-MECH-206 | 0 |  | Zone: 04 Building:QC-10 | Installation and test for drainage pipes in concrete with house connections for Qaha C-10 |  |  | 2026-02-11 | 2026-02-14 | B | CLOSED | 3 | 0 | IN
225 | WIR-MECH-207 | 0 |  | Zone: 02 Building: control room | Installation and test for drainage pipes in walls with vent pipes for Control Room. |  |  | 2026-02-11 | 2026-02-14 | B | CLOSED | 3 | 0 | IN
226 | WIR-MECH-208 | 0 |  | Zone: 04 Building:GATE08 | Installation and test for drainage pipes in walls with vent pipes for Qaha Gate-08 |  |  | 2026-02-11 | 2026-02-14 | B | CLOSED | 3 | 0 | IN
227 | WIR-MECH-209 | 0 |  | Zone: 03 Building:GATE09 | Installation and test for drainage pipes in walls with vent pipe for Qaha Gate-09 |  |  | 2026-02-11 | 2026-02-14 | B | CLOSED | 3 | 0 | IN
228 | WIR-MECH-210 | 0 |  | Zone: 02 Building:Kiosk-07 | Installation and test for drainage pipes in walls with vent pipes for Qaha Kiosk-07 |  |  | 2026-02-11 | 2026-02-14 | B | CLOSED | 3 | 0 | IN
229 | WIR-MECH-211 | 0 |  | Zone: 02 Building:R05 | Installation and test for drainage pipes in walls with vent pipes for Qaha gathering R05 |  |  | 2026-02-11 | 2026-02-14 | B | CLOSED | 3 | 0 | IN
230 | WIR-MECH-212 | 0 |  | Zone: 03 Building: QC-18 | REQUEST: Installation and test for drainage pipes in walls with vent pipes for Library QC-18 |  |  | 2026-02-11 | 2026-02-14 | B | CLOSED | 3 | 0 | IN
231 | WIR-MECH-213 | 0 |  | Zone: 04 Building:QC-03 | : Installation and test for drainage pipes in concrete with house connections for Qaha C-03 |  |  | 2026-02-11 | 2026-02-14 | B | CLOSED | 3 | 0 | IN
232 | WIR-MECH-214 | 0 |  | Zone: 03 Building:QC-04 | Installation and test for drainage pipes in concrete with house connections for Qaha C-04 |  |  | 2026-02-11 | 2026-02-14 | B | CLOSED | 3 | 0 | IN
233 | WIR-MECH-215 | 0 |  | Zone: 04 Building:QC-09 | Installation and test for drainage pipes in concrete with house connections for Qaha C-09 |  |  | 2026-02-11 | 2026-02-14 | B | CLOSED | 3 | 0 | IN
234 | WIR-MECH-216 | 0 |  | Zone: 04 Building:QC-11 | Installation and test for drainage pipes in walls with vent pipes for Qaha C-11 |  |  | 2026-02-11 | 2026-02-14 | B | CLOSED | 3 | 0 | IN
235 | WIR-MECH-217 | 0 |  | Zone: 04 Building:QC-12 | Installation and test for drainage pipes in walls with vent pipes for Qaha C-12 |  |  | 2026-02-11 | 2026-02-14 | B | CLOSED | 3 | 0 | IN
236 | WIR-MECH-218 | 0 |  | Zone: 03 Building:QC-13 | Installation and test for drainage pipes in concrete with house connections for Qaha C-13 |  |  | 2026-02-11 | 2026-02-14 | B | CLOSED | 3 | 0 | IN
237 | WIR-MECH-219 | 0 |  | Zone: 03 Building:QC-14 | Installation and test for drainage pipes in concrete with house connections for Qaha C-14 |  |  | 2026-02-11 | 2026-02-14 | B | CLOSED | 3 | 0 | IN
238 | WIR-MECH-220 | 0 |  |  | CLOZING NCR-001 |  |  | 2026-02-11 |  | ur | PENDING | 50 | 0 | IN
239 | WIR-MECH-221 | 0 |  | Zone: 03 Building:QC-15 | Installation and test for drainage pipes in walls with vent pipes for Qaha C-15 |  |  | 2026-02-11 | 2026-02-16 | B | CLOSED | 5 | 0 | IN
240 | WIR-MECH-222 | 0 |  | Zone: 03 Building:QC-16 | Installation and test for drainage pipes in walls with vent pipes for Qaha C-16 |  |  | 2026-02-11 | 2026-02-17 | B | CLOSED | 6 | 0 | IN
241 | WIR-MECH-223 | 0 |  | Zone: 04 Building:WC-01 | Installation and test for drainage pipes in walls with vent network for Qaha WC-01 |  |  | 2026-02-11 | 2026-02-17 | B | CLOSED | 6 | 0 | IN
242 | WIR-MECH-224 | 0 |  | Zone: 03 Building:WC-02 | Installation and test for drainage pipes in walls with vent network for Qaha WC-02 |  |  | 2026-02-11 | 2026-02-17 | B | CLOSED | 6 | 0 | IN
243 | WIR-MECH-225 | 0 |  | Zone: 03 Building:FA-02 | Installation and test for drainage pipes in walls with vent pipes for Qaha FA-02 |  |  | 2026-02-11 | 2026-02-17 | B | CLOSED | 6 | 0 | IN
244 | WIR-MECH-226 | 0 |  | Zone: 02 Building:FA-03 | Installation and test for drainage pipes in walls with vent pipes for Qaha FA-03 |  |  | 2026-02-11 | 2026-02-17 | B | CLOSED | 6 | 0 | IN
245 | WIR-MECH-227 | 0 |  | Zone: 04 Building:FA-01 | Installation and test for drainage pipes in walls with vent pipes for Qaha FA-01 |  |  | 2026-02-11 | 2026-02-17 | B | CLOSED | 6 | 0 | IN
246 | WIR-MECH-228 | 0 |  | Zone: 04 Building:QC-07 | Installation and test for drainage pipes in concrete with house connections for Qaha C-07 |  |  | 2026-02-14 | 2026-02-17 | B | CLOSED | 3 | 0 | IN
247 | WIR-MECH-229 | 0 |  | Zone: 03 Building:QC-08 | Installation and test for drainage pipes in concrete with house connections for Qaha C-08 |  |  | 2026-02-14 |  | ur | PENDING | 47 | 0 | IN
248 | WIR-MECH-230 | 0 |  | Zone: 04 Building:QC-05 | : Installation and test for drainage pipes in concrete with house connections for Qaha C-05 |  |  | 2026-02-14 |  | ur | PENDING | 47 | 0 | IN
249 | WIR-MECH-231 | 0 |  | Zone: 03 Building:QC-06 | Installation and test for drainage pipes in concrete with house connections for Qaha C-06 |  |  | 2026-02-14 | 2026-02-17 | B | CLOSED | 3 | 0 | IN
250 | WIR-MECH-232 | 0 |  | Zone: 02 Building:Kiosk-20 | Installation and test for drainage pipes in concrete with house connections for Qaha Kiosk-20 |  |  | 2026-02-14 | 2026-02-24 | B | CLOSED | 10 | 0 | IN
251 | WIR-MECH-233 | 0 |  | Zone: 02 Building:Kiosk-24 | Installation and test for drainage pipes in concrete with house connections for Qaha Kiosk-24 |  |  | 2026-02-14 | 2026-02-24 | B | CLOSED | 10 | 0 | IN
252 | WIR-MECH-234 | 0 |  | Zone: 02 Building: Maintenance store | Installation and test for drainage pipes in concrete with house connections for Maintenance store. |  |  | 2026-02-14 | 2026-02-24 | B | CLOSED | 10 | 0 | IN
253 | WIR-MECH-235 | 0 |  | Zone: 02 Building:Kiosk-11 | Installation and test for drainage pipes in concrete with house connections for Qaha Kiosk-11 |  |  | 2026-02-14 | 2026-02-24 | B | CLOSED | 10 | 0 | IN
254 | WIR-MECH-236 | 0 |  | Zone: 02 Building:Kiosk-18 | Installation and test for drainage pipes in concrete with house connections for Qaha Kiosk-18 |  |  | 2026-02-14 | 2026-02-24 | B | CLOSED | 10 | 0 | IN
255 | WIR-MECH-237 | 0 |  | Zone: 02 Building:Kiosk-19 | Installation and test for drainage pipes in concrete with house connections for Qaha Kiosk-19 |  |  | 2026-02-14 | 2026-02-24 | B | CLOSED | 10 | 0 | IN
256 | WIR-MECH-238 | 0 |  | Zone: 02 Building:Kiosk-05 | Installation and test for drainage pipes in concrete with house connections for Qaha Kiosk-05 |  |  | 2026-02-14 | 2026-02-24 | B | CLOSED | 10 | 0 | IN
257 | WIR-MECH-239 | 0 |  | Zone: 02 Building:Kiosk-06 | Installation and test for drainage pipes in concrete with house connections for Qaha Kiosk-06 |  |  | 2026-02-14 | 2026-02-24 | B | CLOSED | 10 | 0 | IN
258 | WIR-MECH-240 | 0 |  | Zone: 02 Building:Kiosk-07 | Installation and test for drainage pipes in concrete with house connections for Qaha Kiosk-07 |  |  | 2026-02-14 | 2026-02-24 | B | CLOSED | 10 | 0 | IN
259 | WIR-MECH-241 | 0 |  | Zone: 04 Building:GATE08 | Installation and test for drainage pipes in concrete with house connections for Qaha Gate-08 |  |  | 2026-02-14 | 2026-02-24 | B | CLOSED | 10 | 0 | IN
260 | WIR-MECH-242 | 0 |  | Zone: 03 Building:GATE09 | Installation and test for drainage pipes in concrete with house connections for Qaha Gate-09 |  |  | 2026-02-14 | 2026-02-24 | B | CLOSED | 10 | 0 | IN
261 | WIR-MECH-243 | 0 |  | Zone: 02 Building: control room | Installation and test for drainage pipes in concrete with house connections for Control Room. |  |  | 2026-02-14 | 2026-02-24 | B | CLOSED | 10 | 0 | IN
262 | WIR-MECH-244 | 0 |  | Zone: 04 Building:VS-05 | Installation and test for water supply network with all valves, WHA & EWH for Qaha VS-05 |  |  |  | 2026-02-24 | B | CLOSED | 46077 | 0 | IN
263 | WIR-MECH-245 | 0 |  | Zone: 04 Building:WC-01 | Installation and test for water supply network with all valves, WHA & EWH for Qaha WC-01 |  |  |  | 2026-02-24 | B | CLOSED | 46077 | 0 | IN
264 | WIR-MECH-246 | 0 |  | Zone: 03 Building:WC-02 | Installation and test for water supply network with all valves, WHA & EWH for Qaha WC-02 |  |  |  | 2026-02-24 | B | CLOSED | 46077 | 0 | IN
265 | WIR-MECH-247 | 0 |  | Zone: 03 Building:VV-01 | Installation and test for water supply network with all valves, WHA & EWH for Qaha VV-01 |  |  |  | 2026-02-24 | B | CLOSED | 46077 | 0 | IN
266 | WIR-MECH-248 | 0 |  | Zone: 04 Building:R03 | Installation and test for water supply network with all valves, WHA & EWH for Qaha VIP lounge-R03 |  |  |  | 2026-02-24 | B | CLOSED | 46077 | 0 | IN
267 | WIR-MECH-249 | 0 |  | Zone: 03 Building:R04 | Installation and test for water supply network with all valves, WHA & EWH for Qaha VIP lounge-R04 |  |  |  | 2026-02-24 | B | CLOSED | 46077 | 0 | IN
268 | WIR-MECH-250 | 0 |  | Zone: 04 Building:R01 | Installation and test for water supply network with all valves, WHA & EWH for Qaha VIP Reception |  |  |  | 2026-02-24 | B | CLOSED | 46077 | 0 | IN
269 | WIR-MECH-251 | 0 |  | Zone: 02 Building:R05 | Installation and test for water supply network with all valves, WHA & EWH for Qaha gathering R05 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
270 | WIR-MECH-252 | 0 |  | Zone: 04 Building:QC-10 | Installation and test for drainage pipes in concrete with house connections for Qaha C-10 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
271 | WIR-MECH-253 | 0 |  | Zone: 02 Building:Kiosk-22 | Installation and test for drainage pipes in concrete with house connections for Qaha Kiosk-22 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
272 | WIR-MECH-254 | 0 |  | Zone: 04 Building:R03 | Installation and test for drainage pipes in concrete with house connection for Qaha VIP lounge-R03 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
273 | WIR-MECH-255 | 0 |  | Zone: 03 Building:R04 | Installation and test for drainage pipes in concrete with house connection for Qaha VIP lounge-R04 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
274 | WIR-MECH-256 | 0 |  | Zone: 04 Building:R01 | Installation and test for drainage pipes in concrete with house connection for Qaha VIP Reception |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
275 | WIR-MECH-257 | 0 |  | Zone: 02 Building:Kiosk-23 | Installation and test for drainage pipes in concrete with house connections for Qaha Kiosk-23 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
276 | WIR-MECH-258 | 0 |  | Zone: 04 Building:Kiosk-01 | Installation of EWH for Qaha Kiosk-01 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
277 | WIR-MECH-259 | 0 |  | Zone: 04 Building:Kiosk-02 | Installation of for Qaha Kiosk-02 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
278 | WIR-MECH-260 | 0 |  | Zone: 03 Building:Kiosk-03 | Installation of EWH for Qaha Kiosk-03 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
279 | WIR-MECH-261 | 0 |  | Zone: 03 Building:Kiosk-04 | Installation of EWH for Qaha Kiosk-04 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
280 | WIR-MECH-262 | 0 |  | Zone: 02 Building:Kiosk-05 | Installation of EWH for Qaha Kiosk-05 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
281 | WIR-MECH-263 | 0 |  | Zone: 02 Building:Kiosk-06 | Installation and of EWH for Qaha Kiosk-06 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
282 | WIR-MECH-264 | 0 |  | Zone: 02 Building:Kiosk-07 | Installation of EWH for Qaha Kiosk-07 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
283 | WIR-MECH-265 | 0 |  | Zone: 02 Building:Kiosk-08 | Installation of EWH for Qaha Kiosk-08 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
284 | WIR-MECH-266 | 0 |  | Zone: 02 Building:Kiosk-09 | Installation of EWH for Qaha Kiosk-09 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
285 | WIR-MECH-267 | 0 |  | Zone: 02 Building:Kiosk-10 | Installation of EWH for Qaha Kiosk-10 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
286 | WIR-MECH-268 | 0 |  | Building:Kiosk-11 | Installation of EWH for Qaha Kiosk-11 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
287 | WIR-MECH-269 | 0 |  | Zone: 02 Building:Kiosk-12 | Installation of EWH for Qaha Kiosk-12 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
288 | WIR-MECH-270 | 0 |  | Zone: 02 Building:Kiosk-17 | Installation of EWH for Qaha Kiosk-17 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
289 | WIR-MECH-271 | 0 |  | Zone: 02 Building:Kiosk-18 | Installation of EWH for Qaha Kiosk-18 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
290 | WIR-MECH-272 | 0 |  | Zone: 02 Building:Kiosk-19 | Installation of EWH for Qaha Kiosk-19 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
291 | WIR-MECH-273 | 0 |  | Zone: 02 Building:Kiosk-20 | Installation of EWH for Qaha Kiosk-20 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
292 | WIR-MECH-274 | 0 |  | Zone: 02 Building:Kiosk-21 | Installation of EWH for Qaha Kiosk-21 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
293 | WIR-MECH-275 | 0 |  | Zone: 02 Building:Kiosk-22 | Installation of EWH for Qaha Kiosk-22 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
294 | WIR-MECH-276 | 0 |  | Zone: 02 Building:Kiosk-23 | Installation of EWH for Qaha Kiosk-23 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
295 | WIR-MECH-277 | 0 |  | Zone: 02 Building:Kiosk-24 | Installation of for Qaha Kiosk-24 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
296 | WIR-MECH-278 | 0 |  | Zone: 02 Building:Kiosk-25 | Installation of EWH for Qaha Kiosk-25 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
297 | WIR-MECH-279 | 0 |  | Zone: 02 Building:Kiosk-30 | Installation of EWH for Qaha Kiosk-30 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
298 | WIR-MECH-280 | 0 |  | Zone: 03 Building:QC-16 | Installation of EWH for Qaha C-16 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
299 | WIR-MECH-281 | 0 |  | Zone: 03 Building: WORK SHOP | Installation of EWH for Work shop |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
300 | WIR-MECH-282 | 0 |  | Zone: 03 Building:QC-13 | Installation of EWH for Qaha C-13 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
301 | WIR-MECH-283 | 0 |  | Zone: 04 Building:QC-03 | Installation of EWH for Qaha C-03 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
302 | WIR-MECH-284 | 0 |  | Zone: 03 Building:QC-04 | Installation of EWH for Qaha C-04 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
303 | WIR-MECH-285 | 0 |  | Zone: 04 Building:QC-05 | Installation of EWH for Qaha C-05 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
304 | WIR-MECH-286 | 0 |  | Zone: 03 Building:QC-06 | Installation of EWH for Qaha C-06 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
305 | WIR-MECH-287 | 0 |  | Zone: 04 Building:QC-07 | Installation of EWH for Qaha C-07 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
306 | WIR-MECH-288 | 0 |  | Zone: 03 Building:QC-08 | Installation and of EWH for Qaha C-08 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
307 | WIR-MECH-289 | 0 |  | Zone: 04 Building:QC-09 | Installation of EWH for Qaha C-09 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
308 | WIR-MECH-290 | 0 |  | Zone: 04 Building:QC-10 | Installation of EWH for Qaha C-10 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
309 | WIR-MECH-291 | 0 |  | Zone: 04 Building:QC-11 | Installation of EWH for Qaha C-11 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
310 | WIR-MECH-292 | 0 |  | Zone: 04 Building:QC-12 | Installation of EWH for Qaha C-12 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
311 | WIR-MECH-293 | 0 |  | Zone: 03 Building:QC-14 | Installation of EWH for Qaha C-14 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
312 | WIR-MECH-294 | 0 |  | Zone: 03 Building:QC-15 | Installation of EWH for Qaha C-15 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
313 | WIR-MECH-295 | 0 |  | Zone: 02 Building:GA-10 | Installation of EWH for Qaha GA-10 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
314 | WIR-MECH-296 | 0 |  | Zone: 02 Building:GA-11 | Installation of EWH for Qaha GA-11 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
315 | WIR-MECH-297 | 0 |  | Zone: 02 Building:GA-01 | Installation of EWH for Qaha GA-01 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
316 | WIR-MECH-298 | 0 |  | Zone: 02 Building:GA-02 | Installation of EWH for Qaha GA-02 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
317 | WIR-MECH-299 | 0 |  | Zone: 02 Building:GA-03 | Installation of EWH for Qaha GA-03 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
318 | WIR-MECH-300 | 0 |  | Zone: 02 Building:GA-04 | Installation of EWH for Qaha GA-04 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
319 | WIR-MECH-301 | 0 |  | Zone: 02 Building:GA-05 | Installation of EWH for Qaha GA-05 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
320 | WIR-MECH-302 | 0 |  | Zone: 02 Building:GA-06 | Installation of EWH for Qaha GA-06 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
321 | WIR-MECH-303 | 0 |  | Zone: 02 Building:GA-07 | Installation of EWH for Qaha GA-07 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
322 | WIR-MECH-304 | 0 |  | Zone: 02 Building:GA-08 | Installation of EWH for Qaha GA-08 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
323 | WIR-MECH-305 | 0 |  | Zone: 02 Building:GA-09 | Installation of EWH for Qaha GA-09 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
324 | WIR-MECH-306 | 0 |  | Zone: 04 Building:FA-01 | Installation of EWH for Qaha FA-01 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
325 | WIR-MECH-307 | 0 |  | Zone: 03 Building:FA-02 | Installation of EWH for Qaha FA-02 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
326 | WIR-MECH-308 | 0 |  | Zone: 02 Building:FA-03 | Installation of EWH for Qaha VF-04 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
327 | WIR-MECH-309 | 0 |  | Zone: 04 Building:VF-01 | Installation of EWH for Qaha VF-01 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
328 | WIR-MECH-310 | 0 |  | Zone: 04 Building:VF-02 | Installation of EWH for Qaha VF-02 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
329 | WIR-MECH-311 | 0 |  | Zone: 04 Building:VF-03 | Installation of EWH for Qaha VF-03 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
330 | WIR-MECH-312 | 0 |  | Zone: 04 Building:VF-04 | Installation of EWH for Qaha VF-04 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
331 | WIR-MECH-313 | 0 |  | Zone: 04 Building:VF-05 | Installation of EWH for Qaha VF-05 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
332 | WIR-MECH-314 | 0 |  | Zone: 03 Building:VF-06 | Installation of EWH for Qaha VF-06 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
333 | WIR-MECH-315 | 0 |  | Zone: 03 Building:VF-07 | Installation of EWH for Qaha VF-07 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
334 | WIR-MECH-316 | 0 |  | Zone: 03 Building:VF-08 | Installation of EWH for Qaha VF-08 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
335 | WIR-MECH-317 | 0 |  | Zone: 03 Building:VF-09 | Installation of EWH for Qaha VF-09 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
336 | WIR-MECH-318 | 0 |  | Zone: 03 Building:VF-10 | Installation of EWH for Qaha VF-10 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
337 | WIR-MECH-319 | 0 |  | Zone: 04 Building:VS-01/VS-02 | Installation of EWH for Qaha VS-01/VS-02 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
338 | WIR-MECH-320 | 0 |  | Zone: 04 Building:VS-03/VS-04 | Installation of EWH for Qaha VS-03/VS-04 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
339 | WIR-MECH-321 | 0 |  | Zone: 04 Building:VS-06/VS-07 | Installation of EWH for Qaha VS-06/VS-07 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
340 | WIR-MECH-322 | 0 |  | Zone: 04 Building:VS-08/VS-09 | Installation of EWH for Qaha VS-08/VS-09 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
341 | WIR-MECH-323 | 0 |  | Zone: 03 Building:VS-10/VS-11 | Installation of EWH for Qaha VS-10/VS11 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
342 | WIR-MECH-324 | 0 |  | Zone: 03 Building:VS-12/VS-13 | Installation of EWH for Qaha VS-12/VS13 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
343 | WIR-MECH-325 | 0 |  | Zone: 03 Building:VS-14/VS-15 | Installation of EWH for Qaha VS-14/VS-15 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
344 | WIR-MECH-326 | 0 |  | Zone: 03 Building:VS-16/VS-17 | Installation of EWH for Qaha VS-16/VS-17 |  |  | 2026-02-21 | 2026-02-24 | B | CLOSED | 3 | 0 | IN
345 | WIR-MECH-327 | 0 |  | Zone: 02 Building: GA-01 | Installation of SPLIT AC units with copper pipes for Qaha GA-01 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
346 | WIR-MECH-328 | 0 |  | Zone: 02 Building: GA-02 | Installation of SPLIT AC units with copper pipes for Qaha GA-02 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
347 | WIR-MECH-329 | 0 |  | Zone: 02 Building: GA-03 | Installation of SPLIT AC units with copper pipes for Qaha GA-03 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
348 | WIR-MECH-330 | 0 |  | Zone: 02 Building: GA-04 | Installation of SPLIT AC units with copper pipes for Qaha GA-04 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
349 | WIR-MECH-331 | 0 |  | Zone: 02 Building: GA-05 | Installation of SPLIT AC units with copper pipes for Qaha GA-05 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
350 | WIR-MECH-332 | 0 |  | Zone: 02 Building: GA-06 | Installation of SPLIT AC units with copper pipes for Qaha GA-06 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
351 | WIR-MECH-333 | 0 |  | Zone: 02 Building: GA-07 | Installation of SPLIT AC units with copper pipes for Qaha GA-07 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
352 | WIR-MECH-334 | 0 |  | Zone: 02 Building: GA-08 | Installation of SPLIT AC units with copper pipes for Qaha GA-08 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
353 | WIR-MECH-335 | 0 |  | Zone: 02 Building: GA-09 | Installation of SPLIT AC units with copper pipes for Qaha GA-09 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
354 | WIR-MECH-336 | 0 |  | Zone: 02 Building: GA-10 | Installation of SPLIT AC units with copper pipes for Qaha GA-10 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
355 | WIR-MECH-337 | 0 |  | Zone: 02 Building: GA-11 | Installation of SPLIT AC units with copper pipes for Qaha GA-11 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
356 | WIR-MECH-338 | 0 |  | Zone: 03 Building: VV-01 | Installation for SPLIT AC units with copper pipes for Qaha VV-01 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
357 | WIR-MECH-339 | 0 |  | Zone: 04 Building: VS-01 | Installation of SPLIT AC units with copper pipes for Qaha VS-01/VS-02 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
358 | WIR-MECH-340 | 0 |  | Zone: 04 Building: VS-03 | Installation of SPLIT AC units with copper pipes for Qaha VS-03/VS-04 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
359 | WIR-MECH-341 | 0 |  | Zone: 04 Building: VS-06 | Installation of SPLIT AC units with copper pipes for Qaha VS-06/VS-07 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
360 | WIR-MECH-342 | 0 |  | Zone: 04 Building: VS-08 | Installation of SPLIT AC units with copper pipes for Qaha VS-08/VS-09 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
361 | WIR-MECH-343 | 0 |  | Zone: 03 Building: VS-10 | Installation of SPLIT AC units with copper pipes for Qaha VS-10/VS-11 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
362 | WIR-MECH-344 | 0 |  | Zone: 03 Building: VS-12-VS-13 | Installation of SPLIT AC units with copper pipes for Qaha VS12-VS-13 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
363 | WIR-MECH-345 | 0 |  | Zone: 03 Building: VS-14 | Installation of SPLIT AC units with copper pipes for Qaha VS-14/VS-15 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
364 | WIR-MECH-346 | 0 |  | Zone: 03 Building: VS-16 | Installation of SPLIT AC units with copper pipes for Qaha VS-16/VS-17 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
365 | WIR-MECH-347 | 0 |  | Zone: 04 Building: VS-05 | Installation of SPLIT AC units with copper pipes for Qaha VS-05 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
366 | WIR-MECH-348 | 0 |  | Zone: 04 Building: QV-01 | Installation of SPLIT AC units with copper pipes for Qaha QV-01 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
367 | WIR-MECH-349 | 0 |  | Zone: 04 Building: QV-02 | Installation of SPLIT AC units with copper pipes for Qaha QV-02 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
368 | WIR-MECH-350 | 0 |  | Zone: 04 Building: QV-03 | Installation of SPLIT AC units with copper pipes for Qaha QV-03 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
369 | WIR-MECH-351 | 0 |  | Zone: 04 Building: QV-04 | Installation of SPLIT AC units with copper pipes for Qaha QV-04 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
370 | WIR-MECH-352 | 0 |  | Zone: 04 Building: QV-05 | Installation of SPLIT AC units with copper pipes for Qaha QV-05 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
371 | WIR-MECH-353 | 0 |  | Zone: 03 Building: QV-06 | Installation of SPLIT AC units with copper pipes for Qaha QV-06 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
372 | WIR-MECH-354 | 0 |  | Zone: 03 Building: QV-07 | Installation of SPLIT AC units with copper pipes for Qaha QV-07 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
373 | WIR-MECH-355 | 0 |  | Zone: 03 Building: QV-08 | Installation of SPLIT AC units with copper pipes for Qaha QV-08 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
374 | WIR-MECH-356 | 0 |  | Zone: 03 Building: QV-09 | Installation of SPLIT AC units with copper pipes for Qaha QV-09 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
375 | WIR-MECH-357 | 0 |  | Zone: 03 Building: QV-10 | Installation of SPLIT AC units with copper pipes for Qaha QV-10 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
376 | WIR-MECH-358 | 0 |  | Zone: 02 Building: GA-01 | Installation of GI Duct with exhaust fan in toilet for Qaha GA-01 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
377 | WIR-MECH-359 | 0 |  | Zone: 02 Building: GA-02 | Installation of GI Duct with exhaust fan in toliet for Qaha GA-02 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
378 | WIR-MECH-360 | 0 |  | Zone: 02 Building: GA-03 | Installation of GI Duct with exhaust fan in toilet for Qaha GA-03 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
379 | WIR-MECH-361 | 0 |  | Zone: 02 Building: GA-04 | Installation of GI Duct with exhaust fan in toilet for Qaha GA-04 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
380 | WIR-MECH-362 | 0 |  | Zone: 02 Building: GA-05 | Installation of GI Duct with exhaust fan in toilet for Qaha GA-05 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
381 | WIR-MECH-363 | 0 |  | Zone: 02 Building: GA-06 | Installation of GI Duct with exhaust fan in toilet for Qaha GA-06 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
382 | WIR-MECH-364 | 0 |  | Zone: 02 Building: GA-07 | Installation of GI Duct with exhaust fan in toilet for Qaha GA-07 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
383 | WIR-MECH-365 | 0 |  | Zone: 02 Building: GA-08 | Installation of GI Duct with exhaust fan in toilet for Qaha GA-08 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
384 | WIR-MECH-366 | 0 |  | Zone: 02 Building: GA-09 | Installation of GI Duct with exhaust fan in toilet for Qaha GA-09 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
385 | WIR-MECH-367 | 0 |  | Zone: 02 Building: GA-10 | Installation of GI Duct with exhaust fan in toilet for Qaha GA-10 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
386 | WIR-MECH-368 | 0 |  | Zone: 02 Building: GA-11 | Installation of GI Duct with exhaust fan in toilet for Qaha GA-11 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
387 | WIR-MECH-369 | 0 |  | Zone: 03 Building: VV-01 | Installation for GI Duct with Exhaust fans in toilet & kitchen for Qaha VV-01 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
388 | WIR-MECH-370 | 0 |  | Zone: 04 Building: VS-01 | Installation of GI Duct with exhaust fan in toilet for Qaha VS-01/VS-02 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
389 | WIR-MECH-371 | 0 |  | Zone: 04 Building: VS-03 | Installation of GI Duct with exhaust fan in toilet for Qaha VS-03/VS-04 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
390 | WIR-MECH-372 | 0 |  | Zone: 04 Building: VS-06 | Installation of GI Duct with exhaust fan in toilet for Qaha VS-06/VS-07 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
391 | WIR-MECH-373 | 0 |  | Zone: 04 Building: VS-08 | Installation of GI Duct with exhaust fan in toilet for Qaha VS-08/VS-09 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
392 | WIR-MECH-374 | 0 |  | Zone: 03 Building: VS-10 | Installation of GI Duct with exhaust fan in toilet for Qaha VS-10/VS-11 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
393 | WIR-MECH-375 | 0 |  | Zone: 03 Building: VS-12-VS-13 | Installation of GI Duct with exhaust fan in toilet for Qaha VS12-VS-13 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
394 | WIR-MECH-376 | 0 |  | Zone: 03 Building: VS-14 | Installation of GI Duct with exhaust fan in toilet for Qaha VS-14/VS-15 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
395 | WIR-MECH-377 | 0 |  | Zone: 03 Building: VS-16 | Installation of GI Duct with exhaust fan in toilet for Qaha VS-16/VS-17 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
396 | WIR-MECH-378 | 0 |  | Zone: 04 Building: VS-05 | Installation of GI Duct with exhaust fan in toilet for Qaha VS-05 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
397 | WIR-MECH-379 | 0 |  | Zone: 02 Building: GA-01 | Installation of GI Duct with exhaust fan in toilet for Qaha QV-01 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
398 | WIR-MECH-380 | 0 |  | Zone: 04 Building: VF-02 | Installation of GI Duct with exhaust fan in toilet for Qaha VF-02 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
399 | WIR-MECH-381 | 0 |  | Zone: 04 Building: VF-03 | Installation of GI Duct with exhaust fan in toilet for Qaha VF-03 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
400 | WIR-MECH-382 | 0 |  | Zone: 04 Building: VF-04 | Installation of GI Duct with exhaust fan in toilet for Qaha VF-04 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
401 | WIR-MECH-383 | 0 |  | Zone: 04 Building: VF-05 | Installation of GI Duct with exhaust fan in toilet for Qaha VF-05 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
402 | WIR-MECH-384 | 0 |  | Zone: 03 Building: VF-06 | Installation of GI Duct with exhaust fan in toilet for Qaha VF-06 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
403 | WIR-MECH-385 | 0 |  | Zone: 03 Building: VF-07 | Installation of GI Duct with exhaust fan in toilet for Qaha VF-07 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
404 | WIR-MECH-386 | 0 |  | Zone: 03 Building: VF-08 | Installation of GI Duct with exhaust fan in yoilet for Qaha VF-08 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
405 | WIR-MECH-387 | 0 |  | Zone: 03 Building: VF-09 | Installation of GI Duct with exhaust fan in toilet for Qaha VF-09 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
406 | WIR-MECH-388 | 0 |  | Zone: 03 Building: VF-10 | Installation of GI Duct with exhaust fan in toilet for Qaha VF-10 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
407 | WIR-MECH-389 | 0 |  | Zone: 02 Building: Control Room | Installation of AC SPLIT units with copper pipes for control room. |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
408 | WIR-MECH-390 | 0 |  | Zone: 02 Building: CONTROL ROOM | Installation of AC split units with copper pipes for CONTROL ROOM |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
409 | WIR-MECH-391 | 0 |  | Zone: 04 Building: QC-03 | Installation of AC split units with copper pipes for Qaha C-03 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
410 | WIR-MECH-392 | 0 |  | Zone: 03 Building: QC-04 | Installation of AC split units with copper pipes for Qaha C-04 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
411 | WIR-MECH-393 | 0 |  | Zone: 04 Building: QC-05 | Installation of AC split units with copper pipes for Qaha C-05 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
412 | WIR-MECH-394 | 0 |  | Zone: 03 Building: QC-06 | Installation of AC split units with copper pipes for Qaha C-06 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
413 | WIR-MECH-395 | 0 |  | Zone: 04 Building: QC-07 | Installation of AC split units with copper pipes for Qaha C-07 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
414 | WIR-MECH-396 | 0 |  | Zone: 03 Building: QC-08 | Installation of AC split units with copper pipes for Qaha C-08 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
415 | WIR-MECH-397 | 0 |  | Zone: 04 Building: QC-09 | Installation of AC split units with copper pipes for Qaha C-09 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
416 | WIR-MECH-398 | 0 |  | Zone: 04 Building: QC-10 | Installation of AC split units with copper pipes for Qaha C-10 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
417 | WIR-MECH-399 | 0 |  | Zone: 04 Building: QC-11 | Installation of AC split units with copper pipes for Qaha C-11 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
418 | WIR-MECH-400 | 0 |  | Zone: 04 Building: QC-12 | Installation of AC split units with copper pipes for Qaha C-12 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
419 | WIR-MECH-401 | 0 |  | Zone: 03 Building: QC-13 | Installation of AC split units with copper pipes for Qaha C-13 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
420 | WIR-MECH-402 | 0 |  | Zone: 03 Building: QC-14 | Installation of AC split units with copper pipes for Qaha C-14 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
421 | WIR-MECH-403 | 0 |  | Zone: 03 Building: QC-15 | Installation of AC split units with copper pipes for Qaha C-15 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
422 | WIR-MECH-404 | 0 |  | Zone: 03 Building: QC-16 | Installation of AC split units with copper pipes for Qaha C-16 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
423 | WIR-MECH-405 | 0 |  | Zone: 04 Building: FA-01 | Installation of AC split units with copper pipes for Qaha FA-01 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
424 | WIR-MECH-406 | 0 |  | Zone: 03 Building: FA-02 | Installation of AC split units with copper pipes for Qaha FA-02 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
425 | WIR-MECH-407 | 0 |  | Zone: 02 Building: FA-03 | Installation of AC split units with copper pipes for Qaha FA-03 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
426 | WIR-MECH-408 | 0 |  | Zone: 04 Building: Kiosk-01 | Installation of AC SPLIT units with copper pipes for Qaha Kiosk-01 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
427 | WIR-MECH-409 | 0 |  | Zone: 04 Building: Kiosk-02 | Installation of AC SPLIT units with copper pipes for Qaha Kiosk-02 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
428 | WIR-MECH-410 | 0 |  | Zone: 03 Building: Kiosk-03 | Installation of AC SPLIT units with copper pipes for Qaha Kiosk-03 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
429 | WIR-MECH-411 | 0 |  | Zone: 03 Building: Kiosk-04 | Installation of AC SPLIT units with copper pipes for Qaha Kiosk-04 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
430 | WIR-MECH-412 | 0 |  | Zone: 02 Building: Kiosk-05 | Installation of AC SPLIT units with copper pipes for Qaha Kiosk-05 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
431 | WIR-MECH-413 | 0 |  | Zone: 02 Building: Kiosk-06 | Installation of AC SPLIT units with copper pipes for Qaha Kiosk-06 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
432 | WIR-MECH-414 | 0 |  | Zone: 02 Building: Kiosk-07 | Installation of AC SPLIT units with copper pipes for Qaha Kiosk-07 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
433 | WIR-MECH-415 | 0 |  | Zone: 02 Building: Kiosk-08 | Installation of AC SPLIT units with copper pipes for Qaha Kiosk-08 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
434 | WIR-MECH-416 | 0 |  | Zone: 02 Building: Kiosk-09 | Installation of AC SPLIT units with copper pipes for Qaha Kiosk-09 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
435 | WIR-MECH-417 | 0 |  | Zone: 02 Building: Kiosk-10 | Installation of AC SPLIT units with copper pipes for Qaha Kiosk-10 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
436 | WIR-MECH-418 | 0 |  | Zone: 02 Building: Kiosk-11 | Installation of AC SPLIT units with copper pipes for Qaha Kiosk-11 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
437 | WIR-MECH-419 | 0 |  | Zone: 02 Building: Kiosk-12 | Installation of AC SPLIT units with copper pipes for Qaha Kiosk-12 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
438 | WIR-MECH-420 | 0 |  | Zone: 02 Building: Kiosk-17 | Installation of AC SPLIT units with copper pipes for Qaha Kiosk-17 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
439 | WIR-MECH-421 | 0 |  | Zone: 02 Building: Kiosk-18 | Installation of AC SPLIT units with copper pipes for Qaha Kiosk-18 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
440 | WIR-MECH-422 | 0 |  | Zone: 02 Building: Kiosk-19 | Installation of AC SPLIT units with copper pipes for Qaha Kiosk-19 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
441 | WIR-MECH-423 | 0 |  | Zone: 02 Building: Kiosk-20 | Installation of AC SPLIT units with copper pipes for Qaha Kiosk-20 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
442 | WIR-MECH-424 | 0 |  | Zone: 02 Building: Kiosk-21 | Installation of AC SPLIT units with copper pipes for Qaha Kiosk-21 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
443 | WIR-MECH-425 | 0 |  | Zone: 02 Building: Kiosk-22 | Installation of AC SPLIT units with copper pipes for Qaha Kiosk-22 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
444 | WIR-MECH-426 | 0 |  | Zone: 02 Building: Kiosk-23 | Installation of AC SPLIT units with copper pipes for Qaha Kiosk-23 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
445 | WIR-MECH-427 | 0 |  | Zone: 02 Building: Kiosk-24 | Installation of AC SPLIT units with copper pipes for Qaha Kiosk-24 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
446 | WIR-MECH-428 | 0 |  | Zone: 02 Building: Kiosk-25 | Installation of AC SPLIT units with copper pipes for Qaha Kiosk-25 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
447 | WIR-MECH-429 | 0 |  | Zone: 02 Building: Kiosk-30 | Installation of AC SPLIT units with copper pipes for Qaha Kiosk-30 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
448 | WIR-MECH-430 | 0 |  | Zone: 02 Building: Camel Station | Installation of exhaust fans for Qaha Camel Station |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
449 | WIR-MECH-431 | 0 |  | Zone: 03 Building: GATE01 | Installation of AC SPLIT units with copper pipes Qaha Gate-01 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
450 | WIR-MECH-432 | 0 |  | Zone: 02 Building: GATE02 | Installation of AC SPLIT units with copper pipes for Qaha Gate-02 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
451 | WIR-MECH-433 | 0 |  | Zone: 04 Building: GATE08 | Installation of copper pipes with control cable for all AC units for Qaha Gate-08 |  |  | 2026-02-21 |  | ur | PENDING | 40 | 0 | IN
452 | WIR-MECH-434 | 0 |  | Zone: 03 Building: GATE09 | Installation of AC split units with copper pipes for Qaha Gate-09 |  |  | 2026-02-21 |  | ur | PENDING | #REF! | 0 | IN
453 | WIR-MECH-435 | 0 |  | Zone: 04 Building: QC-03 | Installation of water supply network with all valves & WHA for Qaha C-03 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
454 | WIR-MECH-436 | 0 |  | Zone: 03 Building: QC-04 | Installation of water supply network with all valves & WHA for Qaha C-04 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
455 | WIR-MECH-437 | 0 |  | Zone: 04 Building: QC-05 | Installation of water supply network with all valves & WHA for Qaha C-05 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
456 | WIR-MECH-438 | 0 |  | Zone: 03 Building: QC-06 | Installation of water supply network with all valves of WHA for Qaha C-06 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
457 | WIR-MECH-439 | 0 |  | Zone: 04 Building: QC-07 | Installation of water supply network with all valves & WHA for Qaha C-07 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
458 | WIR-MECH-440 | 0 |  | Zone: 03 Building: QC-08 | Installation of water supply network with all valves & WHA for Qaha C-08 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
459 | WIR-MECH-441 | 0 |  | Zone: 04 Building: QC-09 | Installation of water supply network with all valves & WHA for Qaha C-09 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
460 | WIR-MECH-442 | 0 |  | Zone: 04 Building: QC-10 | Installation of water supply network with all valves & WHA for Qaha C-10 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
461 | WIR-MECH-443 | 0 |  | Zone: 04 Building: QC-11 | Installation of water supply network with all valves & WHA for Qaha C-11 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
462 | WIR-MECH-444 | 0 |  | Zone: 04 Building: QC-12 | Installation of water supply network with all valves & WHA for Qaha C-12 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
463 | WIR-MECH-445 | 0 |  | Zone: 03 Building: QC-13 | Installation of water supply network with all valves & WHA for Qaha C-13 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
464 | WIR-MECH-446 | 0 |  | Zone: 03 Building: QC-14 | Installation of water supply network with all valves & WHA for Qaha C-14 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
465 | WIR-MECH-447 | 0 |  | Zone: 03 Building: QC-15 | Installation of water supply network with all valves & WHA for Qaha C-15 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
466 | WIR-MECH-448 | 0 |  | Zone: 03 Building: QC-16 | Installation of water supply network with all valves & WHA for Qaha C-16 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
467 | WIR-MECH-449 | 0 |  | Zone: 03 Building: WORK SHOP | Installation of water supply network with all valves & WHA for Work shop |  |  |  |  | ur | PENDING | #REF! | 0 | IN
468 | WIR-MECH-450 | 0 |  | Zone: 04 Building: FA-01 | Installation of water supply network with all valves & WHA for Qaha FA-01 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
469 | WIR-MECH-451 | 0 |  | Zone: 03 Building: FA-02 | Installation of water supply network with all valves & WHA for Qaha FA-02 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
470 | WIR-MECH-452 | 0 |  | Zone: 02 Building: FA-03 | Installation of water supply network with all valves & WHA for Qaha FA-03 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
471 | WIR-MECH-453 | 0 |  | Zone: 02 Building: GA-01 | Installation of water supply network with all valves & WHA for Qaha GA-01 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
472 | WIR-MECH-454 | 0 |  | Zone: 02 Building: GA-02 | Installation of water supply network with all valves & WHA for Qaha GA-02 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
473 | WIR-MECH-455 | 0 |  | Zone: 02 Building: GA-03 | Installation of water supply network with all valves & WHA for Qaha GA-03 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
474 | WIR-MECH-456 | 0 |  | Zone: 02 Building: GA-04 | Installation of water supply network with all valves & WHA for Qaha GA-04 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
475 | WIR-MECH-457 | 0 |  | Zone: 02 Building: GA-05 | Installation of water supply network with all valves & WHA for Qaha GA-05 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
476 | WIR-MECH-458 | 0 |  | Zone: 02 Building: GA-06 | Installation of water supply network with all valves & WHA for Qaha GA-06 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
477 | WIR-MECH-459 | 0 |  | Zone: 02 Building: GA-07 | Installation of water supply network with all valves & WHA for Qaha GA-07 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
478 | WIR-MECH-460 | 0 |  | Zone: 02 Building: GA-08 | Installation of water supply network with all valves & WHA for Qaha GA-08 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
479 | WIR-MECH-461 | 0 |  | Zone: 02 Building: GA-09 | Installation of water supply network with all valves & WHA for Qaha GA-09 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
480 | WIR-MECH-462 | 0 |  | Zone: 02 Building: GA-10 | Installation of water supply network with all valves & WHA for Qaha GA-10 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
481 | WIR-MECH-463 | 0 |  | Zone: 02 Building: GA-11 | Installation of water supply network with all valves & WHA for Qaha GA-11 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
482 | WIR-MECH-464 | 0 |  | Zone: 04 Building: Kiosk-01 | Installation of water supply network with all valves & WHA for Qaha Kiosk-01 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
483 | WIR-MECH-465 | 0 |  | Zone: 04 Building: Kiosk-02 | Installation of water supply network with all valves & WHA for Qaha Kiosk-02 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
484 | WIR-MECH-466 | 0 |  | Zone: 03 Building: Kiosk-03 | Installation of water supply network with all valves & WHA for Qaha Kiosk-03 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
485 | WIR-MECH-467 | 0 |  | Zone: 03 Building: Kiosk-04 | Installation of water supply network with all valves of WHA for Qaha Kiosk-04 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
486 | WIR-MECH-468 | 0 |  | Zone: 02 Building: Kiosk-05 | Installation of water supply network with all valves & WHA for Qaha Kiosk-05 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
487 | WIR-MECH-469 | 0 |  | Zone: 02 Building: Kiosk-06 | Installation of water supply network with all valves & WHA for Qaha Kiosk-06 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
488 | WIR-MECH-470 | 0 |  | Zone: 02 Building: Kiosk-07 | Installation of water supply network with all valves & WHA for Qaha Kiosk-07 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
489 | WIR-MECH-471 | 0 |  | Zone: 02 Building: Kiosk-08 | Installation of water supply network with all valves & WHA for Qaha Kiosk-08 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
490 | WIR-MECH-472 | 0 |  | Zone: 02 Building: Kiosk-09 | Installation of water supply network with all valves & WHA for Qaha Kiosk-09 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
491 | WIR-MECH-473 | 0 |  | Zone: 02 Building: Kiosk-10 | Installation of water supply network with all valves & WHA for Qaha Kiosk-10 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
492 | WIR-MECH-474 | 0 |  | Zone: 02 Building: Kiosk-11 | Installation of water supply network with all valves & WHA for Qaha Kiosk-11 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
493 | WIR-MECH-475 | 0 |  | Zone: 02 Building: Kiosk-12 | Installation of water supply network with all valves & WHA for Qaha Kiosk-12 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
494 | WIR-MECH-476 | 0 |  | Zone: 02 Building: Kiosk-17 | Installation of water supply network with all valves & WHA for Qaha Kiosk-17 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
495 | WIR-MECH-477 | 0 |  | Zone: 02 Building: Kiosk-18 | Installation of water supply network with all valves & WHA for Qaha Kiosk-18 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
496 | WIR-MECH-478 | 0 |  | Zone: 02 Building: Kiosk-19 | Installation of water supply network with all valves & WHA for Qaha Kiosk-19 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
497 | WIR-MECH-479 | 0 |  | Zone: 02 Building: Kiosk-20 | Installation of water supply network with all valves & WHA for Qaha Kiosk-20 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
498 | WIR-MECH-480 | 0 |  | Zone: 02 Building: Kiosk-21 | Installation of water supply network with all valves & WHA for Qaha Kiosk-21 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
499 | WIR-MECH-481 | 0 |  | Zone: 02 Building: Kiosk-22 | Installation of water supply network with all valves & WHA for Qaha Kiosk-22 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
500 | WIR-MECH-482 | 0 |  | Zone: 02 Building: Kiosk-23 | Installation of water supply network with all valves & WHA for Qaha Kiosk-23 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
501 | WIR-MECH-483 | 0 |  | Zone: 02 Building: Kiosk-24 | Installation of water supply network with all valves & WHA for Qaha Kiosk-24 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
502 | WIR-MECH-484 | 0 |  | Zone: 02 Building: Kiosk-25 | Installation of water supply network with all valves & WHA for Qaha Kiosk-25 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
503 | WIR-MECH-485 | 0 |  | Zone: 02 Building: Kiosk-30 | Installation of water supply network with all valves & WHA for Qaha Kiosk-30 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
504 | WIR-MECH-486 | 0 |  | Zone: 03 Building: VV-01 | Installation of water supply network with all valves & WHA for Qaha VV-01 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
505 | WIR-MECH-487 | 0 |  | Zone: 04 Building: VS-05 | Installation of water supply network with all valves & WHA for Qaha VS-05 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
506 | WIR-MECH-488 | 0 |  | Zone: 04 Building: WC-01 | Installation of water supply network with all valves & WHA for Qaha WC-01 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
507 | WIR-MECH-489 | 0 |  | Zone: 03 Building: WC-02 | Installation of water supply network with all valves & WHA for Qaha WC-02 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
508 | WIR-MECH-490 | 0 |  | Zone: 02 Building: R05 | Installation of water supply network with all valves & WHA for Qaha gathering R05 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
509 | WIR-MECH-491 | 0 |  | Zone: 04 Building: R03 | Installation of water supply network with all valves & WHA for Qaha VIP lounge-R03 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
510 | WIR-MECH-492 | 0 |  | Zone: 03 Building: R04 | Installation of water supply network with all valves & WHA for Qaha VIP lounge-R04 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
511 | WIR-MECH-493 | 0 |  | Zone: 04 Building: R01 | Installation of water supply network with all valves & WHA for Qaha VIP Reception |  |  |  |  | ur | PENDING | 46114 | 0 | IN
512 | WIR-MECH-494 | 0 |  | Zone: 04 Building: QC-03 | Test for water supply network with all valves, WHA & EWH for Qaha C-03 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
513 | WIR-MECH-495 | 0 |  | Zone: 03 Building: QC-04 | Test for water supply network with all valves, WHA & EWH for Qaha C-04 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
514 | WIR-MECH-496 | 0 |  | Zone: 04 Building: QC-05 | Test for water supply network with all valves, WHA & EWH for Qaha C-05 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
515 | WIR-MECH-497 | 0 |  | Zone: 03 Building: QC-06 | Test for water supply network with all valves, WHA & EWH for Qaha C-06 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
516 | WIR-MECH-498 | 0 |  | Zone: 04 Building: QC-07 | Test for water supply network with all valves, WHA & EWH for Qaha C-07 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
517 | WIR-MECH-499 | 0 |  | Zone: 03 Building: QC-08 | Test for water supply network with all valves, WHA & EWH for Qaha C-08 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
518 | WIR-MECH-500 | 0 |  | Zone: 04 Building: QC-09 | Test for water supply network with all valves, WHA & EWH for Qaha C-09 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
519 | WIR-MECH-501 | 0 |  | Zone: 04 Building: QC-10 | Test for water supply network with all valves, WHA & EWH for Qaha C-10 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
520 | WIR-MECH-502 | 0 |  | Zone: 04 Building: QC-11 | Test for water supply network with all valves, WHA & EWH for Qaha C-11 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
521 | WIR-MECH-503 | 0 |  | Zone: 04 Building: QC-12 | Test for water supply network with all valves, WHA & EWH for Qaha C-12 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
522 | WIR-MECH-504 | 0 |  | Zone: 03 Building: QC-13 | Test for water supply network with all valves, WHA & EWH for Qaha C-13 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
523 | WIR-MECH-505 | 0 |  | Zone: 03 Building: QC-14 | Test for water supply network with all valves, WHA & EWH for Qaha C-14 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
524 | WIR-MECH-506 | 0 |  | Zone: 03 Building: QC-15 | Test for water supply network with all valves, WHA & EWH for Qaha C-15 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
525 | WIR-MECH-507 | 0 |  | Zone: 03 Building: QC-16 | Test for water supply network with all valves, WHA & EWH for Qaha C-16 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
526 | WIR-MECH-508 | 0 |  | Zone: 03 Building: WORK SHOP | Test for water supply network with all valves, WHA & EWH for Work shop |  |  |  |  | ur | PENDING | 46114 | 0 | IN
527 | WIR-MECH-509 | 0 |  | Zone: 04 Building: FA-01 | Test for water supply network with all valves, WHA & EWH for Qaha FA-01 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
528 | WIR-MECH-510 | 0 |  | Zone: 03 Building: FA-02 | Test for water supply network with all valves, WHA & EWH for Qaha FA-02 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
529 | WIR-MECH-511 | 0 |  | Zone: 02 Building: FA-03 | Test for water supply network with all valves, WHA & EWH for Qaha FA-03 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
530 | WIR-MECH-512 | 0 |  | Zone: 02 Building: GA-01 | Test for water supply network with all valves, WHA & EWH for Qaha GA-01 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
531 | WIR-MECH-513 | 0 |  | Zone: 02 Building: GA-02 | Test for water supply network with all valves, WHA & EWH for Qaha GA-02 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
532 | WIR-MECH-514 | 0 |  | Zone: 02 Building: GA-03 | Test for water supply network with all valves, WHA & EWH for Qaha GA-03 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
533 | WIR-MECH-515 | 0 |  | Zone: 02 Building: GA-04 | Test for water supply network with all valves, WHA & EWH for Qaha GA-04 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
534 | WIR-MECH-516 | 0 |  | Zone: 02 Building: GA-05 | Test for water supply network with all valves, WHA & EWH for Qaha GA-05 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
535 | WIR-MECH-517 | 0 |  | Zone: 02 Building: GA-06 | Test for water supply network with all valves, WHA & EWH for Qaha GA-06 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
536 | WIR-MECH-518 | 0 |  | Zone: 02 Building: GA-07 | Test for water supply network with all valves, WHA & EWH for Qaha GA-07 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
537 | WIR-MECH-519 | 0 |  | Zone: 02 Building: GA-08 | Test for water supply network with all valves, WHA & EWH for Qaha GA-08 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
538 | WIR-MECH-520 | 0 |  | Zone: 02 Building: GA-09 | Test for water supply network with all valves, WHA & EWH for Qaha GA-09 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
539 | WIR-MECH-521 | 0 |  | Zone: 02 Building: GA-10 | Test for water supply network with all valves, WHA & EWH for Qaha GA-10 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
540 | WIR-MECH-522 | 0 |  | Zone: 02 Building: GA-11 | Test for water supply network with all valves, WHA & EWH for Qaha GA-11 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
541 | WIR-MECH-523 | 0 |  | Zone: 04 Building: Kiosk-01 | Test for water supply network with all valves, WHA & EWH for Qaha Kiosk-01 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
542 | WIR-MECH-524 | 0 |  | Zone: 04 Building: Kiosk-02 | Test for water supply network with all valves, WHA & EWH for Qaha Kiosk-02 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
543 | WIR-MECH-525 | 0 |  | Zone: 03 Building: Kiosk-03 | Test for water supply network with all valves, WHA & EWH for Qaha Kiosk-03 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
544 | WIR-MECH-526 | 0 |  | Zone: 03 Building: Kiosk-04 | Test for water supply network with all valves, WHA & EWH for Qaha Kiosk-04 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
545 | WIR-MECH-527 | 0 |  | Zone: 02 Building: Kiosk-05 | Test for water supply network with all valves, WHA & EWH for Qaha Kiosk-05 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
546 | WIR-MECH-528 | 0 |  | Zone: 02 Building: Kiosk-06 | Test for water supply network with all valves, WHA & EWH for Qaha Kiosk-06 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
547 | WIR-MECH-529 | 0 |  | Zone: 02 Building: Kiosk-07 | Test for water supply network with all valves, WHA & EWH for Qaha Kiosk-07 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
548 | WIR-MECH-530 | 0 |  | Zone: 02 Building: Kiosk-08 | Test for water supply network with all valves, WHA & EWH for Qaha Kiosk-08 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
549 | WIR-MECH-531 | 0 |  | Zone: 02 Building: Kiosk-09 | Test for water supply network with all valves, WHA & EWH for Qaha Kiosk-09 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
550 | WIR-MECH-532 | 0 |  | Zone: 02 Building: Kiosk-10 | Test for water supply network with all valves, WHA & EWH for Qaha Kiosk-10 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
551 | WIR-MECH-533 | 0 |  | Zone: 02 Building: Kiosk-11 | Test for water supply network with all valves, WHA & EWH for Qaha Kiosk-11 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
552 | WIR-MECH-534 | 0 |  | Zone: 02 Building: Kiosk-12 | Test for water supply network with all valves, WHA & EWH for Qaha Kiosk-12 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
553 | WIR-MECH-535 | 0 |  | Zone: 02 Building: Kiosk-17 | Test for water supply network with all valves, WHA & EWH for Qaha Kiosk-17 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
554 | WIR-MECH-536 | 0 |  | Zone: 02 Building: Kiosk-18 | InsTest for water supply network with all valves, WHA & EWH for Qaha Kiosk-18 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
555 | WIR-MECH-537 | 0 |  | Zone: 02 Building: Kiosk-19 | Test for water supply network with all valves, WHA & EWH for Qaha Kiosk-19 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
556 | WIR-MECH-538 | 0 |  | Zone: 02 Building: Kiosk-20 | Test for water supply network with all valves, WHA & EWH for Qaha Kiosk-20 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
557 | WIR-MECH-539 | 0 |  | Zone: 02 Building: Kiosk-21 | Test for water supply network with all valves, WHA & EWH for Qaha Kiosk-21 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
558 | WIR-MECH-540 | 0 |  | Zone: 02 Building: Kiosk-22 | Test for water supply network with all valves, WHA & EWH for Qaha Kiosk-22 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
559 | WIR-MECH-541 | 0 |  | Zone: 02 Building: Kiosk-23 | Test for water supply network with all valves, WHA & EWH for Qaha Kiosk-23 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
560 | WIR-MECH-542 | 0 |  | Zone: 02 Building: Kiosk-24 | Test for water supply network with all valves, WHA & EWH for Qaha Kiosk-24 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
561 | WIR-MECH-543 | 0 |  | Zone: 02 Building: Kiosk-25 | Test for water supply network with all valves, WHA & EWH for Qaha Kiosk-25 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
562 | WIR-MECH-544 | 0 |  | Zone: 02 Building: Kiosk-30 | Test for water supply network with all valves, WHA & EWH for Qaha Kiosk-30 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
563 | WIR-MECH-545 | 0 |  | Zone: 04 | Test for water supply network with all valves, WHA & EWH for Qaha VS-01/VS-02 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
564 | WIR-MECH-546 | 0 |  | Zone: 04 | Test for water supply network with all valves, WHA & EWH for Qaha VS-03/VS-04 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
565 | WIR-MECH-547 | 0 |  | Zone: 04 | Test for water supply network with all valves, WHA & EWH for Qaha VS-06/VS-07 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
566 | WIR-MECH-548 | 0 |  | Zone: 04 | Test for water supply network with all valves, WHA & EWH for Qaha VS-08/VS-09 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
567 | WIR-MECH-549 | 0 |  | Zone: 03 | Test for water supply network with all valves, WHA & EWH for Qaha VS-10/VS11 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
568 | WIR-MECH-550 | 0 |  | Zone: 03 | Test for water supply network with all valves, WHA & EWH for Qaha VS-12/VS13 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
569 | WIR-MECH-551 | 0 |  | Zone: 03 | Installation of water supply network with all valves & WHA for Qaha VS-14/VS-15 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
570 | WIR-MECH-552 | 0 |  | Zone: 03 | Test for water supply network with all valves, WHA & EWH for Qaha VS-16/VS-17 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
571 | WIR-MECH-553 | 0 |  | Zone: 04 Building: VF-01 | Test for water supply network with all valves, WHA & EWH for Qaha VF-01 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
572 | WIR-MECH-554 | 0 |  | Zone: 04 Building: VF-02 | Test for water supply network with all valves, WHA & EWH for Qaha VF-02 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
573 | WIR-MECH-555 | 0 |  | Zone: 04 Building: VF-03 | Test for water supply network with all valves, WHA & EWH for Qaha VF-03 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
574 | WIR-MECH-556 | 0 |  | Zone: 04 Building: VF-04 | Test for water supply network with all valves, WHA & EWH for Qaha VF-04 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
575 | WIR-MECH-557 | 0 |  | Zone: 04 Building: VF-05 | Test for water supply network with all valves, WHA & EWH for Qaha VF-05 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
576 | WIR-MECH-558 | 0 |  | Zone: 03 Building: VF-06 | Installation of water supply network with all valves & WHA for Qaha VF-06 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
577 | WIR-MECH-559 | 0 |  | Zone: 03 Building: VF-07 | Test for water supply network with all valves, WHA & EWH for Qaha VF-07 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
578 | WIR-MECH-560 | 0 |  | Zone: 03 Building: VF-08 | Test for water supply network with all valves, WHA & EWH for Qaha VF-08 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
579 | WIR-MECH-561 | 0 |  | Zone: 03 Building: VF-09 | Test for water supply network with all valves, WHA & EWH for Qaha VF-09 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
580 | WIR-MECH-562 | 0 |  | Zone: 03 Building: VF-10 | Test for water supply network with all valves, WHA & EWH for Qaha VF-10 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
581 | WIR-MECH-563 | 0 |  | Zone: 03 Building: VV-01 | Test for water supply network with all valves, WHA & EWH for Qaha VV-01 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
582 | WIR-MECH-564 | 0 |  | Zone: 04 Building: VS-05 | Test for water supply network with all valves, WHA & EWH for Qaha VS-05 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
583 | WIR-MECH-565 | 0 |  | Zone: 04 Building: WC-01 | Test for water supply network with all valves, WHA & EWH for Qaha WC-01 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
584 | WIR-MECH-566 | 0 |  | Zone: 03 Building: WC-02 | Test for water supply network with all valves, WHA & EWH for Qaha WC-02 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
585 | WIR-MECH-567 | 0 |  | Zone: 02 Building: R05 | Test for water supply network with all valves, WHA & EWH for Qaha gathering R05 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
586 | WIR-MECH-568 | 0 |  | Zone: 04 Building: R03 | Test for water supply network with all valves, WHA & EWH for Qaha VIP lounge-R03 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
587 | WIR-MECH-569 | 0 |  | Zone: 03 Building: R04 | Test for water supply network with all valves, WHA & EWH for Qaha VIP lounge-R04 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
588 | WIR-MECH-570 | 0 |  | Zone: 04 Building: R01 | Test for water supply network with all valves, WHA & EWH for Qaha VIP Reception |  |  |  |  | ur | PENDING | 46114 | 0 | IN
589 | WIR-MECH-571 | 0 |  | Zone: all Building: all site | Installation of all FHC @ all site |  |  |  |  | ur | PENDING | 46114 | 0 | IN
590 | WIR-MECH-572 | 0 |  | Zone: 02 Building: GA-01 | Installation of firefighting network with ZCV & Sprinklers for Qaha GA-01 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
591 | WIR-MECH-573 | 0 |  | Zone: 02 Building: GA-02 | Installation of firefighting network with ZCV & Sprinklers for Qaha GA-02 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
592 | WIR-MECH-574 | 0 |  | Zone: 02 Building: GA-03 | Installation of firefighting network with ZCV & Sprinklers for Qaha GA-03 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
593 | WIR-MECH-575 | 0 |  | Zone: 02 Building: GA-04 | Installation of firefighting network with ZCV & Sprinklers for Qaha GA-04 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
594 | WIR-MECH-576 | 0 |  | Zone: 02 Building: GA-05 | Installation of firefighting network with ZCV & Sprinklers for Qaha GA-05 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
595 | WIR-MECH-577 | 0 |  | Zone: 02 Building: GA-06 | Installation of firefighting network with ZCV & Sprinklers for Qaha GA-06 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
596 | WIR-MECH-578 | 0 |  | Zone: 02 Building: GA-07 | Installation of firefighting network with ZCV & Sprinklers for Qaha GA-07 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
597 | WIR-MECH-579 | 0 |  | Zone: 02 Building: GA-08 | Installation of firefighting network with ZCV & Sprinklers for Qaha GA-08 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
598 | WIR-MECH-580 | 0 |  | Zone: 02 Building: GA-09 | Installation of firefighting network with ZCV & Sprinklers for Qaha GA-09 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
599 | WIR-MECH-581 | 0 |  | Zone: 02 Building: GA-10 | Installation of firefighting network with ZCV & Sprinklers for Qaha GA-10 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
600 | WIR-MECH-582 | 0 |  | Zone: 02 Building: GA-11 | Installation of firefighting network with ZCV & Sprinklers for Qaha GA-11 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
601 | WIR-MECH-583 | 0 |  | Zone: 03 Building: VV-01 | Installation of firefighting network with ZCV & Sprinklers for Qaha VV-01 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
602 | WIR-MECH-584 | 0 |  | Zone: 04 | Installation of firefighting network with ZCV & Sprinklers for Qaha VS-01/VS-02 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
603 | WIR-MECH-585 | 0 |  | Zone: 04 | Installation of firefighting network with ZCV & Sprinklers for Qaha VS-03/VS-04 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
604 | WIR-MECH-586 | 0 |  | Zone: 04 Building: VS-05 | Installation of firefighting network with ZCV & Sprinklers for Qaha VS-05 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
605 | WIR-MECH-587 | 0 |  | Zone: 04 | Installation of firefighting network with ZCV & Sprinklers for Qaha VS-06/VS-07 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
606 | WIR-MECH-588 | 0 |  | Zone: 04 | Installation of firefighting network with ZCV & Sprinklers for Qaha VS-08/VS-09 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
607 | WIR-MECH-589 | 0 |  | Zone: 03 | Installation of firefighting network with ZCV & Sprinklers for Qaha VS-10/VS-11 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
608 | WIR-MECH-590 | 0 |  | Zone: 03 Building: VS-12-VS-13 | Installation of firefighting network with ZCV & Sprinklers for Qaha VS12-VS-13 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
609 | WIR-MECH-591 | 0 |  | Zone: 03 | Installation of firefighting network with ZCV & Sprinklers for Qaha VS-14/VS-15 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
610 | WIR-MECH-592 | 0 |  | Zone: 03 | Installation of firefighting network with ZCV & Sprinklers for Qaha VS-16/VS-17 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
611 | WIR-MECH-593 | 0 |  | Zone: 04 Building: VF-01 | Installation of firefighting network with ZCV & Sprinklers for Qaha VF-01 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
612 | WIR-MECH-594 | 0 |  | Zone: 04 Building: VF-02 | Installation of firefighting network with ZCV & Sprinklers for Qaha VF-02 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
613 | WIR-MECH-595 | 0 |  | Zone: 04 Building: VF-03 | Installation of firefighting network with ZCV & Sprinklers for Qaha VF-03 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
614 | WIR-MECH-596 | 0 |  | Zone: 04 Building: VF-04 | Installation of firefighting network with ZCV & Sprinklers for Qaha VF-04 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
615 | WIR-MECH-597 | 0 |  | Zone: 04 Building: VF-05 | Installation of firefighting network with ZCV & Sprinklers for Qaha VF-05 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
616 | WIR-MECH-598 | 0 |  | Zone: 03 Building: VF-06 | Installation of firefighting network with ZCV & Sprinklers for Qaha VF-06 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
617 | WIR-MECH-599 | 0 |  | Zone: 03 Building: VF-07 | Installation of firefighting network with ZCV & Sprinklers for Qaha VF-07 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
618 | WIR-MECH-600 | 0 |  | Zone: 03 Building: VF-08 | Installation of firefighting network with ZCV & Sprinklers for Qaha VF-08 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
619 | WIR-MECH-601 | 0 |  | Zone: 03 Building: VF-09 | Installation of firefighting network with ZCV & Sprinklers for Qaha VF-09 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
620 | WIR-MECH-602 | 0 |  | Zone: 03 Building: VF-10 | Installation of firefighting network with ZCV & Sprinklers for Qaha VF-10 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
621 | WIR-MECH-603 | 0 |  | Zone: all Building: all site | TEST of all FHC @ all site |  |  |  |  | ur | PENDING | 46114 | 0 | IN
622 | WIR-MECH-604 | 0 |  | Zone: 02 Building: GA-01 | TEST of firefighting network with ZCV & Sprinklers for Qaha GA-01 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
623 | WIR-MECH-605 | 0 |  | Zone: 02 Building: GA-02 | TEST of firefighting network with ZCV & Sprinklers for Qaha GA-02 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
624 | WIR-MECH-606 | 0 |  | Zone: 02 Building: GA-03 | TEST of firefighting network with ZCV & Sprinklers for Qaha GA-03 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
625 | WIR-MECH-607 | 0 |  | Zone: 02 Building: GA-04 | TEST of firefighting network with ZCV & Sprinklers for Qaha GA-04 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
626 | WIR-MECH-608 | 0 |  | Zone: 02 Building: GA-05 | TEST of firefighting network with ZCV & Sprinklers for Qaha GA-05 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
627 | WIR-MECH-609 | 0 |  | Zone: 02 Building: GA-06 | TEST of firefighting network with ZCV & Sprinklers for Qaha GA-06 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
628 | WIR-MECH-610 | 0 |  | Zone: 02 Building: GA-07 | TEST of firefighting network with ZCV & Sprinklers for Qaha GA-07 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
629 | WIR-MECH-611 | 0 |  | Zone: 02 Building: GA-08 | TEST of firefighting network with ZCV & Sprinklers for Qaha GA-08 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
630 | WIR-MECH-612 | 0 |  | Zone: 02 Building: GA-09 | TEST of firefighting network with ZCV & Sprinklers for Qaha GA-09 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
631 | WIR-MECH-613 | 0 |  | Zone: 02 Building: GA-10 | TEST of firefighting network with ZCV & Sprinklers for Qaha GA-10 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
632 | WIR-MECH-614 | 0 |  | Zone: 02 Building: GA-11 | TEST of firefighting network with ZCV & Sprinklers for Qaha GA-11 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
633 | WIR-MECH-615 | 0 |  | Zone: 03 Building: VV-01 | TEST of firefighting network with ZCV & Sprinklers for Qaha VV-01 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
634 | WIR-MECH-616 | 0 |  | Zone: 04 | TEST of firefighting network with ZCV & Sprinklers for Qaha VS-01/VS-02 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
635 | WIR-MECH-617 | 0 |  | Zone: 04 | TEST of firefighting network with ZCV & Sprinklers for Qaha VS-03/VS-04 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
636 | WIR-MECH-618 | 0 |  | Zone: 04 Building: VS-05 | TEST of firefighting network with ZCV & Sprinklers for Qaha VS-05 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
637 | WIR-MECH-619 | 0 |  | Zone: 04 | TEST of firefighting network with ZCV & Sprinklers for Qaha VS-06/VS-07 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
638 | WIR-MECH-620 | 0 |  | Zone: 04 | TEST of firefighting network with ZCV & Sprinklers for Qaha VS-08/VS-09 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
639 | WIR-MECH-621 | 0 |  | Zone: 03 | TEST of firefighting network with ZCV & Sprinklers for Qaha VS-10/VS-11 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
640 | WIR-MECH-622 | 0 |  | Zone: 03 Building: VS-12-VS-13 | TEST of firefighting network with ZCV & Sprinklers for Qaha VS12-VS-13 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
641 | WIR-MECH-623 | 0 |  | Zone: 03 | TEST of firefighting network with ZCV & Sprinklers for Qaha VS-14/VS-15 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
642 | WIR-MECH-624 | 0 |  | Zone: 03 | TEST of firefighting network with ZCV & Sprinklers for Qaha VS-16/VS-17 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
643 | WIR-MECH-625 | 0 |  | Zone: 04 Building: VF-01 | TEST of firefighting network with ZCV & Sprinklers for Qaha VF-01 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
644 | WIR-MECH-626 | 0 |  | Zone: 04 Building: VF-02 | TEST of firefighting network with ZCV & Sprinklers for Qaha VF-02 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
645 | WIR-MECH-627 | 0 |  | Zone: 04 Building: VF-03 | TEST of firefighting network with ZCV & Sprinklers for Qaha VF-03 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
646 | WIR-MECH-628 | 0 |  | Zone: 04 Building: VF-04 | TEST of firefighting network with ZCV & Sprinklers for Qaha VF-04 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
647 | WIR-MECH-629 | 0 |  | Zone: 04 Building: VF-05 | TEST of firefighting network with ZCV & Sprinklers for Qaha VF-05 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
648 | WIR-MECH-630 | 0 |  | Zone: 03 Building: VF-06 | TEST of firefighting network with ZCV & Sprinklers for Qaha VF-06 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
649 | WIR-MECH-631 | 0 |  | Zone: 03 Building: VF-07 | TEST of firefighting network with ZCV & Sprinklers for Qaha VF-07 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
650 | WIR-MECH-632 | 0 |  | Zone: 03 Building: VF-08 | TEST of firefighting network with ZCV & Sprinklers for Qaha VF-08 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
651 | WIR-MECH-633 | 0 |  | Zone: 03 Building: VF-09 | TEST of firefighting network with ZCV & Sprinklers for Qaha VF-09 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
652 | WIR-MECH-634 | 0 |  | Zone: 03 Building: VF-10 | TEST of firefighting network with ZCV & Sprinklers for Qaha VF-10 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
653 | WIR-MECH-635 | 0 |  | Zone: 02 Building: R-05 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, and all accessories for Qaha R-05 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
654 | WIR-MECH-636 | 0 |  | Zone: 02 Building: GA-01 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, shower Mixers and all bath rooms accessories for Qaha GA-01 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
655 | WIR-MECH-637 | 0 |  | Zone: 02 Building: GA-02 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, shower Mixers and all bath rooms accessories for Qaha GA-02 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
656 | WIR-MECH-638 | 0 |  | Zone: 02 Building: GA-03 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, shower Mixers and all bath rooms accessories for Qaha GA-03 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
657 | WIR-MECH-639 | 0 |  | Zone: 02 Building: GA-04 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, shower Mixers and all bath rooms accessories for Qaha GA-04 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
658 | WIR-MECH-640 | 0 |  | Zone: 02 Building: GA-05 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, shower Mixers and all bath rooms accessories for Qaha GA-05 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
659 | WIR-MECH-641 | 0 |  | Zone: 02 Building: GA-06 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, shower Mixers and all bath rooms accessories for Qaha GA-06 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
660 | WIR-MECH-642 | 0 |  | Zone: 02 Building: GA-07 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, shower Mixers and all bath rooms accessories for Qaha GA-07 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
661 | WIR-MECH-643 | 0 |  | Zone: 02 Building: GA-08 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, shower Mixers and all bath rooms accessories for Qaha GA-08 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
662 | WIR-MECH-644 | 0 |  | Zone: 02 Building: GA-09 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, shower Mixers and all bath rooms accessories for Qaha GA-09 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
663 | WIR-MECH-645 | 0 |  | Zone: 02 Building: GA-10 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, shower Mixers and all bath rooms accessories for Qaha GA-10 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
664 | WIR-MECH-646 | 0 |  | Zone: 02 Building: GA-11 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, shower Mixers and all bath rooms accessories for Qaha GA-11 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
665 | WIR-MECH-647 | 0 |  | Building: PR-04 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, and all accessories for Qaha PR-01 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
666 | WIR-MECH-648 | 0 |  | Zone: 03 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, and all accessories for Qaha WC-01/WC-02 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
667 | WIR-MECH-649 | 0 |  | Zone: 03 Building: VV-01 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, shower Mixers and all bath rooms accessories for Qaha VV-01 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
668 | WIR-MECH-650 | 0 |  | Zone: 04 | Installation and test for all sanitary fixtures Mixers, WC, LAVs etc. for for Qaha VS-01/VS-02 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
669 | WIR-MECH-651 | 0 |  | Zone: 04 | Installation and test for all sanitary fixtures Mixers, WC, LAVs etc. for for Qaha VS-03/VS-04 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
670 | WIR-MECH-652 | 0 |  | Zone: 04 Building: VS-05 | Installation and test for all sanitary fixtures Mixers, WC, LAVs etc. for for Qaha VS-05 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
671 | WIR-MECH-653 | 0 |  | Zone: 04 | Installation and test for all sanitary fixtures Mixers, WC, LAVs etc. for for Qaha VS-06/VS-07 |  |  |  |  | ur | PENDING | #REF! | 0 | IN
672 | WIR-MECH-654 | 0 |  | Zone: 04 | Installation and test for all sanitary fixtures Mixers, WC, LAVs etc. for for Qaha VS-08/VS-09 |  |  |  |  | ur | PENDING | 46114 | 0 | IN
673 | WIR-MECH-655 | 0 |  | Zone: 03 | Installation and test for all sanitary fixtures Mixers, WC, LAVs etc. for for Qaha VS-10/VS-11 |  |  |  |  | ur | PENDING
674 | WIR-MECH-656 | 0 |  | Zone: 03 Building: VS-12-VS-13 | Installation and test for all sanitary fixtures Mixers, WC, LAVs etc. for for Qaha VS12-VS-13 |  |  |  |  | ur | PENDING
675 | WIR-MECH-657 | 0 |  | Zone: 03 | Installation and test for all sanitary fixtures Mixers, WC, LAVs etc. for for Qaha VS-14/VS-15 |  |  |  |  | ur | PENDING
676 | WIR-MECH-658 | 0 |  | Zone: 03 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, shower Mixers and all bath rooms accessories for Qaha VS-16/VS-17 |  |  |  |  | ur | PENDING
677 | WIR-MECH-659 | 0 |  | Zone: 04 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, shower Mixers and all bath rooms accessories for Qaha VS-01/VS-02 |  |  |  |  | ur | PENDING
678 | WIR-MECH-660 | 0 |  | Zone: 04 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, shower Mixers and all bath rooms accessories for Qaha VS-03/VS-04 |  |  |  |  | ur | PENDING
679 | WIR-MECH-661 | 0 |  | Zone: 04 Building: VS-05 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, shower Mixers and all bath rooms accessories for Qaha VS-05 |  |  |  |  | ur | PENDING
680 | WIR-MECH-662 | 0 |  | Zone: 04 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, shower Mixers and all bath rooms accessories for Qaha VS-06/VS-07 |  |  |  |  | ur | PENDING
681 | WIR-MECH-663 | 0 |  | Zone: 04 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, shower Mixers and all bath rooms accessories for Qaha VS-08/VS-09 |  |  |  |  | ur | PENDING
682 | WIR-MECH-664 | 0 |  | Zone: 03 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, shower Mixers and all bath rooms accessories for Qaha VS-10/VS-11 |  |  |  |  | ur | PENDING
683 | WIR-MECH-665 | 0 |  | Zone: 03 Building: VS-12-VS-13 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, shower Mixers and all bath rooms accessories for Qaha VS12-VS-13 |  |  |  |  | ur | PENDING
684 | WIR-MECH-666 | 0 |  | Zone: 03 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, shower Mixers and all bath rooms accessories for Qaha VS-14/VS-15 |  |  |  |  | ur | PENDING
685 | WIR-MECH-667 | 0 |  | Zone: 04 Building: R-01 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, and all accessories for Qaha R-01 |  |  |  |  | ur | PENDING
686 | WIR-MECH-668 | 0 |  | Zone: 04 Building: VF-01 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, shower Mixers and all bath rooms accessories for for Qaha VF-01 |  |  |  |  | ur | PENDING
687 | WIR-MECH-669 | 0 |  | Zone: 04 Building: VF-02 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, shower Mixers and all bath rooms accessories for Qaha VF-02 |  |  |  |  | ur | PENDING
688 | WIR-MECH-670 | 0 |  | Zone: 04 Building: VF-03 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, shower Mixers and all bath rooms accessories for Qaha VF-03 |  |  |  |  | ur | PENDING
689 | WIR-MECH-671 | 0 |  | Zone: 04 Building: VF-04 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, shower Mixers and all bath rooms accessories for Qaha VF-04 |  |  |  |  | ur | PENDING
690 | WIR-MECH-672 | 0 |  | Zone: 04 Building: VF-05 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, shower Mixers and all bath rooms accessories for Qaha VF-05 |  |  |  |  | ur | PENDING
691 | WIR-MECH-673 | 0 |  | Zone: 03 Building: VF-06 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, shower Mixers and all bath rooms accessories for Qaha VF-06 |  |  |  |  | ur | PENDING
692 | WIR-MECH-674 | 0 |  | Zone: 03 Building: VF-07 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, shower Mixers and all bath rooms accessories for Qaha VF-07 |  |  |  |  | ur | PENDING
693 | WIR-MECH-675 | 0 |  | Zone: 03 Building: VF-08 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, shower Mixers and all bath rooms accessories for Qaha VF-08 |  |  |  |  | ur | PENDING
694 | WIR-MECH-676 | 0 |  | Zone: 03 Building: VF-09 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, shower Mixers and all bath rooms accessories for Qaha VF-09 |  |  |  |  | ur | PENDING
695 | WIR-MECH-677 | 0 |  | Zone: 03 Building: VF-10 | Installation and test for all sanitary fixtures Mixers, WC, LAVs, shower Mixers and all bath rooms accessories for Qaha VF-10 |  |  |  |  | ur | PENDING
696 | WIR-MECH-678 | 0 |  | Zone: 03 Building: E-04 | Installation and test for all sanitary fixtures Mixers, LAVs for Qaha E-04 |  |  |  |  | ur | PENDING
697 | WIR-MECH-679 |  |  | Zone: 03 Building: PR01 | Installation and Test of water supply network with all valves&WHA and EWH for Qaha PR01 |  |  |  |  | ur | PENDING
698 | WIR-MECH-680 |  |  | Zone: 03 Building: PR01 | Installation and test for drainage pipes in walls with house connection for Qaha PR01. |  |  |  |  | ur | PENDING
699 | WIR-MECH-681 |  |  | Zone: 03 Building: PR01 | Installation and test of water supply network with all valves&WHA and EWH for Qaha E01 |  |  |  |  | ur | PENDING
700 | WIR-MECH-682 |  |  | Zone: 03 Building: PR01 | Installation and test for drainage pipes in walls with house connection for Qaha E01. |  |  |  |  | ur | PENDING
701 | WIR-MECH-683 |  |  | Zone: 03 Building: LIBRARY | Installation of fire extinguisher for LIBRARY |  |  |  |  | ur | PENDING
702 | WIR-MECH-684 |  |  | Zone: 04 Building: QC-03 | Installation of fire extinguisher for Qaha C-03 |  |  |  |  | ur | PENDING
703 | WIR-MECH-685 |  |  | Zone: 03 Building: QC-04 | Installation of fire extinguisher for Qaha C-04 |  |  |  |  | ur | PENDING
704 | WIR-MECH-686 |  |  | Zone: 04 Building: QC-05 | Installation of fire extinguisher for Qaha C-05 |  |  |  |  | ur | PENDING
705 | WIR-MECH-687 |  |  | Zone: 03 Building: QC-06 | Installation of fire extinguisher for Qaha C-06 |  |  |  |  | ur | PENDING
706 | WIR-MECH-688 |  |  | Zone: 04 Building: QC-07 | Installation of fire extinguisher for Qaha C-07 |  |  |  |  | ur | PENDING
707 | WIR-MECH-689 |  |  | Zone: 03 Building: QC-08 | Installation of fire extinguisher for Qaha C-08 |  |  |  |  | ur | PENDING
708 | WIR-MECH-690 |  |  | Zone: 04 Building: QC-09 | Installation of fire extinguisher for Qaha C-09 |  |  |  |  | ur | PENDING
709 | WIR-MECH-691 |  |  | Zone: 04 Building: QC-10 | Installation of fire extinguisher for Qaha C-10 |  |  |  |  | ur | PENDING
710 | WIR-MECH-692 |  |  | Zone: 04 Building: QC-11 | Installation of fire extinguisher for Qaha C-11 |  |  |  |  | ur | PENDING
711 | WIR-MECH-693 |  |  | Zone: 04 Building: QC-12 | Installation of fire extinguisher for Qaha C-12 |  |  |  |  | ur | PENDING
712 | WIR-MECH-694 |  |  | Zone: 03 Building: QC-13 | Installation of fire extinguisher for Qaha C-13 |  |  |  |  | ur | PENDING
713 | WIR-MECH-695 |  |  | Zone: 03 Building: QC-14 | Installation of fire extinguisher for Qaha C-14 |  |  |  |  | ur | PENDING
714 | WIR-MECH-696 |  |  | Zone: 03 Building: QC-15 | Installation of fire extinguisher for Qaha C-15 |  |  |  |  | ur | PENDING
715 | WIR-MECH-697 |  |  | Zone: 03 Building: QC-16 | Installation of fire extinguisher for Qaha C-16 |  |  |  |  | ur | PENDING
716 | WIR-MECH-698 |  |  | Zone: 04 Building: FA-01 | Installation of fire extinguisher for Qaha FA-01 |  |  |  |  | ur | PENDING
717 | WIR-MECH-699 |  |  | Zone: 03 Building: FA-02 | Installation of fire extinguisher for Qaha FA-02 |  |  |  |  | ur | PENDING
718 | WIR-MECH-700 |  |  | Zone: 02 Building: FA-03 | Installation of fire extinguisher for Qaha FA-03 |  |  |  |  | ur | PENDING
719 | WIR-MECH-701 |  |  | Zone: 04 Building: Kiosk-01 | Installation of fire extinguisher for Qaha Kiosk-01 |  |  |  |  | ur | PENDING
720 | WIR-MECH-702 |  |  | Zone: 04 Building: Kiosk-02 | Installation of fire extinguisher for Qaha Kiosk-02 |  |  |  |  | ur | PENDING
721 | WIR-MECH-703 |  |  | Zone: 03 Building: Kiosk-03 | Installation of fire extinguisher for Qaha Kiosk-03 |  |  |  |  | ur | PENDING
722 | WIR-MECH-704 |  |  | Zone: 03 Building: Kiosk-04 | Installation of fire extinguisher for Qaha Kiosk-04 |  |  |  |  | ur | PENDING
723 | WIR-MECH-705 |  |  | Zone: 02 Building: Kiosk-05 | Installation of fire extinguisher for Qaha Kiosk-05 |  |  |  |  | ur | PENDING
724 | WIR-MECH-706 |  |  | Zone: 02 Building: Kiosk-06 | Installation of fire extinguisher for Qaha Kiosk-06 |  |  |  |  | ur | PENDING
725 | WIR-MECH-707 |  |  | Zone: 02 Building: Kiosk-07 | Installation of fire extinguisher for Qaha Kiosk-07 |  |  |  |  | ur | PENDING
726 | WIR-MECH-708 |  |  | Zone: 02 Building: Kiosk-08 | Installation of fire extinguisher for Qaha Kiosk-08 |  |  |  |  | ur | PENDING
727 | WIR-MECH-709 |  |  | Zone: 02 Building: Kiosk-09 | Installation of fire extinguisher for Qaha Kiosk-09 |  |  |  |  | ur | PENDING
728 | WIR-MECH-710 |  |  | Zone: 02 Building: Kiosk-10 | Installation of fire extinguisher for Qaha Kiosk-10 |  |  |  |  | ur | PENDING
729 | WIR-MECH-711 |  |  | Zone: 02 Building: Kiosk-11 | Installation of fire extinguisher for Qaha Kiosk-11 |  |  |  |  | ur | PENDING
730 | WIR-MECH-712 |  |  | Zone: 02 Building: Kiosk-12 | Installation of fire extinguisher for Qaha Kiosk-12 |  |  |  |  | ur | PENDING
731 | WIR-MECH-713 |  |  | Zone: 02 Building: Kiosk-17 | Installation of fire extinguisher for Qaha Kiosk-17 |  |  |  |  | ur | PENDING
732 | WIR-MECH-714 |  |  | Zone: 02 Building: Kiosk-18 | Installation of fire extinguisher for Qaha Kiosk-18 |  |  |  |  | ur | PENDING
733 | WIR-MECH-715 |  |  | Zone: 02 Building: Kiosk-19 | Installation of fire extinguisher for Qaha Kiosk-19 |  |  |  |  | ur | PENDING
734 | WIR-MECH-716 |  |  | Zone: 02 Building: Kiosk-20 | Installation of fire extinguisher Qaha Kiosk-20 |  |  |  |  | ur | PENDING
735 | WIR-MECH-717 |  |  | Zone: 02 Building: Kiosk-21 | Installation of fire extinguisher for Qaha Kiosk-21 |  |  |  |  | ur | PENDING
736 | WIR-MECH-718 |  |  | Zone: 02 Building: Kiosk-22 | Installation of fire extinguisher for Qaha Kiosk-22 |  |  |  |  | ur | PENDING
737 | WIR-MECH-719 |  |  | Zone: 02 Building: Kiosk-23 | Installation of fire extinguisher for Qaha Kiosk-23 |  |  |  |  | ur | PENDING
738 | WIR-MECH-720 |  |  | Zone: 02 Building: Kiosk-24 | Installation of fire extinguisher for Qaha Kiosk-24 |  |  |  |  | ur | PENDING
739 | WIR-MECH-721 |  |  | Zone: 02 Building: Kiosk-25 | Installation of fire extinguisher for Qaha Kiosk-25 |  |  |  |  | ur | PENDING
740 | WIR-MECH-722 |  |  | Zone: 02 Building: Kiosk-30 | Installation of fire extinguisher for Qaha Kiosk-30 |  |  |  |  | ur | PENDING
741 | WIR-MECH-723 |  |  | Zone: 03 Building: PR01 | Installation of fire extinguisher for Qaha MASJID PR01 |  |  |  |  | ur | PENDING
742 | WIR-MECH-724 |  |  | Zone: 04 Building: WC-01 | Installation of fire extinguisher for Qaha WC-01 |  |  |  |  | ur | PENDING
743 | WIR-MECH-725 |  |  | Zone: 03 Building: WC-02 | Installation of fire extinguisher for Qaha WC-02 |  |  |  |  | ur | PENDING
744 | WIR-MECH-726 |  |  | Zone: 04 Building: WILD LIFE | Installation of fire extinguisher for WILD LIFE |  |  |  |  | ur | PENDING
745 | WIR-MECH-727 |  |  | Zone: 03 Building: WORK SHOP | Installation of fire extinguisher for work shop |  |  |  |  | ur | PENDING
746 | WIR-MECH-728 |  |  | Zone: 02 Building: Control Room | Installation of fire extinguisher and FM200 for control room. |  |  |  |  | ur | PENDING
747 | WIR-MECH-729 |  |  | Zone: 03 Building: GATE01 | Installation of fire extinguisher Qaha Gate-01 |  |  |  |  | ur | PENDING
748 | WIR-MECH-730 |  |  | Zone: 02 Building: GATE02 | Installation of fire extinguisher for Qaha Gate-02 |  |  |  |  | ur | PENDING
749 | WIR-MECH-731 |  |  | Zone: 02 Building: R05 | Installation of fire extinguisher for Qaha gathering R05 |  |  |  |  | ur | PENDING
750 | WIR-MECH-732 |  |  | Zone: 04 Building: R03 | Installation of fire extinguisher for Qaha VIP lounge-R03 |  |  |  |  | ur | PENDING
751 | WIR-MECH-733 |  |  | Zone: 03 Building: R04 | Installation of fire extinguisher for Qaha VIP lounge-R04 |  |  |  |  | ur | PENDING
752 | WIR-MECH-734 |  |  | Zone: 04 Building: R01 | Installation of fire extinguisher for Qaha VIP Reception |  |  |  |  | ur | PENDING
753 | WIR-MECH-735 |  |  | Zone: 04 Building: R03 | Installation and test of AC units with copper pipes for Qaha LOUNGE R03. |  |  | 25/3/2026 |  | ur
754 | WIR-MECH-736 |  |  | Zone: 04 Building: R03 | Installation and test of GI Duct with exhaust fan for Qaha VIP lounge-R03 |  |  | 25/3/2026 |  | ur
755 | WIR-MECH-737 |  |  | Zone: 03 Building: R04 | Installation and test of AC units with copper pipes for Qaha LOUNGE R04. |  |  | 25/3/2026 |  | ur
756 | WIR-MECH-738 |  |  | Zone: 03 Building: R04 | Installation and test of GI Duct with exhaust fan for Qaha VIP lounge-R04 |  |  | 25/3/2026 |  | ur
757 | WIR-MECH-739 |  |  | Zone: 04 Building: R01 | Installation and test of AC units with copper pipes for Qaha VIP RECEPTION RO1. |  |  | 25/3/2026 |  | ur
758 | WIR-MECH-740 |  |  | Zone: 04 Building: R01 | Installation and test of GI Duct with exhaust fan for Qaha VIP Reception R01. |  |  | 25/3/2026 |  | ur
759 | WIR-MECH-741 |  |  | Zone: 03 Building: E-04 | Installation and test of AC units with copper pipes for Qaha WORKSHOP E-04. |  |  | 25/3/2026 |  | ur
760 | WIR-MECH-742 |  |  | Zone: 03 Building: E-04 | Installation and test of GI Duct with exhaust fan for Qaha Wild life E04 |  |  | 25/3/2026 |  | ur
761 | WIR-MECH-743 |  |  | Zone: 04 Building: E-01 | Installation and test of AC units with copper pipes for Qaha Wild Life E-01 |  |  | 25/3/2026 |  | ur
762 | WIR-MECH-744 |  |  | Zone: 04 Building: E01 | Installation and test of GI Duct with exhaust fan for Qaha Wild life E01 |  |  | 25/3/2026 |  | ur
763 | WIR-MECH-745 |  |  | Zone: 02 Building: R05 | Installation and test of AC units with copper pipes for Qaha GATHERING R05. |  |  | 25/3/2026 |  | ur
764 | WIR-MECH-746 |  |  | Zone: 02 Building: R05 | Installation and test of GI Duct with exhaust fan & all acessories for Qaha gathering R05. |  |  | 25/3/2026 |  | ur
765 | WIR-MECH-747 |  |  | Zone: 04 Building: PR-01 | Installation and test of AC units with copper pipes for Qaha mosque PR-01 . |  |  | 25/3/2026 |  | ur
766 | WIR-MECH-748 |  |  | Zone: 04 Building: PR-01 | Installation and test of GI Duct with exhaust fan for Qaha MOSQUE PR-01. |  |  | 25/3/2026 |  | ur
767 | WIR-MECH-749 |  |  | Zone: 03 Building: WC01 | Installation and test of AC units with copper pipes for Qaha PUPLIC TOILET WC01. |  |  | 25/3/2026 |  | ur
768 | WIR-MECH-750 |  |  | Zone: 03 Building: WC01 | Installation and test of GI Duct with exhaust fan for Qaha PUPLIC TOILET WC01. |  |  | 25/3/2026 |  | ur
769 | WIR-MECH-751 |  |  | Zone: 04 Building: WC02 | Installation and test of AC units with copper pipes for Qaha PUPLIC TOILET WC02. |  |  | 25/3/2026 |  | ur
770 | WIR-MECH-752 |  |  | Zone: 04 Building: WC02 | Installation and test of GI Duct with exhaust fan for Qaha PUPLIC TOILET WC02. |  |  | 25/3/2026 |  | ur
771 | WIR-MECH-753 |  |  | Zone: 03 Building: QC-18 | Installation and test of AC units with copper pipes for QAHA Library C-18 |  |  | 25/3/2026 |  | ur
Formulas:
Progress = IF([Received Date]="",TODAY()-[Outgoing to Consultant],[Received Date]-[Outgoing to Consultant])
Progress = IF([Received Date]="",TODAY()-[Outgoing to Consultant, row below],[Received Date]-[Outgoing to Consultant, row below])
Duration = IF([Rev]=0,[Outgoing to Consultant]+1,IF([Rev]>0,[Outgoing to Consultant]+1))
Over Duration = IF([Duration]="",0,(IF([Received Date]="",TODAY()-[Duration],IF([Received Date]-[Duration]>0,[Received Date]-[Duration],0))))
Owner Logo
Consultant Logo

## SURV
Inspection Request - SURV | [9 empty] | A | Approved |  | Date: | 2026-04-02
[10 empty] | B | Approved with notes
[10 empty] | C | Reject & Resubmit
[10 empty] | CC | Not Resubmitted
[10 empty] | UR | Under Review
DOCUMENT REFERENCE NO |  |  | Element | Location | DESCRIPTION | Attachment |  | Outgoing to Consultant |  | Code Action | Status | Progress | Over Duration | scan | Duration
No. | Reference | REV |  |  |  | Dwg | Report | Submission date | Received Date
1 | WIR-SURV-001 | 0 | Excavation | Zone: 2 Building: GA-01 | Excavation Level |  |  | 2025-05-11 | 2025-11-16 | C | CLOSED | 11 | 10 | IN | 45789
2 | WIR-SURV-002 | 0 | General | Zone: 2 Building: GA-01 | Plain Concrete (PC) |  |  | 2025-05-11 | 2025-11-16 | C | CLOSED | 11 | 10 | IN | 45789
3 | WIR-SURV-003 | 0 | General | Zone: 2 Building: GA-01 | Reinforced Concrete (RC) |  |  | 2025-05-11 | 2025-11-16 | C | CLOSED | 11 | 10 | IN | 2025-05-12
4 | WIR-SURV-004 | 0 | General | Zone: 2 Building: GA-01 | Columns |  |  | 2025-05-11 | 2025-11-16 | C | CLOSED | 11 | 10 | IN | 2025-05-12
5 | WIR-SURV-005 | 0 | General | Zone: 2 Building: GA-02 | Foundation Level |  |  | 2025-05-11 | 2025-11-16 | C | CLOSED | 11 | 10 | IN | 2025-05-12
6 | WIR-SURV-006 | 0 | General | Zone: 2 Building: GA-02 | Plain Concrete (PC) |  |  | 2025-05-11 | 2025-11-16 | C | CLOSED | 11 | 10 | IN | 2025-05-12
7 | WIR-SURV-007 | 0 | General | Zone: 2 Building: GA-02 | Reinforced Concrete (RC) |  |  | 2025-05-11 | 2025-11-16 | C | CLOSED | 11 | 10 | IN | 2025-05-12
8 | WIR-SURV-008 | 0 | General | Zone: 2 Building: GA-02 | Columns |  |  | 2025-05-11 | 2025-11-16 | C | CLOSED | 11 | 10 | IN | 2025-05-12
9 | WIR-SURV-009 | 0 | General | Zone: 2 Building: GA-03 | Foundation Level |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 45789
10 | WIR-SURV-010 | 0 | General | Zone: 2 Building: GA-03 | Plain Concrete (PC) |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 2025-05-12
11 | WIR-SURV-011 | 0 | General | Zone: 2 Building: GA-03 | Reinforced Concrete (RC) |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 2025-05-12
12 | WIR-SURV-012 | 0 | General | Zone: 2 Building: GA-03 | Columns |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 2025-05-12
13 | WIR-SURV-013 | 0 | General | Zone: 2 Building: GA-04 | Foundation Level |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 2025-05-12
14 | WIR-SURV-014 | 0 | General | Zone: 2 Building: GA-04 | Plain Concrete (PC) |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 2025-05-12
15 | WIR-SURV-015 | 0 | General | Zone: 2 Building: GA-04 | Reinforced Concrete (RC) |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 45789
16 | WIR-SURV-016 | 0 | General | Zone: 2 Building: GA-04 | Columns |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 45789
17 | WIR-SURV-017 | 0 | General | Zone: 2 Building: GA-05 | Foundation Level |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 45789
18 | WIR-SURV-018 | 0 | General | Zone: 2 Building: GA-05 | Plain Concrete (PC) |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 45789
19 | WIR-SURV-019 | 0 | General | Zone: 2 Building: GA-05 | Reinforced Concrete (RC) |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 45789
20 | WIR-SURV-020 | 0 | General | Zone: 2 Building: GA-05 | Columns |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 2025-05-12
21 | WIR-SURV-021 | 0 | General | Zone: 2 Building: GA-06 | Foundation Level |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 2025-05-12
22 | WIR-SURV-022 | 0 | General | Zone: 2 Building: GA-06 | Plain Concrete (PC) |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 2025-05-12
23 | WIR-SURV-023 | 0 | General | Zone: 2 Building: GA-06 | Reinforced Concrete (RC) |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 2025-05-12
24 | WIR-SURV-024 | 0 | General | Zone: 2 Building: GA-06 | Columns |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 2025-05-12
25 | WIR-SURV-025 | 0 | General | Zone: 2 Building: GA-07 | Foundation Level |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 2025-05-12
26 | WIR-SURV-026 | 0 | General | Zone: 2 Building: GA-07 | Plain Concrete (PC) |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 2025-05-12
27 | WIR-SURV-027 | 0 | General | Zone: 2 Building: GA-07 | Reinforced Concrete (RC) |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 2025-05-12
28 | WIR-SURV-028 | 0 | General | Zone: 2 Building: GA-07 | Columns |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 2025-05-12
29 | WIR-SURV-029 | 0 | General | Zone: 2 Building: GA-08 | Foundation Level |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 2025-05-12
30 | WIR-SURV-030 | 0 | General | Zone: 2 Building: GA-08 | Plain Concrete (PC) |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 2025-05-12
31 | WIR-SURV-031 | 0 | General | Zone: 2 Building: GA-08 | Reinforced Concrete (RC) |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 2025-05-12
32 | WIR-SURV-032 | 0 | General | Zone: 2 Building: GA-08 | Columns |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 2025-05-12
33 | WIR-SURV-033 | 0 | General | Zone: 2 Building: GA-09 | Foundation Level |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 2025-05-12
34 | WIR-SURV-034 | 0 | General | Zone: 2 Building: GA-09 | Plain Concrete (PC) |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 2025-05-12
35 | WIR-SURV-035 | 0 | General | Zone: 2 Building: GA-09 | Reinforced Concrete (RC) |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 2025-05-12
36 | WIR-SURV-036 | 0 | General | Zone: 2 Building: GA-09 | Columns |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 2025-05-12
37 | WIR-SURV-037 | 0 | General | Zone: 2 Building: GA-10 | Foundation Level |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 2025-05-12
38 | WIR-SURV-038 | 0 | General | Zone: 2 Building: GA-10 | Plain Concrete (PC) |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 2025-05-12
39 | WIR-SURV-039 | 0 | General | Zone: 2 Building: GA-10 | Reinforced Concrete (RC) |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 2025-05-12
40 | WIR-SURV-040 | 0 | General | Zone: 2 Building: GA-10 | Columns |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 2025-05-12
41 | WIR-SURV-041 | 0 | General | Zone: 2 Building: GA-11 | Foundation Level |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 2025-05-12
42 | WIR-SURV-042 | 0 | General | Zone: 2 Building: GA-11 | Plain Concrete (PC) |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 2025-05-12
43 | WIR-SURV-043 | 0 | General | Zone: 2 Building: GA-11 | Reinforced Concrete (RC) |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 2025-05-12
44 | WIR-SURV-044 | 0 | General | Zone: 2 Building: GA-11 | Columns |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 2025-05-12
45 | WIR-SURV-045 | 0 | Excavation | Zone: 2 Building: Gathering | Excavation Level |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 12 | IN | 2025-05-12
46 | WIR-SURV-046 | 0 | General | Zone: 2 Building: Gathering | Plain Concrete (PC) |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 0 | IN
47 | WIR-SURV-047 | 0 | General | Zone: 2 Building: Gathering | Reinforced Concrete (RC) |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 0 | IN
48 | WIR-SURV-048 | 0 | General | Zone: 2 Building: Gathering | Columns |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 0 | IN
49 | WIR-SURV-049 | 0 | General | Zone: 2 Building: Control Room | Excavation Level |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 0 | IN
50 | WIR-SURV-050 | 0 | General | Zone: 2 Building: Control Room | Plain Concrete (PC) |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 0 | IN
51 | WIR-SURV-051 | 0 | General | Zone: 2 Building: Control Room | Reinforced Concrete (RC) |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 0 | IN
52 | WIR-SURV-052 | 0 | General | Zone: 2 Building: Control Room | Columns |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 0 | IN
53 | WIR-SURV-053 | 0 | General | Zone: 2 Building: Maintance Store | Excavation Level |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 0 | IN
54 | WIR-SURV-054 | 0 | General | Zone: 2 Building: Maintance Store | Plain Concrete (PC) |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 0 | IN
55 | WIR-SURV-055 | 0 | General | Zone: 2 Building: Maintance Store | Reinforced Concrete (RC) |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 0 | IN
56 | WIR-SURV-056 | 0 | General | Zone: 2 Building: Maintance Store | Columns |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 0 | IN
57 | WIR-SURV-057 | 0 | General | Zone: 2 Building: Frist Aid | Excavation Level |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 0 | IN
58 | WIR-SURV-058 | 0 | General | Zone: 2 Building: Frist Aid | Plain Concrete (PC) |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 0 | IN
59 | WIR-SURV-059 | 0 | General | Zone: 2 Building: Frist Aid | Reinforced Concrete (RC) |  |  | 2025-05-11 | 2026-11-18 | C | CLOSED | 13 | 0 | IN
60 | WIR-SURV-060 | 0 | General | Zone: 2 Building: Frist Aid | Columns |  |  | 2025-05-11 | 2026-11-18 | B | CLOSED | 13 | 0 | IN
61 | WIR-SURV-001 | 1 | Excavation | Zone: 2 Building: GA-01 | Excavation Level |  |  | 2025-12-11 | 2026-11-13 | B | CLOSED | 1 | 0 | IN
62 | WIR-SURV-002 | 1 | General | Zone: 2 Building: GA-01 | Plain Concrete (PC) |  |  | 2025-12-11 | 2026-11-13 | B | CLOSED | 1 | 0 | IN
63 | WIR-SURV-003 | 1 | General | Zone: 2 Building: GA-01 | Reinforced Concrete (RC) |  |  | 2025-12-11 | 2026-11-13 | B | CLOSED | 1 | 0 | IN
64 | WIR-SURV-004 | 1 | General | Zone: 2 Building: GA-01 | Columns |  |  | 2025-12-11 | 2026-11-13 | B | CLOSED | 1 | 0 | IN
65 | WIR-SURV-005 | 1 | General | Zone: 2 Building: GA-02 | Foundation Level |  |  | 2025-12-11 | 2026-11-13 | B | CLOSED | 1 | 0 | IN
66 | WIR-SURV-006 | 1 | General | Zone: 2 Building: GA-02 | Plain Concrete (PC) |  |  | 2025-12-11 | 2026-11-13 | B | CLOSED | 1 | 0 | IN
67 | WIR-SURV-007 | 1 | General | Zone: 2 Building: GA-02 | Reinforced Concrete (RC) |  |  | 2025-12-11 | 2026-11-13 | B | CLOSED | 1 | 0 | IN
68 | WIR-SURV-008 | 1 | General | Zone: 2 Building: GA-02 | Columns |  |  | 2025-12-11 | 2026-11-13 | B | CLOSED | 1 | 0 | IN
69 | WIR-SURV-009 | 1 | General | Zone: 2 Building: GA-03 | Foundation Level |  |  | 2025-12-11 | 2026-11-13 | B | CLOSED | 1 | 0 | IN
70 | WIR-SURV-010 | 1 | General | Zone: 2 Building: GA-03 | Plain Concrete (PC) |  |  | 2025-12-11 | 2026-11-13 | B | CLOSED | 1 | 0 | IN
71 | WIR-SURV-011 | 1 | General | Zone: 2 Building: GA-03 | Reinforced Concrete (RC) |  |  | 2025-12-11 | 2026-11-13 | B | CLOSED | 1 | 0 | IN
72 | WIR-SURV-012 | 1 | General | Zone: 2 Building: GA-03 | Columns |  |  | 2025-12-11 | 2026-11-13 | B | CLOSED | 1 | 0 | IN
73 | WIR-SURV-013 | 1 | General | Zone: 2 Building: GA-04 | Foundation Level |  |  | 2025-12-11 | 2026-11-13 | B | CLOSED | 1 | 0 | IN
74 | WIR-SURV-014 | 1 | General | Zone: 2 Building: GA-04 | Plain Concrete (PC) |  |  | 2025-12-11 | 2026-11-13 | B | CLOSED | 1 | 0 | IN
75 | WIR-SURV-015 | 1 | General | Zone: 2 Building: GA-04 | Reinforced Concrete (RC) |  |  | 2025-12-11 | 2026-11-13 | B | CLOSED | 1 | 0 | IN
76 | WIR-SURV-016 | 1 | General | Zone: 2 Building: GA-04 | Columns |  |  | 2025-12-11 | 2026-11-13 | B | CLOSED | 1 | 0 | IN
77 | WIR-SURV-017 | 1 | General | Zone: 2 Building: GA-05 | Foundation Level |  |  | 2025-12-11 | 2026-11-13 | B | CLOSED | 1 | 0 | IN
78 | WIR-SURV-018 | 1 | General | Zone: 2 Building: GA-05 | Plain Concrete (PC) |  |  | 2025-12-11 | 2026-11-13 | B | CLOSED | 1 | 0 | IN
79 | WIR-SURV-019 | 1 | General | Zone: 2 Building: GA-05 | Reinforced Concrete (RC) |  |  | 2025-12-11 | 2026-11-13 | B | CLOSED | 1 | 0 | IN
80 | WIR-SURV-020 | 1 | General | Zone: 2 Building: GA-05 | Columns |  |  | 2025-12-11 | 2026-11-13 | B | CLOSED | 1 | 0 | IN
81 | WIR-SURV-021 | 1 | General | Zone: 2 Building: GA-06 | Foundation Level |  |  | 2025-12-11 | 2026-11-13 | B | CLOSED | 1 | 0 | IN | 2025-12-12
82 | WIR-SURV-022 | 1 | General | Zone: 2 Building: GA-06 | Plain Concrete (PC) |  |  | 2025-12-11 | 2026-11-13 | B | CLOSED | 1 | 0 | IN | 2025-12-12
83 | WIR-SURV-023 | 1 | General | Zone: 2 Building: GA-06 | Reinforced Concrete (RC) |  |  | 2025-12-11 | 2026-11-13 | B | CLOSED | 1 | 0 | IN | 2025-12-12
84 | WIR-SURV-024 | 1 | General | Zone: 2 Building: GA-06 | Columns |  |  | 2025-12-11 | 2026-11-13 | B | CLOSED | 1 | 0 | IN | 2025-12-12
85 | WIR-SURV-025 | 1 | General | Zone: 2 Building: GA-07 | Foundation Level |  |  | 2025-12-11 | 2026-11-13 | B | CLOSED | 1 | 0 | IN | 2025-12-12
86 | WIR-SURV-026 | 1 | General | Zone: 2 Building: GA-07 | Plain Concrete (PC) |  |  | 2025-12-11 | 2026-11-13 | B | CLOSED | 1 | 0 | IN | 2025-12-12
87 | WIR-SURV-027 | 1 | General | Zone: 2 Building: GA-07 | Reinforced Concrete (RC) |  |  | 2025-12-11 | 2026-11-13 | B | CLOSED | 1 | 0 | IN | 2025-12-12
88 | WIR-SURV-028 | 1 | General | Zone: 2 Building: GA-07 | Columns |  |  | 2025-12-11 | 2026-11-13 | B | CLOSED | 1 | 0 | IN | 2025-12-12
89 | WIR-SURV-029 | 1 | General | Zone: 2 Building: GA-08 | Foundation Level |  |  | 2025-12-11 | 2026-11-13 | B | CLOSED | 1 | 0 | IN | 2025-12-12
90 | WIR-SURV-030 | 1 | General | Zone: 2 Building: GA-08 | Plain Concrete (PC) |  |  | 2025-12-11 | 2026-11-13 | B | CLOSED | 1 | 0 | IN | 2025-12-12
91 | WIR-SURV-031 | 1 | General | Zone: 2 Building: GA-08 | Reinforced Concrete (RC) |  |  | 2025-11-17 | 2026-11-18 | B | CLOSED | 1 | 0 | IN | 2025-11-18
92 | WIR-SURV-032 | 1 | General | Zone: 2 Building: GA-08 | Columns |  |  | 2025-11-17 | 2026-11-18 | B | CLOSED | 1 | 0 | IN
93 | WIR-SURV-033 | 1 | General | Zone: 2 Building: GA-09 | Foundation Level |  |  | 2025-11-17 | 2026-11-18 | B | CLOSED | 1 | 0 | IN
94 | WIR-SURV-034 | 1 | General | Zone: 2 Building: GA-09 | Plain Concrete (PC) |  |  | 2025-11-17 | 2026-11-18 | B | CLOSED | 1 | 0 | IN
95 | WIR-SURV-035 | 1 | General | Zone: 2 Building: GA-09 | Reinforced Concrete (RC) |  |  | 2025-11-17 | 2026-11-18 | B | CLOSED | 1 | 0 | IN
96 | WIR-SURV-036 | 1 | General | Zone: 2 Building: GA-09 | Columns |  |  | 2025-11-17 | 2026-11-18 | B | CLOSED | 1 | 0 | IN
97 | WIR-SURV-037 | 1 | General | Zone: 2 Building: GA-10 | Foundation Level |  |  | 2025-11-17 | 2026-11-18 | B | CLOSED | 1 | 0 | IN
98 | WIR-SURV-038 | 1 | General | Zone: 2 Building: GA-10 | Plain Concrete (PC) |  |  | 2025-11-17 | 2026-11-18 | B | CLOSED | 1 | 0 | IN
99 | WIR-SURV-039 | 1 | General | Zone: 2 Building: GA-10 | Reinforced Concrete (RC) |  |  | 2025-11-17 | 2026-11-18 | B | CLOSED | 1 | 0 | IN
100 | WIR-SURV-040 | 1 | General | Zone: 2 Building: GA-10 | Columns |  |  | 2025-11-17 | 2026-11-18 | B | CLOSED | 1 | 0 | IN
101 | WIR-SURV-041 | 1 | General | Zone: 2 Building: GA-11 | Foundation Level |  |  | 2025-11-17 | 2026-11-18 | B | CLOSED | 1 | 0 | IN
102 | WIR-SURV-042 | 1 | General | Zone: 2 Building: GA-11 | Plain Concrete (PC) |  |  | 2025-11-17 | 2026-11-18 | B | CLOSED | 1 | 0 | IN
103 | WIR-SURV-043 | 1 | General | Zone: 2 Building: GA-11 | Reinforced Concrete (RC) |  |  | 2025-11-17 | 2026-11-18 | B | CLOSED | 1 | 0 | IN
104 | WIR-SURV-044 | 1 | General | Zone: 2 Building: GA-11 | Columns |  |  | 2025-11-17 | 2026-11-18 | B | CLOSED | 1 | 0 | IN
105 | WIR-SURV-045 | 1 | Excavation | Zone: 2 Building: Gathering | Excavation Level |  |  | 2025-11-17 | 2026-11-18 | B | CLOSED | 1 | 0 | IN
106 | WIR-SURV-046 | 1 | General | Zone: 2 Building: Gathering | Plain Concrete (PC) |  |  | 2025-11-17 | 2026-11-18 | B | CLOSED | 1 | 0 | IN
107 | WIR-SURV-047 | 1 | General | Zone: 2 Building: Gathering | Reinforced Concrete (RC) |  |  | 2025-11-17 | 2026-11-18 | B | CLOSED | 1 | 0 | IN
108 | WIR-SURV-048 | 1 | General | Zone: 2 Building: Gathering | Columns |  |  | 2025-11-17 | 2026-11-18 | B | CLOSED | 1 | 0 | IN
109 | WIR-SURV-049 | 1 | General | Zone: 2 Building: Control Room | Excavation Level |  |  | 2025-11-17 | 2026-11-18 | B | CLOSED | 1 | 0 | IN
110 | WIR-SURV-050 | 1 | General | Zone: 2 Building: Control Room | Plain Concrete (PC) |  |  | 2025-11-17 | 2026-11-18 | B | CLOSED | 1 | 0 | IN
111 | WIR-SURV-051 | 1 | General | Zone: 2 Building: Control Room | Reinforced Concrete (RC) |  |  | 2025-11-17 | 2026-11-18 | B | CLOSED | 1 | 0 | IN
112 | WIR-SURV-052 | 1 | General | Zone: 2 Building: Control Room | Columns |  |  | 2025-11-17 | 2026-11-18 | B | CLOSED | 1 | 0 | IN
113 | WIR-SURV-053 | 1 | General | Zone: 2 Building: Maintance Store | Excavation Level |  |  | 2025-11-17 | 2026-11-18 | B | CLOSED | 1 | 0 | IN
114 | WIR-SURV-054 | 1 | General | Zone: 2 Building: Maintance Store | Plain Concrete (PC) |  |  | 2025-11-17 | 2026-11-18 | B | CLOSED | 1 | 0 | IN
115 | WIR-SURV-055 | 1 | General | Zone: 2 Building: Maintance Store | Reinforced Concrete (RC) |  |  | 2025-11-17 | 2026-11-18 | B | CLOSED | 1 | 0 | IN
116 | WIR-SURV-056 | 1 | General | Zone: 2 Building: Maintance Store | Columns |  |  | 2025-11-17 | 2026-11-18 | B | CLOSED | 1 | 0 | IN
117 | WIR-SURV-057 | 1 | General | Zone: 2 Building: Frist Aid | Excavation Level |  |  | 2025-11-17 | 2026-11-18 | B | CLOSED | 1 | 0 | IN
118 | WIR-SURV-058 | 1 | General | Zone: 2 Building: Frist Aid | Plain Concrete (PC) |  |  | 2025-11-17 | 2026-11-18 | B | CLOSED | 1 | 0 | IN
119 | WIR-SURV-059 | 1 | General | Zone: 2 Building: Frist Aid | Reinforced Concrete (RC) |  |  | 2025-11-17 | 2026-11-18 | B | CLOSED | 1 | 0 | IN
120 | WIR-SURV-060 | 1 | General | Zone: 2 Building: Frist Aid | Columns |  |  | 2025-11-17 | 2026-11-18 | B | CLOSED | 1 | 0 | IN
121 | WIR-SURV-61 | 0 | General | ZONE : 3 | Excavation Level |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
122 | WIR-SURV-62 | 0 | General | ZONE : 3 | Plain Concrete (PC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
123 | WIR-SURV-63 | 0 | General | ZONE : 3 | Reinforced Concrete (RC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
124 | WIR-SURV-64 | 0 | General | ZONE : 3 | Columns |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
125 | WIR-SURV-65 | 0 | General | ZONE : 3 | Foundation Level |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
126 | WIR-SURV-66 | 0 | General | ZONE : 3 | Plain Concrete (PC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
127 | WIR-SURV-67 | 0 | General | ZONE : 3 | Reinforced Concrete (RC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
128 | WIR-SURV-68 | 0 | General | ZONE : 3 | Columns |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
129 | WIR-SURV-69 | 0 | General | ZONE : 3 | Foundation Level |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
130 | WIR-SURV-70 | 0 | General | ZONE : 3 | Plain Concrete (PC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
131 | WIR-SURV-71 | 0 | General | ZONE : 3 | Reinforced Concrete (RC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
132 | WIR-SURV-72 | 0 | General | ZONE : 3 | Columns |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
133 | WIR-SURV-73 | 0 | General | ZONE : 3 | Foundation Level |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
134 | WIR-SURV-74 | 0 | General | ZONE : 3 | Plain Concrete (PC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
135 | WIR-SURV-75 | 0 | General | ZONE : 3 | Reinforced Concrete (RC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
136 | WIR-SURV-76 | 0 | General | ZONE : 3 | Columns |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
137 | WIR-SURV-77 | 0 | General | ZONE : 3 | Foundation Level |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
138 | WIR-SURV-78 | 0 | General | ZONE : 3 | Plain Concrete (PC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
139 | WIR-SURV-79 | 0 | General | ZONE : 3 | Reinforced Concrete (RC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
140 | WIR-SURV-80 | 0 | General | ZONE : 3 | Columns |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
141 | WIR-SURV-81 | 0 | General | ZONE : 3 | Foundation Level |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
142 | WIR-SURV-82 | 0 | General | ZONE : 3 | Plain Concrete (PC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
143 | WIR-SURV-83 | 0 | General | ZONE : 3 | Reinforced Concrete (RC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
144 | WIR-SURV-84 | 0 | General | ZONE : 3 | Columns |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
145 | WIR-SURV-85 | 0 | General | ZONE : 3 | Foundation Level |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
146 | WIR-SURV-86 | 0 | General | ZONE : 3 | Plain Concrete (PC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
147 | WIR-SURV-87 | 0 | General | ZONE : 3 | Reinforced Concrete (RC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
148 | WIR-SURV-88 | 0 | General | ZONE : 3 | Columns |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
149 | WIR-SURV-89 | 0 | General | ZONE : 3 | Foundation Level |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
150 | WIR-SURV-90 | 0 | General | ZONE : 3 | Plain Concrete (PC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
151 | WIR-SURV-91 | 0 | General | ZONE : 3 | Reinforced Concrete (RC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
152 | WIR-SURV-92 | 0 | General | ZONE : 3 | Columns |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
153 | WIR-SURV-93 | 0 | General | ZONE : 3 | Foundation Level |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
154 | WIR-SURV-94 | 0 | General | ZONE : 3 | Plain Concrete (PC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
155 | WIR-SURV-95 | 0 | General | ZONE : 3 | Reinforced Concrete (RC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
156 | WIR-SURV-96 | 0 | General | ZONE : 3 | Columns |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
157 | WIR-SURV-97 | 0 | General | ZONE : 3 | Foundation Level |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
158 | WIR-SURV-98 | 0 | General | ZONE : 3 | Plain Concrete (PC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
159 | WIR-SURV-99 | 0 | General | ZONE : 3 | Reinforced Concrete (RC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
160 | WIR-SURV-100 | 0 | General | ZONE : 3 | Columns |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
161 | WIR-SURV-101 | 0 | General | ZONE : 3 | Foundation Level |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
162 | WIR-SURV-102 | 0 | General | ZONE : 3 | Plain Concrete (PC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
163 | WIR-SURV-103 | 0 | General | ZONE : 3 | Reinforced Concrete (RC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
164 | WIR-SURV-104 | 0 | General | ZONE : 3 | Columns |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
165 | WIR-SURV-105 | 0 | General | ZONE : 3 | Excavation Level |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
166 | WIR-SURV-106 | 0 | General | ZONE : 3 | Plain Concrete (PC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
167 | WIR-SURV-107 | 0 | General | ZONE : 3 | Reinforced Concrete (RC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
168 | WIR-SURV-108 | 0 | General | ZONE : 3 | Columns |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
169 | WIR-SURV-109 | 0 | General | ZONE : 3 | Excavation Level |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
170 | WIR-SURV-110 | 0 | General | ZONE : 3 | Plain Concrete (PC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
171 | WIR-SURV-111 | 0 | General | ZONE : 3 | Reinforced Concrete (RC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
172 | WIR-SURV-112 | 0 | General | ZONE : 3 | Columns |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
173 | WIR-SURV-113 | 0 | General | ZONE : 3 | Excavation Level |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
174 | WIR-SURV-114 | 0 | General | ZONE : 3 | Plain Concrete (PC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
175 | WIR-SURV-115 | 0 | General | ZONE : 3 | Reinforced Concrete (RC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
176 | WIR-SURV-116 | 0 | General | ZONE : 3 | Columns |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
177 | WIR-SURV-117 | 0 | General | ZONE : 3 | Excavation Level |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
178 | WIR-SURV-118 | 0 | General | ZONE : 3 | Plain Concrete (PC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
179 | WIR-SURV-119 | 0 | General | ZONE : 3 | Reinforced Concrete (RC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
180 | WIR-SURV-120 | 0 | General | ZONE : 3 | Columns |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
181 | WIR-SURV-121 | 0 | General | ZONE : 3 | Excavation Level |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
182 | WIR-SURV-122 | 0 | General | ZONE : 3 | Plain Concrete (PC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
183 | WIR-SURV-123 | 0 | General | ZONE : 3 | Reinforced Concrete (RC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
184 | WIR-SURV-124 | 0 | General | ZONE : 3 | Columns |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
185 | WIR-SURV-125 | 0 | General | ZONE : 3 | Foundation Level |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
186 | WIR-SURV-126 | 0 | General | ZONE : 3 | Plain Concrete (PC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
187 | WIR-SURV-127 | 0 | General | ZONE : 3 | Reinforced Concrete (RC) |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
188 | WIR-SURV-128 | 0 | General | ZONE : 3 | Columns |  |  | 2025-11-29 | 2026-12-03 | B | CLOSED | 4 | 0 | IN
189 | WIR-SURV-129 | 0 | General | ZONE : 4 | Excavation Level |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
190 | WIR-SURV-130 | 0 | General | ZONE : 4 | Plain Concrete (PC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
191 | WIR-SURV-131 | 0 | General | ZONE : 4 | Reinforced Concrete (RC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
192 | WIR-SURV-132 | 0 | General | ZONE : 4 | Columns |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
193 | WIR-SURV-133 | 0 | General | ZONE : 4 | Excavation Level |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
194 | WIR-SURV-134 | 0 | General | ZONE : 4 | Plain Concrete (PC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
195 | WIR-SURV-135 | 0 | General | ZONE : 4 | Reinforced Concrete (RC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
196 | WIR-SURV-136 | 0 | General | ZONE : 4 | Columns |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
197 | WIR-SURV-137 | 0 | General | ZONE : 4 | Excavation Level |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
198 | WIR-SURV-138 | 0 | General | ZONE : 4 | Plain Concrete (PC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
199 | WIR-SURV-139 | 0 | General | ZONE : 4 | Reinforced Concrete (RC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
200 | WIR-SURV-140 | 0 | General | ZONE : 4 | Columns |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
201 | WIR-SURV-141 | 0 | General | ZONE : 4 | Excavation Level |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
202 | WIR-SURV-142 | 0 | General | ZONE : 4 | Plain Concrete (PC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
203 | WIR-SURV-143 | 0 | General | ZONE : 4 | Reinforced Concrete (RC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
204 | WIR-SURV-144 | 0 | General | ZONE : 4 | Columns |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
205 | WIR-SURV-145 | 0 | General | ZONE : 4 | Excavation Level |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
206 | WIR-SURV-146 | 0 | General | ZONE : 4 | Plain Concrete (PC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
207 | WIR-SURV-147 | 0 | General | ZONE : 4 | Reinforced Concrete (RC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
208 | WIR-SURV-148 | 0 | General | ZONE : 4 | Columns |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
209 | WIR-SURV-149 | 0 | General | ZONE : 4 | Excavation Level |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
210 | WIR-SURV-150 | 0 | General | ZONE : 4 | Plain Concrete (PC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
211 | WIR-SURV-151 | 0 | General | ZONE : 4 | Reinforced Concrete (RC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
212 | WIR-SURV-152 | 0 | General | ZONE : 4 | Columns |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
213 | WIR-SURV-153 | 0 | General | ZONE : 4 | Excavation Level |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
214 | WIR-SURV-154 | 0 | General | ZONE : 4 | Plain Concrete (PC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
215 | WIR-SURV-155 | 0 | General | ZONE : 4 | Reinforced Concrete (RC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
216 | WIR-SURV-156 | 0 | General | ZONE : 4 | Columns |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
217 | WIR-SURV-157 | 0 | General | ZONE : 4 | Excavation Level |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
218 | WIR-SURV-158 | 0 | General | ZONE : 4 | Plain Concrete (PC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
219 | WIR-SURV-159 | 0 | General | ZONE : 4 | Reinforced Concrete (RC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
220 | WIR-SURV-160 | 0 | General | ZONE : 4 | Columns |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
221 | WIR-SURV-161 | 0 | General | ZONE : 4 | Excavation Level |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
222 | WIR-SURV-162 | 0 | General | ZONE : 4 | Plain Concrete (PC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
223 | WIR-SURV-163 | 0 | General | ZONE : 4 | Reinforced Concrete (RC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
224 | WIR-SURV-164 | 0 | General | ZONE : 4 | Columns |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
225 | WIR-SURV-165 | 0 | General | ZONE : 4 | Excavation Level |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
226 | WIR-SURV-166 | 0 | General | ZONE : 4 | Plain Concrete (PC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
227 | WIR-SURV-167 | 0 | General | ZONE : 4 | Reinforced Concrete (RC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
228 | WIR-SURV-168 | 0 | General | ZONE : 4 | Columns |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
229 | WIR-SURV-169 | 0 | General | ZONE : 4 | Excavation Level |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
230 | WIR-SURV-170 | 0 | General | ZONE : 4 | Plain Concrete (PC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
231 | WIR-SURV-171 | 0 | General | ZONE : 4 | Reinforced Concrete (RC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
232 | WIR-SURV-172 | 0 | General | ZONE : 4 | Columns |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
233 | WIR-SURV-173 | 0 | General | ZONE : 4 | Excavation Level |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
234 | WIR-SURV-174 | 0 | General | ZONE : 4 | Plain Concrete (PC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
235 | WIR-SURV-175 | 0 | General | ZONE : 4 | Reinforced Concrete (RC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
236 | WIR-SURV-176 | 0 | General | ZONE : 4 | Columns |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
237 | WIR-SURV-177 | 0 | General | ZONE : 4 | Excavation Level |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
238 | WIR-SURV-178 | 0 | General | ZONE : 4 | Plain Concrete (PC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
239 | WIR-SURV-179 | 0 | General | ZONE : 4 | Reinforced Concrete (RC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
240 | WIR-SURV-180 | 0 | General | ZONE : 4 | Columns |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
241 | WIR-SURV-181 | 0 | General | ZONE : 4 | Excavation Level |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
242 | WIR-SURV-182 | 0 | General | ZONE : 4 | Plain Concrete (PC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
243 | WIR-SURV-183 | 0 | General | ZONE : 4 | Reinforced Concrete (RC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
244 | WIR-SURV-184 | 0 | General | ZONE : 4 | Columns |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
245 | WIR-SURV-185 | 0 | General | ZONE : 4 | Excavation Level |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
246 | WIR-SURV-186 | 0 | General | ZONE : 4 | Plain Concrete (PC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
247 | WIR-SURV-187 | 0 | General | ZONE : 4 | Reinforced Concrete (RC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
248 | WIR-SURV-188 | 0 | General | ZONE : 4 | Columns |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
249 | WIR-SURV-189 | 0 | General | ZONE : 4 | Excavation Level |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
250 | WIR-SURV-190 | 0 | General | ZONE : 4 | Plain Concrete (PC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
251 | WIR-SURV-191 | 0 | General | ZONE : 4 | Reinforced Concrete (RC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
252 | WIR-SURV-192 | 0 | General | ZONE : 4 | Columns |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
253 | WIR-SURV-193 | 0 | General | ZONE : 4 | Excavation Level |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
254 | WIR-SURV-194 | 0 | General | ZONE : 4 | Plain Concrete (PC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
255 | WIR-SURV-195 | 0 | General | ZONE : 4 | Reinforced Concrete (RC) |  |  | 2025-12-13 | 2026-12-16 | B | CLOSED | 368 | 0 | IN
256 | WIR-SURV-196 | 0 | General | Zone: 2 | (Excavation Level) = F.F.L- 0.60 |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
257 | WIR-SURV-197 | 0 | General | Zone: 2 | (Plain Concrete (PC)) = F.F.L - 0.50 |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
258 | WIR-SURV-198 | 0 | General | Zone: 2 | (Reinforced Concrete (RC)) = F.F.L |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
259 | WIR-SURV-199 | 0 | General | Zone: 2 | (Columns) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
260 | WIR-SURV-200 | 0 | General | ZONE : 3 | (Excavation Level) = F.F.L- 0.60 |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
261 | WIR-SURV-201 | 0 | General | ZONE : 3 | (Plain Concrete (PC)) = F.F.L - 0.50 |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
262 | WIR-SURV-202 | 0 | General | ZONE : 3 | (Reinforced Concrete (RC)) = F.F.L |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
263 | WIR-SURV-203 | 0 | General | ZONE : 3 | (Columns) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
264 | WIR-SURV-204 | 0 | General | ZONE : 4 | (Excavation Level) = F.F.L- 0.60 |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
265 | WIR-SURV-205 | 0 | General | ZONE : 4 | (Plain Concrete (PC)) = F.F.L - 0.50 |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
266 | WIR-SURV-206 | 0 | General | ZONE : 4 | (Reinforced Concrete (RC)) = F.F.L |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
267 | WIR-SURV-207 | 0 | General | ZONE : 4 | (Columns) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
268 | WIR-SURV-208 | 0 | General | Zone: 2 | (Excavation Level) |  |  | 2026-01-23 |  | B | PENDING | 25 | 0 | IN
269 | WIR-SURV-209 | 0 | General | Zone: 2 | (Plain Concrete (PC)) |  |  | 2026-01-23 |  | B | PENDING | 25 | 0 | IN
270 | WIR-SURV-210 | 0 | General | Zone: 2 | (Reinforced Concrete (RC)) |  |  | 2026-01-23 |  | B | PENDING | 25 | 0 | IN
271 | WIR-SURV-211 | 0 | General | Zone: 2 | (Excavation Level) |  |  | 2026-01-23 |  | B | PENDING | 25 | 0 | IN
272 | WIR-SURV-212 | 0 | General | Zone: 2 | (Plain Concrete (PC)) |  |  | 2026-01-23 |  | B | PENDING | 25 | 0 | IN
273 | WIR-SURV-213 | 0 | General | Zone: 2 | (Reinforced Concrete (RC)) |  |  | 2026-01-23 |  | B | PENDING | 25 | 0 | IN
274 | WIR-SURV-214 | 0 | General | Zone: 2 | (Plain Concrete (PC)) |  |  | 2026-01-23 |  | B | PENDING | 25 | 0 | IN
275 | WIR-SURV-215 | 0 | General | Zone: 2 | (Reinforced Concrete (RC)) |  |  | 2026-01-23 |  | B | PENDING | 25 | 0 | IN
276 | WIR-SURV-216 | 0 | General |  |  |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
277 | WIR-SURV-217 | 0 | General | Zone: 2 | (Plain Concrete (PC)) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
278 | WIR-SURV-218 | 0 | General | Zone: 2 | (Reinforced Concrete (RC)) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
279 | WIR-SURV-219 | 0 | General | Zone: 2 | (Excavation Level) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
280 | WIR-SURV-220 | 0 | General | Zone: 2 | (Excavation Level) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
281 | WIR-SURV-221 | 0 | General | Zone: 2 | (Plain Concrete (PC)) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
282 | WIR-SURV-222 | 0 | General | Zone: 2 | (Reinforced Concrete (RC)) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
283 | WIR-SURV-223 | 0 | General | Zone: 2 | (Excavation Level) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
284 | WIR-SURV-224 | 0 | General | Zone: 2 | (Plain Concrete (PC)) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
285 | WIR-SURV-225 | 0 | General | Zone: 2 | (Reinforced Concrete (RC)) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
286 | WIR-SURV-226 | 0 | General | Zone: 2 | (Excavation Level) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
287 | WIR-SURV-227 | 0 | General | Zone: 2 | (Plain Concrete (PC)) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
288 | WIR-SURV-228 | 0 | General | Zone: 2 | (Reinforced Concrete (RC)) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
289 | WIR-SURV-229 | 0 | General | Zone: 2 | (Excavation Level) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
290 | WIR-SURV-230 | 0 | General | Zone: 2 | (Plain Concrete (PC)) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
291 | WIR-SURV-231 | 0 | General | Zone: 2 | (Reinforced Concrete (RC)) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
292 | WIR-SURV-232 | 0 | General | Zone: 2 | (Excavation Level) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
293 | WIR-SURV-233 | 0 | General | Zone: 2 | (Plain Concrete (PC)) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
294 | WIR-SURV-234 | 0 | General | Zone: 2 | (Reinforced Concrete (RC)) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
295 | WIR-SURV-235 | 0 | General | Zone: 2 | (Excavation Level) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
296 | WIR-SURV-236 | 0 | General | Zone: 2 | (Plain Concrete (PC)) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
297 | WIR-SURV-237 | 0 | General | Zone: 2 | (Reinforced Concrete (RC)) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
298 | WIR-SURV-238 | 0 | General | Zone: 2 | (Excavation Level) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
299 | WIR-SURV-239 | 0 | General | Zone: 2 | (Plain Concrete (PC)) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
300 | WIR-SURV-240 | 0 | General | Zone: 2 | (Reinforced Concrete (RC)) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
301 | WIR-SURV-241 | 0 | General | Zone: 2 | (Excavation Level) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
302 | WIR-SURV-242 | 0 | General | Zone: 2 | (Plain Concrete (PC)) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
303 | WIR-SURV-243 | 0 | General | Zone: 2 | (Reinforced Concrete (RC)) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
304 | WIR-SURV-244 | 0 | General | Zone: 2 | (Excavation Level) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
305 | WIR-SURV-245 | 0 | General | Zone: 2 | (Plain Concrete (PC)) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
306 | WIR-SURV-246 | 0 | General | Zone: 2 | (Reinforced Concrete (RC)) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
307 | WIR-SURV-247 | 0 | General | Zone: 2 | (Excavation Level) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
308 | WIR-SURV-248 | 0 | General | Zone: 2 | (Plain Concrete (PC)) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
309 | WIR-SURV-249 | 0 | General | Zone: 2 | (Reinforced Concrete (RC)) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
310 | WIR-SURV-250 | 0 | General | Zone: 2 | (Excavation Level) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
311 | WIR-SURV-251 | 0 | General | Zone: 2 | (Plain Concrete (PC)) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
312 | WIR-SURV-252 | 0 | General | Zone: 2 | (Reinforced Concrete (RC)) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
313 | WIR-SURV-253 | 0 | General | Zone: 2 | (Excavation Level) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
314 | WIR-SURV-254 | 0 | General | Zone: 2 | (Plain Concrete (PC)) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
315 | WIR-SURV-255 | 0 | General | Zone: 2 | (Reinforced Concrete (RC)) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
316 | WIR-SURV-256 | 0 | General | Zone: 2 | (Excavation Level) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
317 | WIR-SURV-257 | 0 | General | Zone: 2 | (Plain Concrete (PC)) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
318 | WIR-SURV-258 | 0 | General | Zone: 2 | (Reinforced Concrete (RC)) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
319 | WIR-SURV-259 | 0 | General | Zone: 2 | (Excavation Level) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
320 | WIR-SURV-260 | 0 | General | Zone: 2 | (Plain Concrete (PC)) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
321 | WIR-SURV-261 | 0 | General | Zone: 2 | (Reinforced Concrete (RC)) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
322 | WIR-SURV-262 | 0 | General | Zone: 2 | (Excavation Level) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
323 | WIR-SURV-263 | 0 | General | Zone: 2 | (Excavation Level) |  |  | 2026-01-23 | 2026-02-04 | B | CLOSED | 12 | 0 | IN
324 | WIR-SURV-264 | 0 | General | Zone: 5S FOR MAIN ROAD | (LEVEL OF 5S) |  |  | 2026-02-15 | 2026-02-12 | B | PENDING | 2 | 0 | IN
325 | WIR-SURV-265 | 0 | General |  | Asbuilt |  |  | 2026-02-15 |  | UR | PENDING | 2 | 0 | IN
326 | WIR-SURV-266 |  | General | Zone: 3&4 | (LEVEL OF 5S) |  |  | 2026-02-15 | 2026-02-12 | B | PENDING | 2 | 0 | IN
327 | WIR-SURV-267 |  | General |  | Asbuilt |  |  | 2026-02-15 |  | UR | PENDING | 2 | 0 | IN
328 | WIR-SURV-268 |  | General | Zone: 2 | LEVEL OF 5S |  |  | 2026-02-15 | 2026-02-12 | B | PENDING | 2 | 0 | IN
329 | WIR-SURV-269 |  | General |  | Check Asbuilt for Lengths at Fences in all Project up to 25-01-2026 |  |  | 2026-02-15 |  | UR | PENDING | 2 | 0 | IN
330 | WIR-SURV-270 |  | General | WILD LIFE | (Excavation Level) |  |  | 2026-02-15 | 2026-02-02 | B | PENDING | 2 | 0 | IN
331 | WIR-SURV-271 |  | General | WILD LIFE | (Plain Concrete (PC)) |  |  | 2026-02-15 | 2026-02-02 | B | PENDING | 2 | 0 | IN
332 | WIR-SURV-272 |  | General | WILD LIFE | Columns |  |  | 2026-02-15 | 2026-02-02 | B | PENDING | 2 | 0 | IN
333 | WIR-SURV-273 |  | General | WILD LIFE | (Reinforced Concrete (RC)) |  |  | 2026-02-15 | 2026-02-02 | B | PENDING | 2 | 0 | IN
334 | WIR-SURV-274 |  | General | playground | (Excavation Level) |  |  | 2026-02-15 | 2026-02-02 | B | PENDING | 2 | 0 | IN
335 | WIR-SURV-275 |  | General | playground | (Plain Concrete (PC)) |  |  | 2026-02-15 | 2026-02-02 | B | PENDING | 2 | 0 | IN
336 | WIR-SURV-276 |  | General | playground | (Reinforced Concrete (RC)) |  |  | 2026-02-15 | 2026-02-02 | B | PENDING | 2 | 0 | IN
337 | WIR-SURV-277 |  | General | playground | Columns |  |  | 2026-02-15 | 2026-02-02 | B | PENDING | 2 | 0 | IN
338 | WIR-SURV-278 |  | General | mosque | (Excavation Level) |  |  | 2026-02-15 | 2026-02-02 | B | PENDING | 2 | 0 | IN
339 | WIR-SURV-279 |  | General | mosque | (Plain Concrete (PC)) |  |  | 2026-02-15 | 2026-02-02 | B | PENDING | 2 | 0 | IN
340 | WIR-SURV-280 |  | General | mosque | (Reinforced Concrete (RC)) |  |  | 2026-02-15 | 2026-02-02 | B | PENDING | 2 | 0 | IN
341 | WIR-SURV-281 |  | General | mosque | Columns |  |  | 2026-02-15 | 2026-02-02 | B | PENDING | 2 | 0 | IN
| WIR-SURV-282 |  |  | Zone: 2 | (Excavation Level)
Formulas:
Duration = IF([REV]=0,[Outgoing to Consultant]+1,IF([REV]>0,[Outgoing to Consultant]+1))
Owner Logo
Consultant Logo

## SUMMARY REPORTS
D
[17 empty] | WORK ACTIVITIES | Code Action |  | Issue for | FLOOR | ELEMENT
|  |  | 1686 |  | INSPECTION REQUEST FOR All PROJECT | [11 empty] | Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10
[5 empty] | A | B | C | UR | D | [7 empty] | STR | A | APPROVED | APPROVAL |  | str | serv | arch | elec | mech
|  | 2123 | 1686 |  | 0 | 1203 | 115 | 345 | 0 | 1663 | [6 empty] | ARCH | B | APPROVE AS NOTET | INFORMATION | PC | Concrete | Concrete | Block | Lighting
[5 empty] | 0% | 71.35% | 6.821% | 20.46% | 0% | [7 empty] | ELEC | C | REVICE & RESUBMIT |  | RC | Con.slabs | Con.slabs | Cladding | Power
Description | Code | Quantity | [8 empty] | 661 | 175 | 203 | 771 | 341 | 2151 | MECH | D | REJECTED |  | B.COL | Insulation | Block | Plastering | Low Current
IR SU | A | 0 | [14 empty] | SERV | UR | UNDER REVIEW |  | G.COL | Back Filling | Cladding | Insulation
| B | 279 | 279 | Profast-PROJECT NAME INSPECTION REQUEST | [12 empty] | SEFT | CA | CANCEL |  | 1.COL | Excavation | Plastering | Painting
| CC | 59 | 0 | [13 empty] | MATERAIL | CC | Not Resubmitted |  | 2.COL | Finishing | Insulation | Marble
| UR | 3 | 0 | [13 empty] | Column1: G; Column2: C , B; Column5: 3.COL; Column7: Back Filling; Column8: Stone
| D | 0 | 0 | [13 empty] | Column5: 4.COL; Column7: Painting; Column8: G.poard
|  | 341 | 279 | [13 empty] | Column5: R.COL; Column7: Excavation; Column8: celar
[20 empty] | B.FLOOR | B.SLAB |  | General
Description | Code | Quantity | [14 empty] | Column4: G.FLOOR; Column5: G.SLAB; Column8: Handrail
IR STR | A | 0 | [14 empty] | Column4: 1.FLOOR; Column5: 1.SLAB; Column8: GRC
| B | 289 | 364 | [13 empty] | Column4: 2.FLOOR; Column5: 2.SLAB
| CC | 192 | 70 | [13 empty] | Column4: 3.FLOOR; Column5: 3.SLAB
| UR | 152 | 71 | [13 empty] | Column4: 4.FLOOR; Column5: 4.SLAB
| D | 16 | 18 | [13 empty] | Column4: R.FLOOR; Column5: R.SLAB
|  | 649 | 523 | [13 empty] | Column4: Landscap; Column5: Re.Wall
[20 empty] | Roods | Stairs
S.O.G
Description | Code | Quantity | [14 empty] | Column5: GENERAL
IR ELEC | A | 0 | [14 empty] | Column5: ELEV
| B | 38 | 70 | [13 empty] | Column5: Ramp
| CC | 23 | 21 | [13 empty] | Column5: Core
| UR | 141 | 2 | [13 empty] | Column5: Tank
| D | 1 | 1 | [13 empty] | Column5: Post
|  | 203 | 94 | [13 empty] | Column5: Entrance
Description | Code | Quantity
IR MECH | A | 0
| B | 277 | 480
| CC | 19 | 2
| UR | 457 | 250
| D | 0 | 0
|  | 753 | 732
Description | Code | Quantity
IR ARCH | A | 0
| B | 12 | 10
| CC | 22 | 22
| UR | 139 | 22
| D | 4 | 4
|  | 177 | 58

## Rola
Inspection Request - SURV
DOCUMENT REFERENCE NO |  |  | Element | Location | DESCRIPTION | Attachment |  | Outgoing to Consultant
No. | Reference | REV |  |  |  | Dwg | Report | Submission date | Received Date
1 | WIR-CIVIL-23 |  | STR |  |  |  |  | 2025-11-29
2 | WIR-CIVIL-24 |  | STR |  |  |  |  | 2025-11-29
3 | WIR-CIVIL-25 |  | STR |  |  |  |  | 2025-11-29
4 | WIR-CIVIL-26 |  | STR |  |  |  |  | 2025-11-29
5 | WIR-CIVIL-27 |  | STR |  |  |  |  | 2025-11-29
6 | WIR-CIVIL-28 |  | STR |  |  |  |  | 2025-11-29
7 | WIR-CIVIL-29 |  | STR |  |  |  |  | 2025-11-29
#REF! | WIR-CIVIL-30 |  | STR |  |  |  |  | 2025-11-29
8 | WIR-CIVIL-31 |  | STR |  |  |  |  | 2025-11-29
9 | WIR-CIVIL-32 |  | STR |  |  |  |  | 2025-11-29
10 | WIR-CIVIL-33 |  | STR |  |  |  |  | 2025-11-29
11 | WIR-CIVIL-34 |  | STR |  |  |  |  | 2025-11-29
12 | WIR-CIVIL-35 |  | STR |  |  |  |  | 2025-11-29
13 | WIR-CIVIL-36 |  | STR |  |  |  |  | 2025-11-29
14 | WIR-CIVIL-37 |  | STR |  |  |  |  | 2025-11-29
15 | WIR-CIVIL-38 |  | STR |  |  |  |  | 2025-11-29
16 | WIR-CIVIL-39 |  | STR |  |  |  |  | 2025-11-29
17 | WIR-CIVIL-40 |  | STR |  |  |  |  | 2025-11-29
18 | WIR-CIVIL-41 |  | STR |  |  |  |  | 2025-11-29
19 | WIR-CIVIL-42 |  | STR |  |  |  |  | 2025-11-29
20 | WIR-CIVIL-43 |  | STR |  |  |  |  | 2025-11-29
21 | WIR-CIVIL-44 |  | STR |  |  |  |  | 2025-11-29
22 | WIR-CIVIL-45 |  | STR |  |  |  |  | 2025-11-29
23 | WIR-CIVIL-46 |  | STR |  |  |  |  | 2025-11-29
24 | WIR-CIVIL-47 |  | STR |  |  |  |  | 2025-11-29
25 | WIR-CIVIL-48 |  | STR |  |  |  |  | 2025-11-29
26 | WIR-CIVIL-49 |  | STR |  |  |  |  | 2025-11-29
27 | WIR-CIVIL-50 |  | STR |  |  |  |  | 2025-11-29
28 | WIR-CIVIL-51 |  | STR |  |  |  |  | 2025-11-29
29 | WIR-CIVIL-52 |  | STR |  |  |  |  | 2025-11-29
30 | WIR-CIVIL-53 |  | STR |  |  |  |  | 2025-11-29
31 | WIR-CIVIL-54 |  | STR |  |  |  |  | 2025-11-29
32 | WIR-CIVIL-55 |  | STR |  |  |  |  | 2025-11-29
33 | WIR-CIVIL-56 |  | STR |  |  |  |  | 2025-11-29
34 | WIR-CIVIL-57 |  | STR |  |  |  |  | 2025-11-29
35 | WIR-CIVIL-58 |  | STR |  |  |  |  | 2025-11-29
36 | WIR-CIVIL-59 |  | STR |  |  |  |  | 2025-11-29
37 | WIR-CIVIL-60 |  | STR |  |  |  |  | 2025-11-29
38 | WIR-CIVIL-61 |  | STR |  |  |  |  | 2025-11-29
39 | WIR-CIVIL-62 |  | STR |  |  |  |  | 2025-11-29
40 | WIR-CIVIL-63 |  | STR |  |  |  |  | 2025-11-29
41 | WIR-CIVIL-64 |  | STR |  |  |  |  | 2025-11-29
42 | WIR-CIVIL-65 |  | STR |  |  |  |  | 2025-11-29
43 | WIR-CIVIL-66 |  | STR |  |  |  |  | 2025-11-29
44 | WIR-CIVIL-67 |  | STR |  |  |  |  | 2025-11-29
45 | WIR-CIVIL-68 |  | STR |  |  |  |  | 2025-11-29
46 | WIR-CIVIL-69 |  | STR |  |  |  |  | 2025-11-29
47 | WIR-CIVIL-70 |  | STR |  |  |  |  | 2025-11-29
48 | WIR-CIVIL-71 |  | STR |  |  |  |  | 2025-11-29
49 | WIR-CIVIL-72 |  | STR |  |  |  |  | 2025-11-29
50 | WIR-CIVIL-73 |  | STR |  |  |  |  | 2025-11-29
51 | WIR-CIVIL-74 |  | STR |  |  |  |  | 2025-11-29
52 | WIR-CIVIL-75 |  | STR |  |  |  |  | 2025-11-29
53 | WIR-CIVIL-76 |  | STR |  |  |  |  | 2025-11-29
54 | WIR-CIVIL-77 |  | STR |  |  |  |  | 2025-11-29
55 | WIR-CIVIL-78 |  | STR |  |  |  |  | 2025-11-29
56 | WIR-CIVIL-79 |  | STR |  |  |  |  | 2025-11-29
57 | WIR-CIVIL-80 |  | STR |  |  |  |  | 2025-11-29
58 | WIR-CIVIL-81 |  | STR |  |  |  |  | 2025-11-29
59 | WIR-CIVIL-82 |  | STR |  |  |  |  | 2025-11-29
60 | WIR-CIVIL-83 |  | STR |  |  |  |  | 2025-11-29
61 | WIR-CIVIL-84 |  | STR |  |  |  |  | 2025-11-29
62 | WIR-CIVIL-85 |  | STR |  |  |  |  | 2025-11-29
63 | WIR-CIVIL-86 |  | STR |  |  |  |  | 2025-11-29
64 | WIR-CIVIL-87 |  | STR |  |  |  |  | 2025-11-29
65 | WIR-CIVIL-88 |  | STR |  |  |  |  | 2025-11-29
66 | WIR-CIVIL-89 |  | STR |  |  |  |  | 2025-11-29
67 | WIR-CIVIL-90 |  | STR |  |  |  |  | 2025-11-29
68 | WIR-CIVIL-91 |  | STR |  |  |  |  | 2025-11-29
69 | WIR-CIVIL-92 |  | STR |  |  |  |  | 2025-11-29
70 | WIR-CIVIL-93 |  | STR |  |  |  |  | 2025-11-29
71 | WIR-CIVIL-94 |  | STR |  |  |  |  | 2025-11-29
72 | WIR-CIVIL-95 |  | STR |  |  |  |  | 2025-11-29
73 | WIR-CIVIL-96 |  | STR |  |  |  |  | 2025-11-29
74 | WIR-CIVIL-97 |  | STR |  |  |  |  | 2025-11-29
75 | WIR-CIVIL-98 |  | STR |  |  |  |  | 2025-11-29
76 | WIR-CIVIL-99 |  | STR |  |  |  |  | 2025-11-29
77 | WIR-CIVIL-100 |  | STR |  |  |  |  | 2025-11-29
78 | WIR-CIVIL-101 |  | STR |  |  |  |  | 2025-11-29
79 | WIR-CIVIL-102 |  | STR |  |  |  |  | 2025-11-29
80 | WIR-CIVIL-103 |  | STR |  |  |  |  | 2025-11-29
81 | WIR-CIVIL-104 |  | STR |  |  |  |  | 2025-11-29
82 | WIR-CIVIL-105 |  | STR |  |  |  |  | 2025-11-29
83 | WIR-CIVIL-106 |  | STR |  |  |  |  | 2025-11-29
266 | WIR-Civil-201 | 0 | STR | ZONE :3-4 Building : Q-C(03-04) | Prevention Termites . Polythene Sheet |  |  | 2026-01-26
267 | WIR-Civil-202 | 0 | STR | ZONE :3-4 Building : Q-C(03-04) | Form Work of P.C Footing |  |  | 2026-01-26
268 | WIR-Civil-203 | 0 | STR | ZONE :3-4 Building : Q-C(03-04) | Pouring For P.C Footing |  |  | 2026-01-26
269 | WIR-Civil-204 | 0 | STR | ZONE :3-4 Building : Q-C(03-04) | Form and Steel Work of R.C raft |  |  | 2026-01-26
270 | WIR-Civil-205 | 0 | STR | ZONE :3-4 Building : Q-C(03-04) | Pouring For R.C raft |  |  | 2026-01-26
271 | WIR-Civil-206 | 0 | STR | ZONE :3-4 Building : Q-C(03-04) | Surface Preparation for R.C Footing Before Insulation |  |  | 2026-01-26
272 | WIR-Civil-207 | 0 | STR | ZONE :3-4 Building : Q-C(03-04) | Insulation of R.C raft |  |  | 2026-01-26
273 | WIR-Civil-208 | 0 | STR | ZONE :3-4 Building : Q-C(03-04) | Steel structure working |  |  | 2026-01-26
274 | WIR-Civil-209 | 0 | STR | ZONE :3-4 Building : Q-C(03-04) | Pouring For Screed ( ground floor ) |  |  | 2026-01-26
275 | WIR-Civil-210 | 0 | STR | ZONE :3-4 Building : Q-C(03-04) | Installation of H.C.S |  |  | 2026-01-26
276 | WIR-Civil-211 | 0 | STR | ZONE :3-4 Building : Q-C(03-04) | Steel works of Screed after H.C.S |  |  | 2026-01-26
277 | WIR-Civil-212 | 0 | STR | ZONE :3-4 Building : Q-C(03-04) | Pouring For Screed |  |  | 2026-01-26
278 | WIR-Civil-213 | 0 | STR | ZONE :3-4 Building : Q-C(05-06) | Prevention Termites . Polythene Sheet |  |  | 2026-01-26
279 | WIR-Civil-214 | 0 | STR | ZONE :3-4 Building : Q-C(05-06) | Form Work of P.C Footing |  |  | 2026-01-26
280 | WIR-Civil-215 | 0 | STR | ZONE :3-4 Building : Q-C(05-06) | Pouring For P.C Footing |  |  | 2026-01-26
281 | WIR-Civil-216 | 0 | STR | ZONE :3-4 Building : Q-C(05-06) | Form and Steel Work of R.C raft |  |  | 2026-01-26
282 | WIR-Civil-217 | 0 | STR | ZONE :3-4 Building : Q-C(05-06) | Pouring For R.C raft |  |  | 2026-01-26
283 | WIR-Civil-218 | 0 | STR | ZONE :3-4 Building : Q-C(05-06) | Surface Preparation for R.C Footing Before Insulation |  |  | 2026-01-26
284 | WIR-Civil-219 | 0 | STR | ZONE :3-4 Building : Q-C(05-06) | Insulation of R.C raft |  |  | 2026-01-26
285 | WIR-Civil-220 | 0 | STR | ZONE :3-4 Building : Q-C(05-06) | Steel structure working |  |  | 2026-01-26
286 | WIR-Civil-221 | 0 | STR | ZONE :3-4 Building : Q-C(05-06) | Pouring For Screed ( ground floor ) |  |  | 2026-01-26
287 | WIR-Civil-222 | 0 | STR | ZONE :3-4 Building : Q-C(05-06) | Installation of H.C.S |  |  | 2026-01-26
288 | WIR-Civil-223 | 0 | STR | ZONE :3-4 Building : Q-C(05-06) | Steel works of Screed after H.C.S |  |  | 2026-01-26
289 | WIR-Civil-224 | 0 | STR | ZONE :3-4 Building : Q-C(05-06) | Pouring For Screed |  |  | 2026-01-26
291 | WIR-Civil-226 | 0 | STR | ZONE :3-4 Building : Q-C(07-08) | Prevention Termites . Polythene Sheet |  |  | 2026-01-26
292 | WIR-Civil-227 | 0 | STR | ZONE :3-4 Building : Q-C(07-08) | Form Work of P.C Footing |  |  | 2026-01-26
293 | WIR-Civil-228 | 0 | STR | ZONE :3-4 Building : Q-C(07-08) | Pouring For P.C Footing |  |  | 2026-01-26
294 | WIR-Civil-229 | 0 | STR | ZONE :3-4 Building : Q-C(07-08) | Form and Steel Work of R.C raft |  |  | 2026-01-26
295 | WIR-Civil-230 | 0 | STR | ZONE :3-4 Building : Q-C(07-08) | Pouring For R.C raft |  |  | 2026-01-26
296 | WIR-Civil-231 | 0 | STR | ZONE :3-4 Building : Q-C(07-08) | Surface Preparation for R.C Footing Before Insulation |  |  | 2026-01-26
297 | WIR-Civil-232 | 0 | STR | ZONE :3-4 Building : Q-C(07-08) | Insulation of R.C raft |  |  | 2026-01-26
298 | WIR-Civil-233 | 0 | STR | ZONE :3-4 Building : Q-C(07-08) | Steel structure working |  |  | 2026-01-26
299 | WIR-Civil-234 | 0 | STR | ZONE :3-4 Building : Q-C(07-08) | Pouring For Screed ( ground floor ) |  |  | 2026-01-26
300 | WIR-Civil-235 | 0 | STR | ZONE :3-4 Building : Q-C(07-08) | Installation of H.C.S |  |  | 2026-01-26
301 | WIR-Civil-236 | 0 | STR | ZONE :3-4 Building : Q-C(07-08) | Steel works of Screed after H.C.S |  |  | 2026-01-26
302 | WIR-Civil-237 | 0 | STR | ZONE :3-4 Building : Q-C(07-08) | Pouring For Screed |  |  | 2026-01-26
370 | WIR-Civil-306 | 0 | STR | ZONE : 3-4 Building : Q-C(11-12-15-16) | Prevention Termites . Polythene Sheet |  |  | 2026-01-26
371 | WIR-Civil-307 | 0 | STR | ZONE : 3-4 Building : Q-C(11-12-15-16) | Form Work of P.C Footing |  |  | 2026-01-26
372 | WIR-Civil-308 | 0 | STR | ZONE : 3-4 Building : Q-C(11-12-15-16) | Pouring For P.C Footing |  |  | 2026-01-26
373 | WIR-Civil-309 | 0 | STR | ZONE : 3-4 Building : Q-C(11-12-15-16) | Form and Steel Work of R.C raft |  |  | 2026-01-26
374 | WIR-Civil-310 | 0 | STR | ZONE : 3-4 Building : Q-C(11-12-15-16) | Pouring For R.C raft |  |  | 2026-01-26
375 | WIR-Civil-311 | 0 | STR | ZONE : 3-4 Building : Q-C(11-12-15-16) | Surface Preparation for R.C Footing Before Insulation |  |  | 2026-01-26
376 | WIR-Civil-312 | 0 | STR | ZONE : 3-4 Building : Q-C(11-12-15-16) | Insulation of R.C raft |  |  | 2026-01-26
377 | WIR-Civil-313 | 0 | STR | ZONE : 3-4 Building : Q-C(11-12-15-16) | Steel Work of Columns |  |  | 2026-01-26
378 | WIR-Civil-314 | 0 | STR | ZONE : 3-4 Building : Q-C(11-12-15-16) | Form Work of Columns |  |  | 2026-01-26
379 | WIR-Civil-315 | 0 | STR | ZONE : 3-4 Building : Q-C(11-12-15-16) | Pouring For Columns |  |  | 2026-01-26
380 | WIR-Civil-316 | 0 | STR | ZONE : 3-4 Building : Q-C(11-12-15-16) | Steel Work of Upper Beam and slab |  |  | 2026-01-26
381 | WIR-Civil-317 | 0 | STR | ZONE : 3-4 Building : Q-C(11-12-15-16) | Form Work of Upper Beam and slab |  |  | 2026-01-26
382 | WIR-Civil-318 | 0 | STR | ZONE : 3-4 Building : Q-C(11-12-15-16) | Pouring For Upper Beam ands slab |  |  | 2026-01-26
383 | WIR-Civil-319 | 0 | STR | ZONE : 3-4 Building : Q-C(11-12-15-16) | Pouring For screed ( ground floor ) |  |  | 2026-01-26
384 | WIR-Civil-320 | 0 | STR | ZONE : 3-4 Building : Q-C(11-12-15-16) | Installation of H.C.S |  |  | 2026-01-26
385 | WIR-Civil-321 | 0 | STR | ZONE : 3-4 Building : Q-C(11-12-15-16) | Steel works of Screed after H.C.S |  |  | 2026-01-26
386 | WIR-Civil-322 | 0 | STR | ZONE : 3-4 Building : Q-C(11-12-15-16) | Pouring For Screed |  |  | 2026-01-26
152 | WIR-MECH-015 |  | MECH |  |  |  |  | 2025-11-29
153 | WIR-MECH-016 |  | MECH |  |  |  |  | 2025-11-29
154 | WIR-MECH-017 |  | MECH |  |  |  |  | 2025-11-29
155 | WIR-MECH-018 |  | MECH |  |  |  |  | 2025-11-29
156 | OT-GEN-00111 |  | OTHER |  |  |  |  | 2025-11-29
Owner Logo
Consultant Logo